## Project Plan
The below planner is intended to support communities by providing a template to plan all of the major tasks that require consideration throughout the Neighbourhood Development Plan making process. We envisage communities will use this by blocking out how long they believe various tasks will take, as demonstrated below. This should help break down and focus individual tasks and give them an overall view of the number of steps required before a Neighbourhood Plan can be adopted. For ease of reference and for printing purposes, separate sheets for each stage of the process have been for groups to split down the process further, these can be accessed at the bottom of the document. This list is by no means comprehensive so if you identify any issues or additional tasks please let us know as soon as possible so we can update it for the benefit of other groups. Please notify us by email at planningpolicy@eastdevon.gov.uk
Please note this is not a deadline but an estimation of how long the development of a Neighbourhood Plan might take. You can add or remove columns as necessary.
Key
Not started
In Progress
Completed
Stage | Milestones | Suggested tasks: | How EDDC can help | Action owner | Month 1 | Month 2 | Month 3 | Month 4 | Month 5 | Month 6 | Month 7 | Month 8 | Month 9 | Month 10 | Month 11 | Month 12 | Month 13 | Month 14 | Month 15 | Month 16 | Month 17 | Month 18 | Month 19 | Month 20 | Month 21 | Month 22 | Month 23 | Month 24
1 | Getting Started
| Initial Discussions and starting the process | Holding a Parish/Town Council meeting to agree whether a Neighbourhood Plan is the right tool for the area. | Guidance on 'Is Neighbourhood Planning the right tool for you?' on EDDC website | bar: Month 1
Officers from EDDC can meet with the parish council to provide an introduction to process | bar: Month 1
| Decide on the extent of the area the plan will cover | Liasing with surrounding parishes and discussing whether to share information or do a joint plan. | EDDC can advise on appropriateness of area | bar: Month 2
| Complete and submit neighbourhood area/forum application form | Parish/Town Council to send complete Neighbourhood Area designation form and map to EDDC | EDDC can provide you with map of the proposed neighbourhood area | bar: Month 3
| Form a steering/working group | Advertise on the parish newsletter/website the intention to produce a NP and recruit members from the community alongside councillors | Guidance on 'forming the steering group' on EDDC website | bar: Month 3
Agree roles (chair, project manager, secretary etc) | bar: Month 3
Consider skills/experience/interests of steering Group | bar: Month 4
|  | Produce a terms of reference or constitution | EDDC can provide a terms of reference template
Populate the project plan (this document) with timescales and assign individual tasks.
| Apply for funding to support NP production | Apply for government grants of up to £8,000 | EDDC are also providing an additional £2000 to groups who have designated their area (make sure to apply for other funding first)
2 | Engaging the community and gathering information
| Gather baseline info and evidence | Gather existing information e.g. demographic and socio-economic information, designated/protected sites, views from any previous surveys, other relevent plan evidence | Guidance on 'gathering evidence and information' on EDDC website
Assess evidence gathered to identify gaps
Source or produce additional evidence if required
|  | Map all of the features and designations in your parish - e.g. infrastructure, trees and environmental elements, leisure/recretion facilities, shops, historical assets etc | EDDC can provide you with maps for various features, please don't hesitate to contact us.
| Engage and informally consult with community | Summarise the existing evidence base and produce a questionnaire based on the themes. You could also couple this with workshops and a launch event. | Review our 'guide to consultation' on EDDC website
|  | Analyse questionnaire responses and gauge support and understanding of neighbourhood planning, broadly define key issues and priorities from responses | Questionnaire templates on EDDC website
|  | Identify and engage with key consultees and stakeholders including potential developers and landowners | Guidance on 'who are the statutory consultees' on EDDC website.
| Decide on the scope and content | Based on consultation responses and evidence gathered, identify key themes for the Neighbourhood Plan, e.g. Housing , Design, Environment, Heritage, Community Facilities etc
|  | Develop draft vision and objectives for the Neighbourhood Plan based on evidence and consultation to date | guidance on 'producing a vision and ojectives' on EDDC website
Decide on the plan length and whether it will need to be refreshed at certain periods. e.g. Every 5 years or to coincide with local plan review
|  | check relevent strategic policies in the East Devon Local Plan aimed at your parish e.g. Housing allocations or employment allocations in your parish | EDDC can advise on what policies are relevent
|  | Conduct further workshops and consultation with the community to ensure that the vision and objectives reflect community aspirations | Review our 'guide to consultation' on EDDC website
3 | Writing the document
| Draft the plan | Based on evidence, examine potential sites for development and areas for protection | EDDC can advise on what sites were previously put forward under the SHLAA, we can also provide the sustainability criteria and site assesment process if you want to assess new sites.
|  | Consult and agree the preferred direction with landowners | EDDC can provide you with a list of non-residential rate paying addresses in your parish
|  | Decide on the basic format and layout of the plan | EDDC can provide sample plans
|  | Identify and assess various options on how to tackle the issues raised, e.g. This could be done through a sustainability appraisal or SEA if your plan requires it. | EDDC can advise on whether certain options are realistic
Decide on whether the issues can be addressed through a land-use policy or community action
|  | Draft policies and community actions | EDDC officers can offer advice, alongside guidance found on the EDDC website
|  | Request a screening opinion from EDDC as to whether your plan will require SEA or HRA | EDDC officers can offer advice on the process
|  | Start to prepare basic condition statement and consultation statement | Templates and guidance can be found on EDDC website
|  | Check conformity with the East Devon Local Plan | EDDC can advise on any conformity issues
Compile, draft and proof-read neighbourhood plan
Gain Parish or Town council endorsement
4 | Statutory consultation and submitting the plan
| Pre-submission consultation | Undertake a formal six week consultation on the draft Neighbourhood Plan as per the regulations to ensure that it reflects community aspirations
Amend the plan in response to comments received
| Finalise the Plan | Complete and finalise consultation statement and basic conditions statement
|  | Consider undertaking a 'health check' before you formally submit to EDDC | More information can be found on the NPIERS website by clicking here
| Submission and adoption of the plan | Submit the plan to EDDC with all of the supporting documentation | If EDDC has any concerns we will advise and work them through with you.
EDDC will review the Neighbourhood Plan and if it meets requirements, it will then be publicised for consultation
EDDC will appoint independant examiner with approval from the parish or town council
Independent examiner will produce a report advising whether the neighbourhood plan should proceed to referendum, subject to any modifications.
Parish Council to decide on whether to accept any recommended modifications by the examiner.
Publicise any modifications made
EDDC to organise a referendum on the final plan
Upon successful referendum, PLAN ADOPTED
5 | Delivering and monitoring the Plan
| Delivering the plan actions | Parish/Town Council to develop an Implementation Plan, e.g. working with developers and the community to follow-up any community actions | Guidance on 'after the plan is made' on EDDC website
| Monitoring progress of actions | Decide on how to monitor progress against objectives and reporting back to the community

## Getting Started
Key
Not started
In Progress
Completed
Stage | Milestones | Suggested tasks: | How EDDC can help | Action owner | Month 1 | Month 2 | Month 3 | Month 4 | Month 5 | Month 6 | Month 7 | Month 8 | Month 9 | Month 10 | Month 11 | Month 12
1 | Getting Started
| Initial Discussions and starting the process | Holding a Parish/Town Council meeting to agree whether a Neighbourhood Plan is the right tool for the area. | Guidance on 'Is Neighbourhood Planning the right tool for you?' on EDDC website | bar: Month 1
Officers from EDDC can meet with the parish council to provide an introduction to process | bar: Month 1
| Decide on the extent of the area the plan will cover | Liasing with surrounding parishes and discussing whether to share information or do a joint plan. | EDDC can advise on appropriateness of area | bar: Completed Month 2
| Complete and submit neighbourhood area/forum application form | Parish/Town Council to send complete Neighbourhood Area designation form and map to EDDC | EDDC can provide you with map of the proposed neighbourhood area | bar: Completed Month 3
| Form a steering/working group | Advertise on the parish newsletter/website the intention to produce a NP and recruit members from the community alongside councillors | Guidance on 'forming the steering group' on EDDC website | bar: Completed Month 3
Agree roles (chair, project manager, secretary etc) | bar: Completed Month 3
Consider skills/experience/interests of steering Group | bar: Completed Month 4
|  | Produce a terms of reference or constitution | EDDC can provide a terms of reference template
Populate the project plan (this document) with timescales and assign individual tasks.
| Apply for funding to support NP production | Apply for government grants of up to £8,000 | EDDC are also providing an additional £2000 to groups who have designated their area (make sure to apply for other funding first)

## Engaging the community...
Key
Not started
In Progress
Completed
Stage | Milestones | Suggested tasks: | How EDDC can help | Action owner | Month 1 | Month 2 | Month 3 | Month 4 | Month 5 | Month 6 | Month 7 | Month 8 | Month 9 | Month 10 | Month 11 | Month 12
2 | Engaging the community and gathering information
| Gather baseline info and evidence | Gather existing information e.g. demographic and socio-economic information, designated/protected sites, views from any previous surveys, other relevent plan evidence | Guidance on 'gathering evidence and information' on EDDC website
Assess evidence gathered to identify gaps
Source or produce additional evidence if required
|  | Map all of the features and designations in your parish - e.g. infrastructure, trees and environmental elements, leisure/recretion facilities, shops, historical assets etc | EDDC can provide you with maps for various features in your parish.
|  | Produce a consultation strategy, outlining how you intend to consult with the community throughout the process. | Guidance on 'producing a consultation strategy' on EDDC website.
| Engage and informally consult with community | Summarise the existing evidence base and produce a questionnaire based on the themes. You could also couple this with workshops and a launch event. | Review our 'guide to consultation' on EDDC website
|  | Analyse questionnaire responses and gauge support and understanding of neighbourhood planning, broadly define key issues and priorities from responses | Questionnaire templates on EDDC website
|  | Identify and engage with key consultees and stakeholders including potential developers and landowners | Guidance on 'who are the statutory consultees' on EDDC website.
| Decide on the scope and content | Based on consultation responses and evidence gathered, identify key themes for the Neighbourhood Plan, e.g. Housing , Design, Environment, Heritage, Community Facilities etc
|  | Develop draft vision and objectives for the Neighbourhood Plan based on evidence and consultation to date | guidance on 'producing a vision and ojectives' on EDDC website
Decide on the plan length and whether it will need to be refreshed at certain periods. e.g. Every 5 years or to coincide with local plan review
|  | check relevent strategic policies in the East Devon Local Plan aimed at your parish e.g. Housing allocations or employment allocations in your parish | EDDC can advise on what policies are relevent
|  | Conduct further workshops and consultation with the community to ensure that the vision and objectives reflect community aspirations | Review our 'guide to consultation' on EDDC website

## Writing the document
Key
Not started
In Progress
Completed
Stage | Milestones | Suggested tasks: | How EDDC can help | Action owner | Month 1 | Month 2 | Month 3 | Month 4 | Month 5 | Month 6 | Month 7 | Month 8 | Month 9 | Month 10 | Month 11 | Month 12
3 | Writing the document
| Draft the plan | Based on evidence, examine potential sites for development and areas for protection | EDDC can advise on what sites were previously put forward under the SHLAA, we can also provide the sustainability criteria and site assesment process if you want to assess new sites.
|  | Consult and agree the preferred direction with landowners | EDDC can provide you with a list of non-residential rate paying addresses in your parish
|  | Decide on the basic format and layout of the plan | EDDC can provide sample plans
|  | Identify and assess various options on how to tackle the issues raised, e.g. This could be done through a sustainability appraisal or SEA if your plan requires it. | EDDC can advise on whether certain options are realistic
Decide on whether the issues can be addressed through a land use policy or community action
|  | Draft policies and community actions | EDDC officers can offer advice, alongside guidance found on the EDDC website
|  | Request a screening opinion from EDDC as to whether your plan will require SEA or HRA | EDDC officers can offer advice on the process
|  | Start to prepare basic condition statement and consultation statement | Templates can be found on EDDC website
|  | Check conformity with the East Devon Local Plan | EDDC can advise on any conformity issues
Compile, draft and proof-read neighbourhood plan
Gain Parish or Town council endorsement

## Statutory consultation...
Key
Not started
In Progress
Completed
Stage | Milestones | Suggested tasks: | How EDDC can help | Action owner | Month 1 | Month 2 | Month 3 | Month 4 | Month 5 | Month 6 | Month 7 | Month 8 | Month 9 | Month 10 | Month 11 | Month 12
4 | Statutory consultation and submitting the plan
| Pre-submission consultation | Undertake a formal six week consultation on the draft Neighbourhood Plan as per the regulations to ensure that it reflects community aspirations
Amend the plan in response to comments received
| Finalise the Plan | Complete and finalise consultation statement and basic conditions statement
|  | Consider undertaking a 'health check' before you formally submit to EDDC | More information can be found on the NPIERS website by clicking here
| Submission and adoption of the plan | Submit the plan to EDDC with all of the supporting documentation | If EDDC has any concerns we will advise and work them through with you.
EDDC will review the Neighbourhood Plan and if it meets requirements, it will then be publicised for consultation
EDDC will appoint independant examiner with approval from the parish or town council
Independent examiner will produce a report advising whether the neighbourhood plan should proceed to referendum, subject to any modifications.
Parish Council to decide on whether to accept any recommended modifications by the examiner.
Publicise any modifications made
EDDC to organise a referendum on the final plan
Upon successful referendum, PLAN ADOPTED

## Delivering and monitoring...
Key
Not started
In Progress
Completed
Stage | Milestones | Suggested tasks: | How EDDC can help | Action owner | Month 1 | Month 2 | Month 3 | Month 4 | Month 5 | Month 6 | Month 7 | Month 8 | Month 9 | Month 10 | Month 11 | Month 12
5 | Delivering and monitoring the Plan
| Delivering the plan actions | Parish/Town Council to develop an Implementation Plan, e.g. working with developers and the community to follow-up any community actions | Guidance on 'after the plan is made' on EDDC website
| Monitoring progress of actions | Decide on how to monitor progress against objectives and reporting back to the community