## Future cost, inflation and risk
Table 5 and 6
[5 empty] | Quantity | Rate | Total
|  |  |  | Partly sunk costs as it includes part of RHDHV costs - NOT TO BE REPORTED IN TABLE 6 | 1 | 491700 | 491700 | from EDDC email on 07/10/22 |  |  |  | 291498.7
|  |  |  | Future staff costs | 1 | 50000 | 50000
|  |  |  | Consultants’ fees - Detailed design Consultant = 2.5% | 1 | 305000 | 305000 | 305000 | 2.5% of construction costs
|  |  |  | ECI | 1 | 20000 | 20000 | Assuming at least 4 meetings
|  |  |  | Other consultants - Landscape, phisical modelling | 1 | 70000 | 70000
|  |  |  | Site investigation and survey = | 1 | 375000 | 375000 | Dredging or other site investigation and surveys needed
|  |  |  | Site supervision | 1 | 267375 | 267375 | Including ECC PM and ECC Supervisor
|  |  |  | Environmental mitigation = None | 1 | 0 | 0
|  |  |  | Environmental enhancement = None | 1 | 0 | 0
[5 empty] | 1 | 0 | 0
|  |  |  | Other (specify) |  |  | 0
|  |  |  | Land purchase & compensation | 1 | 45000 | 45000 | Derived as an average of potential impact on hotels / businesses.
|  |  |  | RHDHV cost to date to be included in overall request for funding | 1 | 282471.68 | 282471.68
|  | Previous project | 172375.68 | to be included in overall request for funding
PC1679 - OBC from P1679_Inflation_Optimism Bias_v01 (19/10/22) - Not linked to file
Inflation (on PV Costs)
| Year 1 |  | 7% |  | Year 2 |  | 14.5% |  | Year 2 |  | 21%
PV | Future costs year 1 including Professional Advice, (excluding salary), site investigation and survey | 679710.1449 | 47579.7101 |  | Future costs year 1 including Professional Advice, (excluding salary) | 85416.2291 | 12385.3532 |  | Construction costs, supervision, land purchase | 11214255.2173 | 2354993.5956
Cash |  |  | 49245 |  |  |  | 13267.5 |  |  |  | 2611023.495
| Overall Inflation value PV | 2414958.659
| Overall Inflation value Cash | 2673535.995
| Risk 95%ile | 3060000
| salary | 50000
| Professional advice | 395000 | 395000
| Site investigation and survey | 375000
| Construction | 12108570.2142
| Supervision and ECC PM | 267375
| Compensation | 45000 | 50587.4534 | 3009412.5466
| Total cost | 13240945.2142
| Optimism Bias 15.6% | 2065587.4534
| Overall risk | 5125587.4534

## Construction Costs_2022
Costs taken from Van Oord estimate on 24/03/2022 and revised to exclude wall cladding
Note: Maintenance for Connaught Garden deleted | [5 empty] | Other Costs |  | Quantity | Rate
Added Demountable defences £30,000 | [6 empty] | Supervision | 43 | 15500 | 666500
[7 empty] | Walfare, Offices and Sundries | 43 | 3700 | 159100
[7 empty] | Mobilise Plant, Compound Setup | 1 | 88000 | 88000
[7 empty] | Demob plant, reinstate compound | 1 | 92000 | 92000
1005600
|  |  | Frontage | Item | frequency (every x years) | Quantity | Unit | Rate | Sub total | total
Remains same as VO updated costs | Option S1.1a 1 Short Groyne | [9 empty] | I would move this to maintenance and put £5k every year |  | 0
Increased from 25k to 30k | 1 Short Groyne |  |  | Make safe street furniture lighting and drainage etc | - | 1 | Sum | 30000 | 30000 |  |  |  | 0
Costs merged, and increased from 790k to 1.9k |  |  |  | Remove existing wall & Basic Splash wall to rear of seafront promenade | - | 600 | Sum | 3268.8144 | 1961288.664 |  |  |  | 0
|  |  | Frontage B (ST) | Demountable defences | - | 1 | sum | 27000 | 27000 |  | Mamahead = £62k for 60m therefore this at @600m = £600k |  | 3000
Increased from 12 to 14 and from 15k to 18k |  |  |  | Flood gates | - | 14 | Nr | 18000 | 252000 |  |  |  | 0
Remains unchanged |  |  |  | Reinstate street features | - | 1 | sum | 100000 | 100000 |  |  |  | 0
Rate updated from 31.9 to 30.94 |  | Initial Capital Cost |  | Beach Recharge | - | 36000 | m3 | 30.94 | 1113840 |  |  |  | 0
Reduced from 180 to 166 |  |  | Frontage C (EB) | 1no. 60m Long rock groyne | - | 1697.4313 | m3 | 166.3919 | 282438.8909 |  |  |  | 646542.2193
New items added from VO updates costs |  |  |  | Mobilise rockworks onshore |  | 1 | Nr | 110000 | 110000
Increased from 650k to 1,813k |  |  |  | Mobilise dredging |  | 1 | Nr | 1813000 | 1813000 |  |  |  | 0
Increased by 180k to 500k |  |  |  | Boat users ramp | - | 1 | Sum | 500000 | 500000 |  |  |  | 0
Rate updated from 31.9 to 30.94 |  |  |  | Beach Recharge | - | 20000 | m3 | 30.94 | 618800 |  |  |  | 193375
Increased from 93k to 443k |  |  | Frontage D (RS) | Repair River Sid Training Wall (Seaward structure) | - | 1 | sum | 443487.15 | 443487.15 | 7251854.7049 | Good |  | 0
|  | Ongoing Costs | Frontage B (ST) | Maintenance to gates | 10 | 14 | sum | 2000 | 28000 |  | I think there is a initial capital recharge
|  |  |  | Replacement to demountable defences | 50 | 1 | sum | 27000 | 27000
|  |  |  | Maintenance to demountable defences | 10 | 1 | sum | 1000 | 1000
|  |  |  | Beach Recharge | 10 | 32400 | m3 | 31.9 | 1033560
|  |  |  | Beach Recycle from Frontage C (EB) | 1 | 3600 | m3 | 8 | 28800
|  |  | Frontage C (EB) | Beach Recharge | 10 | 6600 | m3 | 31.9 | 210540 |  | The last recharge was mid 1980's I think 30m curved crest will disappear quickly so recharge every 10 years is good figure
|  |  | Frontage D (RS) | Repair River Sid River Wall (Adjacent to the Ham) | 30 | 1 | Sum | 100000 | 100000 |  | Good.
Remains same as VO updated costs | Option S1.1b 2 Short Groynes
Increased from 25k to 30k | 2 Short Groynes |  |  | Make safe street furniture lighting and drainage etc | - | 1 | Sum | 30000 | 30000
Costs merged, and increased from 790k to 1.9k |  |  |  | Remove existing wall & Basic Splash wall to rear of seafront promenade | - | 600 | Sum | 3268.8144 | 1961288.664
|  |  | Frontage B (ST) | Demountable defences | - | 1 | sum | 27000 | 27000
Increased from 12 to 14 and from 15k to 18k |  |  |  | Flood gates | - | 14 | Nr | 18000 | 252000
Remains unchanged |  |  |  | Reinstate street features | - | 1 | sum | 100000 | 100000
Rate updated from 31.9 to 30.94 |  | Initial Capital Cost |  | Beach Recharge | - | 36000 | m3 | 30.94 | 1113840
Reduced from 180 to 166 |  |  | Frontage C (EB) | 2no. 60m Long rock groyne | - | 3394.8627 | m3 | 166.3919 | 564877.7818
New items added from VO updates costs |  |  |  | Mobilise rockworks onshore |  | 1 | Nr | 110000 | 110000
Increased from 650k to 1,813k |  |  |  | Mobilise dredging |  | 1 | Nr | 1813000 | 1813000
Increased by 180k to 500k |  |  |  | Boat Users Ramp | - | 1 | Sum | 500000 | 500000
Rate updated from 31.9 to 30.94 |  |  |  | Beach Recharge | - | 20000 | m3 | 30.94 | 618800
Increased from 93k to 443k |  |  | Frontage D (RS) | Repair River Sid Training Wall (Seaward structure) | - | 1 | sum | 443487.15 | 443487.15 | 7534293.5958
Ongoing Costs
|  |  | Frontage B (ST) | Maintenance to gates | 10 | 14 | sum | 2000 | 28000
|  |  |  | Replacement to demountable defences | 50 | 1 | sum | 27000 | 27000
|  |  |  | Maintenance to demountable defences | 10 | 1 | sum | 1000 | 1000
|  |  |  | Beach Recharge | 10 | 30600 | m3 | 31.9 | 976140
|  |  |  | Beach Recycle from Frontage C (EB) | 1 | 5400 | m3 | 8 | 43200
|  |  | Frontage C (EB) | Beach Recharge | 10 | 5000 | m3 | 31.9 | 159500
|  |  | Frontage D (RS) | Repair River Sid River Wall (Adjacent to the Ham) | 30 | 1 | Sum | 100000 | 100000 |  | I think these two options are not likely to provide the technical requirements for the project
Remains same as VO updated costs | Option S1.1c 1 Long Groyne
Increased from 25k to 30k | 1 Long Groyne |  |  | Make safe street furniture lighting and drainage etc | - | 1 | sum | 30000 | 30000
Costs merged, and increased from 790k to 1.9k |  |  |  | Remove existing wall & Basic Splash wall to rear of seafront promenade | - | 600 | Sum | 3268.8144 | 1961288.664
|  |  | Frontage B (ST) | Demountable defences | - | 1 | sum | 27000 | 30000 |  | Refer to construction costing tab
Increased from 12 to 14 and from 15k to 18k |  |  |  | Flood gates | - | 14 | Nr | 18000 | 252000 |  | Cladding to splash wall has been removed
Remains unchanged |  |  |  | Reinstate street features | - | 1 | Sum | 100000 | 100000
Rate updated from 31.9 to 30.94 |  | Initial Capital Cost |  | Beach Recharge | - | 36000 | m3 | 30.94 | 1113840
Reduced from 180 to 166 |  |  | Frontage C (EB) | 1no. 120m Long rock groyne | - | 5583.0896 | m3 | 166.3919 | 928981.1102
New items added from VO updates costs |  |  |  | Mobilise rockworks onshore |  | 1 | Nr | 110000 | 110000
Increased from 650k to 1,813k |  |  |  | Mobilise dredging |  | 1 | Nr | 1813000 | 1813000
Increased by 180k to 500k |  |  |  | Boat Users Ramp | - | 1 | Sum | 500000 | 500000 |  | Refer to Construction cost sheet for construction cost of the ramp
Rate updated from 31.9 to 30.94 |  |  |  | Beach Recharge | - | 26250 | m3 | 30.94 | 812175 |  | Beach profile which is being recharged has been reduced in order to correspond to a linear profile compared to the first assumption of an accumulated profile | Rev M cost | Rev N cost | Gain | Cost Decrease Achieved
Increased from 93k to 443k |  |  | Frontage D (RS) | Repair river Sid Training Wall (Seaward structure) | - | 1 | sum | 443487.15 | 443487.15 | 8094771.9242 | Updated according to Construction Costing sheet | 6074856.1303 | 8094771.9242 | -2019915.7939 | -33.25%
Ongoing Costs
|  |  | Frontage B (ST) | Maintenance to gates | 10 | 14 | sum | 2000 | 28000
|  |  |  | Replacement to demountable defences | 50 | 1 | sum | 27000 | 27000
|  |  |  | Maintenance to demountable defences | 10 | 1 | sum | 1000 | 1000
|  |  |  | Beach Recharge | 10 | 25200 | m3 | 31.9 | 803880 |  | Supplied from the town beach.
|  |  |  | Beach Recycle from Frontage C (EB) | 5 | 10800 | m3 | 8 | 86400
|  |  | Frontage D (RS) | Repair River Sid River Wall (Adjacent to the Ham) | 30 | 1 | Sum | 100000 | 100000
Remains same as VO updated costs | Option S1.1d 1 Long & 1 short Groynes
Increased from 25k to 30k | 1 Long & 1 Short Groynes |  |  | Make safe street furniture lighting and drainage etc | - | 1 | sum | 30000 | 30000
Costs merged, and increased from 790k to 1.9k |  |  |  | Remove existing wall & Basic Splash wall to rear of seafront promenade | - | 600 | Sum | 3268.81 | 1961286
|  |  | Frontage B (ST) | Demountable defences | - | 1 | sum | 27000 | 30000
Increased from 12 to 14 and from 15k to 18k |  |  |  | Flood gates | - | 14 | Nr | 18000 | 252000
Remains unchanged |  |  |  | Reinstate street features | - | 1 | Sum | 100000 | 100000
Rate updated from 31.9 to 30.94 |  | Initial Capital Cost |  | Beach Recharge | - | 36000 | m3 | 30.94 | 1113840
Reduced from 180 to 166 |  |  | Frontage C (EB) | 1no. 60m Long and 1no. 120m long rock groyne | - | 7280.5209 | m3 | 166.3919 | 1211420.0011
New items added from VO updates costs |  |  |  | Mobilise rockworks onshore |  | 1 | Nr | 110000 | 110000
Increased from 650k to 1,813k |  |  |  | Mobilise dredging |  | 1 | Nr | 1813000 | 1813000
Increased by 180k to 500k |  |  |  | Boat Users Ramp | - | 1 | Sum | 500000 | 500000
Rate updated from 31.9 to 30.94 |  |  |  | Beach Recharge | - | 26250 | m3 | 30.94 | 812175
Increased from 93k to 443k |  |  | Frontage D (RS) | Repair River Sid Training Wall (Seaward structure) | - | 1 | sum | 443487.15 | 443487.15 | 8377208.1511
Ongoing Costs
|  |  | Frontage B (ST) | Maintenance to gates | 10 | 14 | sum | 2000 | 28000
|  |  |  | Replacement to demountable defences | 50 | 1 | sum | 27000 | 27000
|  |  |  | Maintenance to demountable defences | 10 | 1 | sum | 1000 | 1000
|  |  |  | Beach Recharge | 10 | 23400 | m3 | 31.9 | 746460
|  |  |  | Beach Recycle from Frontage C (EB) | 5 | 12600 | m3 | 8 | 100800
|  |  | Frontage D (RS) | Repair River Sid River Wall (Adjacent to the Ham) | 30 | 1 | Sum | 100000 | 100000
Remains same as VO updated costs | Option S1.1e 2 Long Groynes | [9 empty] | 0 | 0
Increased from 25k to 30k | 2 Long Groynes |  |  | Make safe street furniture lighting and drainage etc | - | 1 | sum | 30000 | 30000 |  | 3487126 | 30000
Costs merged, and increased from 790k to 1.9k |  |  |  | Remove existing wall & Basic Splash wall to rear of seafront promenade | - | 600 | Sum | 3268.81 | 1961286 |  |  | 1961286
|  |  | Frontage B (ST) | Demountable defences | - | 1 | sum | 27000 | 30000 |  |  | 30000
Increased from 12 to 14 and from 15k to 18k |  |  |  | Flood gates | - | 14 | Nr | 18000 | 252000 |  |  | 252000
Remains unchanged |  |  |  | Reinstate street features | - | 1 | Sum | 100000 | 100000 |  |  | 100000
Rate updated from 31.9 to 30.94 |  | Initial Capital Cost |  | Beach Recharge | - | 36000 | m3 | 30.94 | 1113840 |  |  | 1113840
Reduced from 180 to 166 |  |  | Frontage C (EB) | 2no. 120m Long rock groyne | - | 11166.1792 | m3 | 166.3919 | 1857962.2204 |  | 5093137.2204 | 1211420.0011
New items added from VO updates costs |  |  |  | Mobilise rockworks onshore |  | 1 | Nr | 110000 | 110000
Increased from 650k to 1,813k |  |  |  | Mobilise dredging |  | 1 | Nr | 1813000 | 1813000 |  |  | 1813000
Increased by 180k to 500k |  |  |  | Boat Users Ramp | - | 1 | Sum | 500000 | 500000 |  |  | 500000
Rate updated from 31.9 to 30.94 |  |  |  | Beach Recharge | - | 26250 | m3 | 30.94 | 812175 |  |  | 812175
Increased from 93k to 443k |  |  | Frontage D (RS) | Repair River Sid Training Wall (Seaward structure) | - | 1 | sum | 443487.15 | 443487.15 | 9023750.3704 | 443487.15 | 443487.15
|  | Ongoing Costs | Frontage B (ST) | Maintenance to gates | 10 | 14 | sum | 2000 | 28000
|  |  |  | Replacement to demountable defences | 50 | 1 | sum | 27000 | 27000
|  |  |  | Maintenance to demountable defences | 10 | 1 | sum | 1000 | 1000
|  |  |  | Beach Recharge | 10 | 28800 | m3 | 31.9 | 918720
|  |  |  | Beach Recycle from Frontage C (EB) | 5 | 7200 | m3 | 8 | 57600
|  |  | Frontage D (RS) | Repair River Sid River Wall (Adjacent to the Ham) | 30 | 1 | Sum | 100000 | 100000 |  | These three options I think will all technically work, I don’t think there are much more benefits for the intermediate groyne
We did try to call them a terminal and intermediate groyne
I think the rate for the seaward end of the longer groyne may be more expensive as harder conditions as in the water. May need to uplift the rates
Remains same as VO updated costs | Option S4 | [9 empty] | 0 | 30000
Increased from 25k to 30k | One Offshore Breakwater |  |  | Make safe street furniture lighting and drainage etc | - | 1 | sum | 30000 | 30000 |  | 6495326.954 | 252000
Costs merged, and increased from 790k to 1.9k |  |  |  | Remove existing wall & Basic Splash wall to rear of seafront promenade | - | 600 | Sum | 3268.8144 | 1961288.664 |  |  | 100000
|  |  | Frontage B (ST) | Demountable defences | - | 1 | sum | 27000 | 30000 |  |  | 1113840
Increased from 14 to 11 and from 15k to 18k |  |  |  | Flood gates | - | 14 | Nr | 18000 | 252000 |  |  | 1857962.2204
Remains unchanged |  |  |  | Reinstate street features | - | 1 | Sum | 100000 | 100000 |  |  | 1813000
New rock breakwater added |  |  |  | 1no. Offshore breakwater |  | 70 | Sum | 3008198.29 | 3008198.29
Rate updated from 31.9 to 30.94 |  | Initial Capital Cost |  | Beach Recharge | - | 36000 | m3 | 30.94 | 1113840 |  |  | 500000
Reduced from 180 to 166 |  |  | Frontage C (EB) | 1no. 120m Long rock groyne | - | 5583.0896 | m3 | 166.3919 | 928981.1102 |  | 4164156.1102 | 812175
New items added from VO updates costs |  |  |  | Mobilise rockworks onshore |  | 1 | Nr | 110000 | 110000
Increased from 650k to 1,813k |  |  |  | Mobilise dredging |  | 1 | Nr | 1813000 | 1813000 |  |  | 443487.15
Increased by 180k to 500k |  |  |  | Boat Users Ramp | - | 1 | Sum | 500000 | 500000 |  |  | 0
Rate updated from 31.9 to 30.94 |  |  |  | Beach Recharge | - | 26250 | m3 | 30.94 | 812175 |  |  | 28000
Increased from 93k to 443k |  |  | Frontage D (RS) | Repair River Sid Training Wall (Seaward structure) | - | 1 | sum | 443487.15 | 443487.15 | 11102970.2142 | 443487.15 | 918720
@ 50% due to the recycling form East beach
|  | Ongoing Costs | Frontage B (ST) | Maintenance to gates | 10 | 14 | sum | 2000 | 28000
|  |  |  | Replacement to demountable defences | 50 | 1 | sum | 27000 | 27000
|  |  |  | Maintenance to demountable defences | 10 | 1 | sum | 1000 | 1000
|  |  |  | Beach Recharge | 10 | 2700 | m3 | 31.9 | 86130
|  |  |  | Beach Recycle from Frontage C (EB) | 5 | 10800 | m3 | 8 | 86400
|  |  | Frontage D (RS) | Repair River Sid River Wall (Adjacent to the Ham) | 30 | 1 | Sum | 100000 | 100000 |  |  | 1 short | 10
[12 empty] | 2 short | 15
[12 empty] | 1 long | 30
[12 empty] | 1 long 1 short | 35
[12 empty] | 2 long | 20
|  |  |  | Splash Wall/Demountable defences | 2373288.664
|  |  |  | Offshore breakwater | 3008198.29
|  |  |  | Beach recharge | 1926015
|  |  |  | Rock groyne | 3351981.1102
|  |  |  | Repair River Sid training wall | 443487.15
|  |  |  | Sub-total | 11102970.2142
|  |  |  | Contractor costs & prelims | 1005600
|  |  |  | Total | 12108570.2142
Note on G28: Ayman Elmaghrbi: assum 10% retained by the short groyne
Note on G70: Ayman Elmaghrbi: Assume 30% of material is retained by east groyne (Frontage C)
Note on G90: Ayman Elmaghrbi: assume 35% is retaind by one long and one short groynes
Note on G110: Ayman Elmaghrbi: assum only 20% is retined by the two groynes as the middle groyne would reduce what 1 long groyne would retain

## OBC Cost _Van Oord 2022
SIDMOUTH ECI
Van Oord March 2022 and subsequent emails
SITE PRELIMS | Quantity | Unit | Rate | BUDGET COST | COMMENTS
Supervision | 43 |  | 15500 | 666500
Walfare, Offices and Sundries | 43 |  | 3700 | 159100
Mobilise Plant, Compound Setup | 1 |  | 88000 | 88000
Demob plant, reinstate compound | 1 |  | 92000 | 92000
OPTIONS 4
Frontage B
Make safe street furniture, lighting etc | 1 | sum | 30000 | 30000
Construct splash wall inc remove old, brick facing & coping, Reinstate road & promenade, drains etc | 1 | sum | 1961288.664 | 1961288.664
Flood gates | 14 | no | 18000 | 252000
Reinstate Street furniture & lighting | 1 | sum | 100000 | 100000
Beach recharge | 36000 | m3 | 30.94 | 1113840
1no. Offshore breakwater | 1 | sum | 3008198.29 | 3008198.29
Frontage C
120m long rock groyne - Class 1 rock 8-12t assume 1.8t/m3 | 5583.0896 | m3 | 166.3919 | 928981.1102
Maintenance Access Ramp | 1 | sum | 500000 | 500000
Mobilise rockworks onshore | 1 | sum | 110000 | 110000
Mobilise dredging | 1 | sum | 1813000 | 1813000
Beach Recharge | 26250 | m3 | 30.94 | 812175
Frontage D
River Sid Training wall encasement - 200mm thick fibre concrete | 1 | sum | 443487.15 | 443487.15
INITIAL CAPITAL COST |  |  |  | 12078570.2142
Already undertaken
£12,078,570.21
Amended to exclude clading
Amended following Contractor revision

## OpAp PV Costs
Client/Authority
East Devon District Council
Project name
Sidmouth Beach Management Plan
Project reference
Base date for estimates (year 0) |  |  | 2018-01-01
Scaling factor (e.g. £m, £k, £) |  |  | £
Initial discount rate |  |  | 3.5%
|  | Option S1.1a | 1 Short Groyne |  |  | TOTALS: | PV | PV | PV | PV | PV | Option S1.1b | 2 Short Groynes |  |  | TOTALS: | PV | PV | PV | PV | PV | Option S1.1c | 1 Long Groyne |  |  | TOTALS: | PV | PV | PV | PV | PV | Option S1.1d | 1 Long & 1 Short Groynes |  |  | TOTALS: | PV | PV | PV | PV | PV | Option S1.1e | 2 Long Groynes |  |  | TOTALS: | PV | PV | PV | PV | PV | Option S4 | One Offshore Breakwater |  |  | TOTALS: | PV | PV | PV | PV | PV
|  |  |  | Frequency | Cost
[43 empty] | Maintain Front. A | 0 | 0
|  |  | Maintain Flood Gates Fron. B | 10 | 28000 | [7 empty] | Maintain Flood Gates Fron. B | 10 | 28000 | [7 empty] | Maintain Flood Gates Fron. B | 10 | 28000 | [7 empty] | Maintain Flood Gates Fron. B | 10 | 28000 | [7 empty] | Maintain Flood Gates Fron. B | 10 | 28000 | [7 empty] | Maintain Flood Gates Fron. B | 10 | 28000
|  |  | Replacement to demountable defences | 50 | 27000 | [7 empty] | Replacement to demountable defences | 50 | 27000 | [7 empty] | Replacement to demountable defences | 50 | 27000 | [7 empty] | Replacement to demountable defences | 50 | 27000 | [7 empty] | Replacement to demountable defences | 50 | 27000 | [7 empty] | Replacement to demountable defences | 50 | 27000
|  |  | Maintenance to demountable defences | 10 | 1000 | [7 empty] | Maintenance to demountable defences | 10 | 1000 | [7 empty] | Maintenance to demountable defences | 10 | 1000 | [7 empty] | Maintenance to demountable defences | 10 | 1000 | [7 empty] | Maintenance to demountable defences | 10 | 1000 | [7 empty] | Maintenance to demountable defences | 10 | 1000
|  |  | Recharge Fron. B | 10 | 1033560 | [7 empty] | Recharge Fron. B | 10 | 976140 | [7 empty] | Recharge Fron. B | 10 | 803880 | [7 empty] | Recharge Fron. B | 10 | 746460 | [7 empty] | Recharge Fron. B | 10 | 918720 | [7 empty] | Recharge Fron. B | 10 | 86130
|  |  | Recycle Fron. B | 1 | 28800 | [7 empty] | Recycle Fron. B | 1 | 43200 | [7 empty] | Recycle Fron. B | 5 | 86400 | [7 empty] | Recycle Fron. B | 5 | 100800 | [7 empty] | Recycle Fron. B | 5 | 57600 | [7 empty] | Recycle Fron. B | 5 | 86400
|  |  | Recharge Fron. C | 10 | 210540 | [7 empty] | Recharge Fron. C | 10 | 159500 | [7 empty] | Recharge Fron. C | 100 | 0 | [7 empty] | Recharge Fron. C | 100 | 0 | [7 empty] | Recharge Fron. C | 100 | 0 | [7 empty] | Recharge Fron. C | 100 | 0
|  |  | Repiar River Wall Fron. D | 30 | 100000 | [7 empty] | Repiar River Wall Fron. D | 30 | 100000 | [7 empty] | Repiar River Wall Fron. D | 30 | 100000 | [7 empty] | Repiar River Wall Fron. D | 30 | 100000 | [7 empty] | Repiar River Wall Fron. D | 30 | 100000 | [7 empty] | Repiar River Wall Fron. D | 30 | 100000
|  |  | Year of construction: | 2 | [8 empty] | Year of construction: | 2 | [8 empty] | Year of construction: | 2 | [8 empty] | Year of construction: | 2 | [8 empty] | Year of construction: | 2 | [8 empty] | Year of construction: | 2
|  | Capital | Maint. | Other | Negative costs | Cash | Capital | Maint | Other | Negative costs | Total PV cost | Capital | Maint. | Other | Negative costs | Cash | Capital | Maint | Other | Negative costs | Total PV cost | Capital | Maint. | Other | Negative costs | Cash | Capital | Maint | Other | Negative costs | Total PV cost | Capital | Maint. | Other | Negative costs | Cash | Capital | Maint | Other | Negative costs | Total PV cost | Capital | Maint. | Other | Negative costs | Cash | Capital | Maint | Other | Negative costs | Total PV cost | Capital | Maint. | Other | Negative costs | Cash | Capital | Maint | Other | Negative costs | Total PV cost
| cash sum | 8257454.7049 | 14578500 | 1364846.68 | 0 | 24200801.3849 | 7708422.3248 | 3742840.0682 | 1309956.5346 | 0 | 12761218.9277 | 8539893.5958 | 14999160 | 1364846.68 | 0 | 24903900.2758 | 7972082.0517 | 3882546.6837 | 1309956.5346 | 0 | 13164585.27 | 9100371.9242 | 9464520 | 1364846.68 | 0 | 19929738.6042 | 8495294.5685 | 2395779.474 | 1309956.5346 | 0 | 12201030.5772 | 9382808.1511 | 9221340 | 1364846.68 | 0 | 19968994.8311 | 8758951.8085 | 2336897.8894 | 1309956.5346 | 0 | 12405806.2326 | 10029350.3704 | 9950880 | 1364846.68 | 0 | 21345077.0504 | 9362505.8885 | 2513542.6432 | 1309956.5346 | 0 | 13186005.0663 | 12108570.2142 | 3004770 | 1414846.68 | 0 | 16528186.8942 | 11303479.8611 | 755672.152 | 1358265.7134 | 0 | 13417417.7265
Discount
year | Factor
0 | 1 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0
1 | 0.96618 | 0 | 0 | 1097471.68 |  | 1097471.68 | 0 | 0 | 1060359.1111 | 0 | 1060359.1111 | 0 | 0 | 1097471.68 |  | 1097471.68 | 0 | 0 | 1060359.1111 | 0 | 1060359.1111 | 0 | 0 | 1097471.68 |  | 1097471.68 | 0 | 0 | 1060359.1111 | 0 | 1060359.1111 | 0 | 0 | 1097471.68 |  | 1097471.68 | 0 | 0 | 1060359.1111 | 0 | 1060359.1111 | 0 | 0 | 1097471.68 |  | 1097471.68 | 0 | 0 | 1060359.1111 | 0 | 1060359.1111 | 0 | 0 | 1147471.68 |  | 1147471.68 | 0 | 0 | 1108668.2899 | 0 | 1108668.2899
2 | 0.93351 | 8257454.7049 | 0 | 267375 |  | 8524829.7049 | 7708422.3248 | 0 | 249597.4235 | 0 | 7958019.7483 | 8539893.5958 | 0 | 267375 |  | 8807268.5958 | 7972082.0517 | 0 | 249597.4235 | 0 | 8221679.4752 | 9100371.9242 | 0 | 267375 |  | 9367746.9242 | 8495294.5685 | 0 | 249597.4235 | 0 | 8744891.992 | 9382808.1511 | 0 | 267375 |  | 9650183.1511 | 8758951.8085 | 0 | 249597.4235 | 0 | 9008549.232 | 10029350.3704 | 0 | 267375 |  | 10296725.3704 | 9362505.8885 | 0 | 249597.4235 | 0 | 9612103.312 | 12108570.2142 | 0 | 267375 |  | 12375945.2142 | 11303479.8611 | 0 | 249597.4235 | 0 | 11553077.2846
3 | 0.90194 | 0 | 28800 |  |  | 28800 | 0 | 25975.9499 | 0 | 0 | 25975.9499 | 0 | 43200 |  |  | 43200 | 0 | 38963.9249 | 0 | 0 | 38963.9249 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0
4 | 0.87144 | 0 | 28800 |  |  | 28800 | 0 | 25097.5362 | 0 | 0 | 25097.5362 | 0 | 43200 |  |  | 43200 | 0 | 37646.3042 | 0 | 0 | 37646.3042 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0
5 | 0.84197 | 0 | 28800 |  |  | 28800 | 0 | 24248.8272 | 0 | 0 | 24248.8272 | 0 | 43200 |  |  | 43200 | 0 | 36373.2408 | 0 | 0 | 36373.2408 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0
6 | 0.8135 | 0 | 28800 |  |  | 28800 | 0 | 23428.8186 | 0 | 0 | 23428.8186 | 0 | 43200 |  |  | 43200 | 0 | 35143.2278 | 0 | 0 | 35143.2278 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0
7 | 0.78599 | 0 | 28800 |  |  | 28800 | 0 | 22636.5397 | 0 | 0 | 22636.5397 | 0 | 43200 |  |  | 43200 | 0 | 33954.8095 | 0 | 0 | 33954.8095 | 0 | 86400 |  |  | 86400 | 0 | 67909.619 | 0 | 0 | 67909.619 | 0 | 100800 |  |  | 100800 | 0 | 79227.8888 | 0 | 0 | 79227.8888 | 0 | 57600 |  |  | 57600 | 0 | 45273.0793 | 0 | 0 | 45273.0793 | 0 | 86400 |  |  | 86400 | 0 | 67909.619 | 0 | 0 | 67909.619
8 | 0.75941 | 0 | 28800 |  |  | 28800 | 0 | 21871.0528 | 0 | 0 | 21871.0528 | 0 | 43200 |  |  | 43200 | 0 | 32806.5792 | 0 | 0 | 32806.5792 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0
9 | 0.73373 | 0 | 28800 |  |  | 28800 | 0 | 21131.452 | 0 | 0 | 21131.452 | 0 | 43200 |  |  | 43200 | 0 | 31697.178 | 0 | 0 | 31697.178 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0
10 | 0.70892 | 0 | 28800 |  |  | 28800 | 0 | 20416.8618 | 0 | 0 | 20416.8618 | 0 | 43200 |  |  | 43200 | 0 | 30625.2928 | 0 | 0 | 30625.2928 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0
11 | 0.68495 | 0 | 28800 |  |  | 28800 | 0 | 19726.4366 | 0 | 0 | 19726.4366 | 0 | 43200 |  |  | 43200 | 0 | 29589.6548 | 0 | 0 | 29589.6548 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0
12 | 0.66178 | 0 | 1301900 |  |  | 1301900 | 0 | 861575.676 | 0 | 0 | 861575.676 | 0 | 1207840 |  |  | 1207840 | 0 | 799328.339 | 0 | 0 | 799328.339 | 0 | 919280 |  |  | 919280 | 0 | 608364.1505 | 0 | 0 | 608364.1505 | 0 | 876260 |  |  | 876260 | 0 | 579894.233 | 0 | 0 | 579894.233 | 0 | 1005320 |  |  | 1005320 | 0 | 665303.9854 | 0 | 0 | 665303.9854 | 0 | 201530 |  |  | 201530 | 0 | 133369.1881 | 0 | 0 | 133369.1881
13 | 0.6394 | 0 | 28800 |  |  | 28800 | 0 | 18414.8396 | 0 | 0 | 18414.8396 | 0 | 43200 |  |  | 43200 | 0 | 27622.2594 | 0 | 0 | 27622.2594 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0
14 | 0.61778 | 0 | 28800 |  |  | 28800 | 0 | 17792.1156 | 0 | 0 | 17792.1156 | 0 | 43200 |  |  | 43200 | 0 | 26688.1733 | 0 | 0 | 26688.1733 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0
15 | 0.59689 | 0 | 28800 |  |  | 28800 | 0 | 17190.4498 | 0 | 0 | 17190.4498 | 0 | 43200 |  |  | 43200 | 0 | 25785.6747 | 0 | 0 | 25785.6747 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0
16 | 0.57671 | 0 | 28800 |  |  | 28800 | 0 | 16609.1303 | 0 | 0 | 16609.1303 | 0 | 43200 |  |  | 43200 | 0 | 24913.6954 | 0 | 0 | 24913.6954 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0
17 | 0.5572 | 0 | 28800 |  |  | 28800 | 0 | 16047.4688 | 0 | 0 | 16047.4688 | 0 | 43200 |  |  | 43200 | 0 | 24071.2033 | 0 | 0 | 24071.2033 | 0 | 86400 |  |  | 86400 | 0 | 48142.4065 | 0 | 0 | 48142.4065 | 0 | 100800 |  |  | 100800 | 0 | 56166.141 | 0 | 0 | 56166.141 | 0 | 57600 |  |  | 57600 | 0 | 32094.9377 | 0 | 0 | 32094.9377 | 0 | 86400 |  |  | 86400 | 0 | 48142.4065 | 0 | 0 | 48142.4065
18 | 0.53836 | 0 | 28800 |  |  | 28800 | 0 | 15504.8008 | 0 | 0 | 15504.8008 | 0 | 43200 |  |  | 43200 | 0 | 23257.2012 | 0 | 0 | 23257.2012 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0
19 | 0.52016 | 0 | 28800 |  |  | 28800 | 0 | 14980.4839 | 0 | 0 | 14980.4839 | 0 | 43200 |  |  | 43200 | 0 | 22470.7258 | 0 | 0 | 22470.7258 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0
20 | 0.50257 | 0 | 28800 |  |  | 28800 | 0 | 14473.8975 | 0 | 0 | 14473.8975 | 0 | 43200 |  |  | 43200 | 0 | 21710.8462 | 0 | 0 | 21710.8462 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0
21 | 0.48557 | 0 | 28800 |  |  | 28800 | 0 | 13984.442 | 0 | 0 | 13984.442 | 0 | 43200 |  |  | 43200 | 0 | 20976.663 | 0 | 0 | 20976.663 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0
22 | 0.46915 | 0 | 1301900 |  |  | 1301900 | 0 | 610787.2062 | 0 | 0 | 610787.2062 | 0 | 1207840 |  |  | 1207840 | 0 | 566658.8979 | 0 | 0 | 566658.8979 | 0 | 919280 |  |  | 919280 | 0 | 431280.7918 | 0 | 0 | 431280.7918 | 0 | 876260 |  |  | 876260 | 0 | 411097.9317 | 0 | 0 | 411097.9317 | 0 | 1005320 |  |  | 1005320 | 0 | 471646.5121 | 0 | 0 | 471646.5121 | 0 | 201530 |  |  | 201530 | 0 | 94547.9266 | 0 | 0 | 94547.9266
23 | 0.45329 | 0 | 28800 |  |  | 28800 | 0 | 13054.6262 | 0 | 0 | 13054.6262 | 0 | 43200 |  |  | 43200 | 0 | 19581.9394 | 0 | 0 | 19581.9394 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0
24 | 0.43796 | 0 | 28800 |  |  | 28800 | 0 | 12613.1655 | 0 | 0 | 12613.1655 | 0 | 43200 |  |  | 43200 | 0 | 18919.7482 | 0 | 0 | 18919.7482 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0
25 | 0.42315 | 0 | 28800 |  |  | 28800 | 0 | 12186.6333 | 0 | 0 | 12186.6333 | 0 | 43200 |  |  | 43200 | 0 | 18279.9499 | 0 | 0 | 18279.9499 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0
26 | 0.40884 | 0 | 28800 |  |  | 28800 | 0 | 11774.5249 | 0 | 0 | 11774.5249 | 0 | 43200 |  |  | 43200 | 0 | 17661.7874 | 0 | 0 | 17661.7874 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0
27 | 0.39501 | 0 | 28800 |  |  | 28800 | 0 | 11376.3526 | 0 | 0 | 11376.3526 | 0 | 43200 |  |  | 43200 | 0 | 17064.5289 | 0 | 0 | 17064.5289 | 0 | 86400 |  |  | 86400 | 0 | 34129.0577 | 0 | 0 | 34129.0577 | 0 | 100800 |  |  | 100800 | 0 | 39817.234 | 0 | 0 | 39817.234 | 0 | 57600 |  |  | 57600 | 0 | 22752.7052 | 0 | 0 | 22752.7052 | 0 | 86400 |  |  | 86400 | 0 | 34129.0577 | 0 | 0 | 34129.0577
28 | 0.38165 | 0 | 28800 |  |  | 28800 | 0 | 10991.645 | 0 | 0 | 10991.645 | 0 | 43200 |  |  | 43200 | 0 | 16487.4675 | 0 | 0 | 16487.4675 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0
29 | 0.36875 | 0 | 28800 |  |  | 28800 | 0 | 10619.9469 | 0 | 0 | 10619.9469 | 0 | 43200 |  |  | 43200 | 0 | 15929.9203 | 0 | 0 | 15929.9203 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0
30 | 0.35628 | 0 | 28800 |  |  | 28800 | 0 | 10260.8182 | 0 | 0 | 10260.8182 | 0 | 43200 |  |  | 43200 | 0 | 15391.2273 | 0 | 0 | 15391.2273 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0
31 | 0.3459 | 0 | 28800 |  |  | 28800 | 0 | 9961.9594 | 0 | 0 | 9961.9594 | 0 | 43200 |  |  | 43200 | 0 | 14942.9392 | 0 | 0 | 14942.9392 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0
32 | 0.33583 | 0 | 1401900 |  |  | 1401900 | 0 | 470795.2718 | 0 | 0 | 470795.2718 | 0 | 1307840 |  |  | 1307840 | 0 | 439207.4244 | 0 | 0 | 439207.4244 | 0 | 1019280 |  |  | 1019280 | 0 | 342301.3087 | 0 | 0 | 342301.3087 | 0 | 976260 |  |  | 976260 | 0 | 327854.0495 | 0 | 0 | 327854.0495 | 0 | 1105320 |  |  | 1105320 | 0 | 371195.8269 | 0 | 0 | 371195.8269 | 0 | 301530 |  |  | 301530 | 0 | 101261.7864 | 0 | 0 | 101261.7864
33 | 0.32605 | 0 | 28800 |  |  | 28800 | 0 | 9390.1022 | 0 | 0 | 9390.1022 | 0 | 43200 |  |  | 43200 | 0 | 14085.1533 | 0 | 0 | 14085.1533 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0
34 | 0.31655 | 0 | 28800 |  |  | 28800 | 0 | 9116.6041 | 0 | 0 | 9116.6041 | 0 | 43200 |  |  | 43200 | 0 | 13674.9061 | 0 | 0 | 13674.9061 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0
35 | 0.30733 | 0 | 28800 |  |  | 28800 | 0 | 8851.0719 | 0 | 0 | 8851.0719 | 0 | 43200 |  |  | 43200 | 0 | 13276.6079 | 0 | 0 | 13276.6079 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0
36 | 0.29838 | 0 | 28800 |  |  | 28800 | 0 | 8593.2737 | 0 | 0 | 8593.2737 | 0 | 43200 |  |  | 43200 | 0 | 12889.9106 | 0 | 0 | 12889.9106 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0
37 | 0.28969 | 0 | 28800 |  |  | 28800 | 0 | 8342.9842 | 0 | 0 | 8342.9842 | 0 | 43200 |  |  | 43200 | 0 | 12514.4763 | 0 | 0 | 12514.4763 | 0 | 86400 |  |  | 86400 | 0 | 25028.9526 | 0 | 0 | 25028.9526 | 0 | 100800 |  |  | 100800 | 0 | 29200.4447 | 0 | 0 | 29200.4447 | 0 | 57600 |  |  | 57600 | 0 | 16685.9684 | 0 | 0 | 16685.9684 | 0 | 86400 |  |  | 86400 | 0 | 25028.9526 | 0 | 0 | 25028.9526
38 | 0.28125 | 0 | 28800 |  |  | 28800 | 0 | 8099.9847 | 0 | 0 | 8099.9847 | 0 | 43200 |  |  | 43200 | 0 | 12149.977 | 0 | 0 | 12149.977 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0
39 | 0.27306 | 0 | 28800 |  |  | 28800 | 0 | 7864.0628 | 0 | 0 | 7864.0628 | 0 | 43200 |  |  | 43200 | 0 | 11796.0942 | 0 | 0 | 11796.0942 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0
40 | 0.2651 | 0 | 28800 |  |  | 28800 | 0 | 7635.0124 | 0 | 0 | 7635.0124 | 0 | 43200 |  |  | 43200 | 0 | 11452.5186 | 0 | 0 | 11452.5186 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0
41 | 0.25738 | 0 | 28800 |  |  | 28800 | 0 | 7412.6334 | 0 | 0 | 7412.6334 | 0 | 43200 |  |  | 43200 | 0 | 11118.9501 | 0 | 0 | 11118.9501 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0
42 | 0.24989 | 0 | 1301900 |  |  | 1301900 | 0 | 325327.246 | 0 | 0 | 325327.246 | 0 | 1207840 |  |  | 1207840 | 0 | 301822.921 | 0 | 0 | 301822.921 | 0 | 919280 |  |  | 919280 | 0 | 229715.6699 | 0 | 0 | 229715.6699 | 0 | 876260 |  |  | 876260 | 0 | 218965.5523 | 0 | 0 | 218965.5523 | 0 | 1005320 |  |  | 1005320 | 0 | 251215.9052 | 0 | 0 | 251215.9052 | 0 | 201530 |  |  | 201530 | 0 | 50359.6281 | 0 | 0 | 50359.6281
43 | 0.24261 | 0 | 28800 |  |  | 28800 | 0 | 6987.1179 | 0 | 0 | 6987.1179 | 0 | 43200 |  |  | 43200 | 0 | 10480.6769 | 0 | 0 | 10480.6769 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0
44 | 0.23554 | 0 | 28800 |  |  | 28800 | 0 | 6783.6096 | 0 | 0 | 6783.6096 | 0 | 43200 |  |  | 43200 | 0 | 10175.4144 | 0 | 0 | 10175.4144 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0
45 | 0.22868 | 0 | 28800 |  |  | 28800 | 0 | 6586.0288 | 0 | 0 | 6586.0288 | 0 | 43200 |  |  | 43200 | 0 | 9879.0432 | 0 | 0 | 9879.0432 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0
46 | 0.22202 | 0 | 28800 |  |  | 28800 | 0 | 6394.2027 | 0 | 0 | 6394.2027 | 0 | 43200 |  |  | 43200 | 0 | 9591.304 | 0 | 0 | 9591.304 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0
47 | 0.21555 | 0 | 28800 |  |  | 28800 | 0 | 6207.9638 | 0 | 0 | 6207.9638 | 0 | 43200 |  |  | 43200 | 0 | 9311.9457 | 0 | 0 | 9311.9457 | 0 | 86400 |  |  | 86400 | 0 | 18623.8913 | 0 | 0 | 18623.8913 | 0 | 100800 |  |  | 100800 | 0 | 21727.8732 | 0 | 0 | 21727.8732 | 0 | 57600 |  |  | 57600 | 0 | 12415.9275 | 0 | 0 | 12415.9275 | 0 | 86400 |  |  | 86400 | 0 | 18623.8913 | 0 | 0 | 18623.8913
48 | 0.20928 | 0 | 28800 |  |  | 28800 | 0 | 6027.1493 | 0 | 0 | 6027.1493 | 0 | 43200 |  |  | 43200 | 0 | 9040.7239 | 0 | 0 | 9040.7239 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0
49 | 0.20318 | 0 | 28800 |  |  | 28800 | 0 | 5851.6013 | 0 | 0 | 5851.6013 | 0 | 43200 |  |  | 43200 | 0 | 8777.4019 | 0 | 0 | 8777.4019 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0
50 | 0.19726 | 0 | 28800 |  |  | 28800 | 0 | 5681.1663 | 0 | 0 | 5681.1663 | 0 | 43200 |  |  | 43200 | 0 | 8521.7494 | 0 | 0 | 8521.7494 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0
51 | 0.19152 | 0 | 28800 |  |  | 28800 | 0 | 5515.6954 | 0 | 0 | 5515.6954 | 0 | 43200 |  |  | 43200 | 0 | 8273.5431 | 0 | 0 | 8273.5431 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0
52 | 0.18594 | 0 | 1328900 |  |  | 1328900 | 0 | 247094.3779 | 0 | 0 | 247094.3779 | 0 | 1234840 |  |  | 1234840 | 0 | 229604.9527 | 0 | 0 | 229604.9527 | 0 | 946280 |  |  | 946280 | 0 | 175950.386 | 0 | 0 | 175950.386 | 0 | 903260 |  |  | 903260 | 0 | 167951.2889 | 0 | 0 | 167951.2889 | 0 | 1032320 |  |  | 1032320 | 0 | 191948.5802 | 0 | 0 | 191948.5802 | 0 | 228530 |  |  | 228530 | 0 | 42492.6467 | 0 | 0 | 42492.6467
53 | 0.18052 | 0 | 28800 |  |  | 28800 | 0 | 5199.0719 | 0 | 0 | 5199.0719 | 0 | 43200 |  |  | 43200 | 0 | 7798.6079 | 0 | 0 | 7798.6079 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0
54 | 0.17527 | 0 | 28800 |  |  | 28800 | 0 | 5047.6426 | 0 | 0 | 5047.6426 | 0 | 43200 |  |  | 43200 | 0 | 7571.464 | 0 | 0 | 7571.464 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0
55 | 0.17016 | 0 | 28800 |  |  | 28800 | 0 | 4900.6239 | 0 | 0 | 4900.6239 | 0 | 43200 |  |  | 43200 | 0 | 7350.9359 | 0 | 0 | 7350.9359 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0
56 | 0.1652 | 0 | 28800 |  |  | 28800 | 0 | 4757.8873 | 0 | 0 | 4757.8873 | 0 | 43200 |  |  | 43200 | 0 | 7136.831 | 0 | 0 | 7136.831 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0
57 | 0.16039 | 0 | 28800 |  |  | 28800 | 0 | 4619.3081 | 0 | 0 | 4619.3081 | 0 | 43200 |  |  | 43200 | 0 | 6928.9621 | 0 | 0 | 6928.9621 | 0 | 86400 |  |  | 86400 | 0 | 13857.9242 | 0 | 0 | 13857.9242 | 0 | 100800 |  |  | 100800 | 0 | 16167.5782 | 0 | 0 | 16167.5782 | 0 | 57600 |  |  | 57600 | 0 | 9238.6161 | 0 | 0 | 9238.6161 | 0 | 86400 |  |  | 86400 | 0 | 13857.9242 | 0 | 0 | 13857.9242
58 | 0.15572 | 0 | 28800 |  |  | 28800 | 0 | 4484.7651 | 0 | 0 | 4484.7651 | 0 | 43200 |  |  | 43200 | 0 | 6727.1477 | 0 | 0 | 6727.1477 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0
59 | 0.15119 | 0 | 28800 |  |  | 28800 | 0 | 4354.1409 | 0 | 0 | 4354.1409 | 0 | 43200 |  |  | 43200 | 0 | 6531.2113 | 0 | 0 | 6531.2113 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0
60 | 0.14678 | 0 | 28800 |  |  | 28800 | 0 | 4227.3213 | 0 | 0 | 4227.3213 | 0 | 43200 |  |  | 43200 | 0 | 6340.9819 | 0 | 0 | 6340.9819 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0
61 | 0.14251 | 0 | 28800 |  |  | 28800 | 0 | 4104.1954 | 0 | 0 | 4104.1954 | 0 | 43200 |  |  | 43200 | 0 | 6156.2931 | 0 | 0 | 6156.2931 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0
62 | 0.13836 | 0 | 1401900 |  |  | 1401900 | 0 | 193961.4184 | 0 | 0 | 193961.4184 | 0 | 1307840 |  |  | 1307840 | 0 | 180947.6435 | 0 | 0 | 180947.6435 | 0 | 1019280 |  |  | 1019280 | 0 | 141023.6069 | 0 | 0 | 141023.6069 | 0 | 976260 |  |  | 976260 | 0 | 135071.5275 | 0 | 0 | 135071.5275 | 0 | 1105320 |  |  | 1105320 | 0 | 152927.7659 | 0 | 0 | 152927.7659 | 0 | 301530 |  |  | 301530 | 0 | 41718.5152 | 0 | 0 | 41718.5152
63 | 0.13433 | 0 | 28800 |  |  | 28800 | 0 | 3868.5978 | 0 | 0 | 3868.5978 | 0 | 43200 |  |  | 43200 | 0 | 5802.8967 | 0 | 0 | 5802.8967 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0
64 | 0.13041 | 0 | 28800 |  |  | 28800 | 0 | 3755.9202 | 0 | 0 | 3755.9202 | 0 | 43200 |  |  | 43200 | 0 | 5633.8803 | 0 | 0 | 5633.8803 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0
65 | 0.12662 | 0 | 28800 |  |  | 28800 | 0 | 3646.5244 | 0 | 0 | 3646.5244 | 0 | 43200 |  |  | 43200 | 0 | 5469.7867 | 0 | 0 | 5469.7867 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0
66 | 0.12293 | 0 | 28800 |  |  | 28800 | 0 | 3540.315 | 0 | 0 | 3540.315 | 0 | 43200 |  |  | 43200 | 0 | 5310.4725 | 0 | 0 | 5310.4725 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0
67 | 0.11935 | 0 | 28800 |  |  | 28800 | 0 | 3437.199 | 0 | 0 | 3437.199 | 0 | 43200 |  |  | 43200 | 0 | 5155.7985 | 0 | 0 | 5155.7985 | 0 | 86400 |  |  | 86400 | 0 | 10311.5971 | 0 | 0 | 10311.5971 | 0 | 100800 |  |  | 100800 | 0 | 12030.1966 | 0 | 0 | 12030.1966 | 0 | 57600 |  |  | 57600 | 0 | 6874.398 | 0 | 0 | 6874.398 | 0 | 86400 |  |  | 86400 | 0 | 10311.5971 | 0 | 0 | 10311.5971
68 | 0.11587 | 0 | 28800 |  |  | 28800 | 0 | 3337.0864 | 0 | 0 | 3337.0864 | 0 | 43200 |  |  | 43200 | 0 | 5005.6296 | 0 | 0 | 5005.6296 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0
69 | 0.1125 | 0 | 28800 |  |  | 28800 | 0 | 3239.8897 | 0 | 0 | 3239.8897 | 0 | 43200 |  |  | 43200 | 0 | 4859.8346 | 0 | 0 | 4859.8346 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0
70 | 0.10922 | 0 | 28800 |  |  | 28800 | 0 | 3145.524 | 0 | 0 | 3145.524 | 0 | 43200 |  |  | 43200 | 0 | 4718.286 | 0 | 0 | 4718.286 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0
71 | 0.10604 | 0 | 28800 |  |  | 28800 | 0 | 3053.9068 | 0 | 0 | 3053.9068 | 0 | 43200 |  |  | 43200 | 0 | 4580.8602 | 0 | 0 | 4580.8602 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0
72 | 0.10295 | 0 | 1301900 |  |  | 1301900 | 0 | 134030.5179 | 0 | 0 | 134030.5179 | 0 | 1207840 |  |  | 1207840 | 0 | 124347.0472 | 0 | 0 | 124347.0472 | 0 | 919280 |  |  | 919280 | 0 | 94639.8145 | 0 | 0 | 94639.8145 | 0 | 876260 |  |  | 876260 | 0 | 90210.9083 | 0 | 0 | 90210.9083 | 0 | 1005320 |  |  | 1005320 | 0 | 103497.6267 | 0 | 0 | 103497.6267 | 0 | 201530 |  |  | 201530 | 0 | 20747.5 | 0 | 0 | 20747.5
73 | 0.099951 | 0 | 28800 |  |  | 28800 | 0 | 2878.6001 | 0 | 0 | 2878.6001 | 0 | 43200 |  |  | 43200 | 0 | 4317.9001 | 0 | 0 | 4317.9001 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0
74 | 0.09704 | 0 | 28800 |  |  | 28800 | 0 | 2794.7573 | 0 | 0 | 2794.7573 | 0 | 43200 |  |  | 43200 | 0 | 4192.136 | 0 | 0 | 4192.136 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0
75 | 0.094214 | 0 | 28800 |  |  | 28800 | 0 | 2713.3567 | 0 | 0 | 2713.3567 | 0 | 43200 |  |  | 43200 | 0 | 4070.035 | 0 | 0 | 4070.035 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0
76 | 0.091916 | 0 | 28800 |  |  | 28800 | 0 | 2647.1772 | 0 | 0 | 2647.1772 | 0 | 43200 |  |  | 43200 | 0 | 3970.7658 | 0 | 0 | 3970.7658 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0
77 | 0.089674 | 0 | 28800 |  |  | 28800 | 0 | 2582.6119 | 0 | 0 | 2582.6119 | 0 | 43200 |  |  | 43200 | 0 | 3873.9179 | 0 | 0 | 3873.9179 | 0 | 86400 |  |  | 86400 | 0 | 7747.8358 | 0 | 0 | 7747.8358 | 0 | 100800 |  |  | 100800 | 0 | 9039.1417 | 0 | 0 | 9039.1417 | 0 | 57600 |  |  | 57600 | 0 | 5165.2238 | 0 | 0 | 5165.2238 | 0 | 86400 |  |  | 86400 | 0 | 7747.8358 | 0 | 0 | 7747.8358
78 | 0.087487 | 0 | 28800 |  |  | 28800 | 0 | 2519.6214 | 0 | 0 | 2519.6214 | 0 | 43200 |  |  | 43200 | 0 | 3779.4321 | 0 | 0 | 3779.4321 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0
79 | 0.085353 | 0 | 28800 |  |  | 28800 | 0 | 2458.1672 | 0 | 0 | 2458.1672 | 0 | 43200 |  |  | 43200 | 0 | 3687.2508 | 0 | 0 | 3687.2508 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0
80 | 0.083271 | 0 | 28800 |  |  | 28800 | 0 | 2398.2119 | 0 | 0 | 2398.2119 | 0 | 43200 |  |  | 43200 | 0 | 3597.3179 | 0 | 0 | 3597.3179 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0
81 | 0.08124 | 0 | 28800 |  |  | 28800 | 0 | 2339.7189 | 0 | 0 | 2339.7189 | 0 | 43200 |  |  | 43200 | 0 | 3509.5784 | 0 | 0 | 3509.5784 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0
82 | 0.079259 | 0 | 1301900 |  |  | 1301900 | 0 | 103186.9947 | 0 | 0 | 103186.9947 | 0 | 1207840 |  |  | 1207840 | 0 | 95731.9146 | 0 | 0 | 95731.9146 | 0 | 919280 |  |  | 919280 | 0 | 72861.0035 | 0 | 0 | 72861.0035 | 0 | 876260 |  |  | 876260 | 0 | 69451.2911 | 0 | 0 | 69451.2911 | 0 | 1005320 |  |  | 1005320 | 0 | 79680.4282 | 0 | 0 | 79680.4282 | 0 | 201530 |  |  | 201530 | 0 | 15973.0202 | 0 | 0 | 15973.0202
83 | 0.077326 | 0 | 28800 |  |  | 28800 | 0 | 2226.9782 | 0 | 0 | 2226.9782 | 0 | 43200 |  |  | 43200 | 0 | 3340.4672 | 0 | 0 | 3340.4672 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0
84 | 0.07544 | 0 | 28800 |  |  | 28800 | 0 | 2172.6616 | 0 | 0 | 2172.6616 | 0 | 43200 |  |  | 43200 | 0 | 3258.9924 | 0 | 0 | 3258.9924 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0
85 | 0.0736 | 0 | 28800 |  |  | 28800 | 0 | 2119.6699 | 0 | 0 | 2119.6699 | 0 | 43200 |  |  | 43200 | 0 | 3179.5048 | 0 | 0 | 3179.5048 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0
86 | 0.071805 | 0 | 28800 |  |  | 28800 | 0 | 2067.9706 | 0 | 0 | 2067.9706 | 0 | 43200 |  |  | 43200 | 0 | 3101.9559 | 0 | 0 | 3101.9559 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0
87 | 0.070053 | 0 | 28800 |  |  | 28800 | 0 | 2017.5323 | 0 | 0 | 2017.5323 | 0 | 43200 |  |  | 43200 | 0 | 3026.2985 | 0 | 0 | 3026.2985 | 0 | 86400 |  |  | 86400 | 0 | 6052.5969 | 0 | 0 | 6052.5969 | 0 | 100800 |  |  | 100800 | 0 | 7061.3631 | 0 | 0 | 7061.3631 | 0 | 57600 |  |  | 57600 | 0 | 4035.0646 | 0 | 0 | 4035.0646 | 0 | 86400 |  |  | 86400 | 0 | 6052.5969 | 0 | 0 | 6052.5969
88 | 0.068345 | 0 | 28800 |  |  | 28800 | 0 | 1968.3242 | 0 | 0 | 1968.3242 | 0 | 43200 |  |  | 43200 | 0 | 2952.4863 | 0 | 0 | 2952.4863 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0
89 | 0.066678 | 0 | 28800 |  |  | 28800 | 0 | 1920.3163 | 0 | 0 | 1920.3163 | 0 | 43200 |  |  | 43200 | 0 | 2880.4744 | 0 | 0 | 2880.4744 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0
90 | 0.065051 | 0 | 28800 |  |  | 28800 | 0 | 1873.4793 | 0 | 0 | 1873.4793 | 0 | 43200 |  |  | 43200 | 0 | 2810.219 | 0 | 0 | 2810.219 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0
91 | 0.063465 | 0 | 28800 |  |  | 28800 | 0 | 1827.7847 | 0 | 0 | 1827.7847 | 0 | 43200 |  |  | 43200 | 0 | 2741.677 | 0 | 0 | 2741.677 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0
92 | 0.061917 | 0 | 1401900 |  |  | 1401900 | 0 | 86801.1979 | 0 | 0 | 86801.1979 | 0 | 1307840 |  |  | 1307840 | 0 | 80977.3013 | 0 | 0 | 80977.3013 | 0 | 1019280 |  |  | 1019280 | 0 | 63110.582 | 0 | 0 | 63110.582 | 0 | 976260 |  |  | 976260 | 0 | 60446.9202 | 0 | 0 | 60446.9202 | 0 | 1105320 |  |  | 1105320 | 0 | 68437.9057 | 0 | 0 | 68437.9057 | 0 | 301530 |  |  | 301530 | 0 | 18669.7804 | 0 | 0 | 18669.7804
93 | 0.060407 | 0 | 28800 |  |  | 28800 | 0 | 1739.7118 | 0 | 0 | 1739.7118 | 0 | 43200 |  |  | 43200 | 0 | 2609.5677 | 0 | 0 | 2609.5677 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0
94 | 0.058933 | 0 | 28800 |  |  | 28800 | 0 | 1697.2798 | 0 | 0 | 1697.2798 | 0 | 43200 |  |  | 43200 | 0 | 2545.9197 | 0 | 0 | 2545.9197 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0
95 | 0.057496 | 0 | 28800 |  |  | 28800 | 0 | 1655.8827 | 0 | 0 | 1655.8827 | 0 | 43200 |  |  | 43200 | 0 | 2483.8241 | 0 | 0 | 2483.8241 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0
96 | 0.056094 | 0 | 28800 |  |  | 28800 | 0 | 1615.4953 | 0 | 0 | 1615.4953 | 0 | 43200 |  |  | 43200 | 0 | 2423.243 | 0 | 0 | 2423.243 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0
97 | 0.054725 | 0 | 28800 |  |  | 28800 | 0 | 1576.093 | 0 | 0 | 1576.093 | 0 | 43200 |  |  | 43200 | 0 | 2364.1395 | 0 | 0 | 2364.1395 | 0 | 86400 |  |  | 86400 | 0 | 4728.279 | 0 | 0 | 4728.279 | 0 | 100800 |  |  | 100800 | 0 | 5516.3255 | 0 | 0 | 5516.3255 | 0 | 57600 |  |  | 57600 | 0 | 3152.186 | 0 | 0 | 3152.186 | 0 | 86400 |  |  | 86400 | 0 | 4728.279 | 0 | 0 | 4728.279
98 | 0.053391 | 0 | 28800 |  |  | 28800 | 0 | 1537.6517 | 0 | 0 | 1537.6517 | 0 | 43200 |  |  | 43200 | 0 | 2306.4776 | 0 | 0 | 2306.4776 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0
99 | 0.052088 | 0 | 28800 |  |  | 28800 | 0 | 1500.148 | 0 | 0 | 1500.148 | 0 | 43200 |  |  | 43200 | 0 | 2250.222 | 0 | 0 | 2250.222 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0

## OBC PV Costs
Client/Authority
East Devon District Council
Project name
Sidmouth Beach Management Plan
| Project reference | [116 empty] | 5125587.4534
| Base date for estimates (year 0) |  |  | 2018-01-01
| Scaling factor (e.g. £m, £k, £) |  |  | £
| Initial discount rate |  |  | 3.5%
|  |  | Option S1.1a | 1 Short Groyne |  |  | TOTALS: | PV | PV | PV | PV | PV | Option S1.1b | 2 Short Groynes |  |  | TOTALS: | PV | PV | PV | PV | PV | Option 1.1c: | 1 Long Groyne | [19 empty] | TOTALS: | PV | PV | [17 empty] | PV | PV | Option S1.1d | 1 Long & 1 Short Groynes |  |  | TOTALS: | PV | PV | PV | PV | PV | Option S1.1e | 2 Long Groynes |  |  | TOTALS: | PV | PV | PV | PV | PV | Option 4: | One Offshore Breakwater | [18 empty] | TOTALS: | PV | PV | [17 empty] | PV | PV
[5 empty] | Frequency | Cost
[67 empty] | Maintain Front. A | 1 | 0 | [7 empty] | Maintain Front. A | 1 | 0 | [22 empty] | Maintain Front. A | 0
|  |  |  | Maintain Flood Gates Fron. B | 10 | 28000 | [7 empty] | Maintain Flood Gates Fron. B | 10 | 28000 | [23 empty] | Maintain Flood Gates Fron. B | 10 |  | 28000 | [23 empty] | Maintain Flood Gates Fron. B | 10 | 28000 | [7 empty] | Maintain Flood Gates Fron. B | 10 | 28000 | [22 empty] | Maintain Flood Gates Fron. B | 10 |  | 28000
|  |  |  | Replacement to demountable defences | 50 | 27000 | [7 empty] | Replacement to demountable defences | 50 | 27000 | [23 empty] | Replacement to demountable defences | 50 |  | 27000 | [58 empty] | Replacement to demountable defences | 50 |  | 27000
|  |  |  | Maintenance to demountable defences | 10 | 1000 | [7 empty] | Maintenance to demountable defences | 10 | 1000 | [23 empty] | Maintenance to demountable defences | 10 |  | 1000 | [58 empty] | Maintenance to demountable defences | 10 |  | 1000
|  |  |  | Recharge Fron. B | 10 | 1033560 | [7 empty] | Recharge Fron. B | 10 | 976140 | [23 empty] | Recharge Fron. B | 10 |  | 803880 | [23 empty] | Recharge Fron. B | 10 | 746460 | [7 empty] | Recharge Fron. B | 10 | 918720 | [22 empty] | Recharge Fron. B | 10 |  | 86130
|  |  |  | Recycle Fron. B | 1 | 28800 | [7 empty] | Recycle Fron. B | 1 | 43200 | [23 empty] | Recycle Fron. B | 5 |  | 86400 | [23 empty] | Recycle Fron. B | 5 | 100800 | [7 empty] | Recycle Fron. B | 5 | 57600 | [22 empty] | Recycle Fron. B | 5 |  | 86400
|  |  |  | Recharge Fron. C | 10 | 210540 | [7 empty] | Recharge Fron. C | 10 | 159500 | [23 empty] | Recharge Fron. C | 100 |  | 0 | [23 empty] | Recharge Fron. C | 100 | 0 | [7 empty] | Recharge Fron. C | 100 | 0 | [22 empty] | Recharge Fron. C | 100 |  | 0
|  |  |  | Repiar River Wall Fron. D | 30 | 100000 | [7 empty] | Repiar River Wall Fron. D | 30 | 100000 | [23 empty] | Repiar River Wall Fron. D | 30 |  | 100000 | [23 empty] | Repiar River Wall Fron. D | 30 | 100000 | [7 empty] | Repiar River Wall Fron. D | 30 | 100000 | [22 empty] | Repiar River Wall Fron. D | 30 |  | 100000
|  |  |  | Year of construction: | 2 | [8 empty] | Year of construction: | 2 | [24 empty] | Year of construction: | 2 | [25 empty] | Year of construction: | 2 | [8 empty] | Year of construction: | 2 | [23 empty] | Year of construction: | 2
|  |  | Capital | Maint. | Other | Negative costs | Cash | Capital | Maint | Other | Negative costs | Total PV cost | Capital | Maint. | Other | Negative costs | Cash | Capital | Maint | Other | Negative costs | Total PV cost | Construction Costs | Maint. | Existing staff costs | Further staff costs | Site investigation and survey | Consultants’ fees | Contractors’ fees | Cost consultants’ fees |  | Inflation allowance | Environmental enhancement | Environmental mitigation | Existing staff costs | Further staff costs | Consultants’ fees | Site supervision | Cost consultants’ fees | Land purchase & compensation | Risk - Monte Carlo 50% | Risk - Monte Carlo 50% | Negative costs | Cash | Capital | Maint | Existing staff costs | Further staff costs | Site investigation and survey | Consultants’ fees | Contractors’ fees | Cost consultants’ fees | Construction costs | Inflation allowance for months | Environmental enhancement | Environmental mitigation | Existing staff costs | Further staff costs | Consultants’ fees | Site supervision | Cost consultants’ fees | Land purchase & compensation | Risk - Monte Carlo 50% - Capital | Risk - Monte Carlo 50% - Maintenance | Total PV cost | Capital | Maint. | Other | Negative costs | Cash | Capital | Maint | Other | Negative costs | Total PV cost | Capital | Maint. | Other | Negative costs | Cash | Capital | Maint | Other | Negative costs | Total PV cost | Construction Costs | Maint. | Existing staff costs | Further staff costs | Site investigation and survey | Consultants’ fees | Contractors’ fees | Cost consultants’ fees | Inflation allowance | Environmental enhancement | Environmental mitigation | Existing staff costs | Further staff costs | Consultants’ fees | Site supervision | Cost consultants’ fees | Land purchase & compensation | Risk - Monte Carlo 95% | Risk - OB Future Costs | Negative costs | Cash | Capital | Maint | Existing staff costs | Further staff costs | Site investigation and survey | Consultants’ fees | Contractors’ fees | Cost consultants’ fees | Construction costs | Inflation allowance for months | Environmental enhancement | Environmental mitigation | Existing staff costs | Further staff costs | Consultants’ fees | Site supervision | Cost consultants’ fees | Land purchase & compensation | Risk - Monte Carlo 95% - Capital | Risk - Monte Carlo 50% - Maintenance | Total PV cost
|  | cash sum | 8257454.7049 | 14578500 | 0 | 0 | 22835954.7049 | 7708422.3248 | 3742840.0682 | 0 | 0 | 11451262.393 | 8539893.5958 | 14999160 | 0 | 0 | 23539053.5958 | 7972082.0517 | 3882546.6837 | 0 | 0 | 11854628.7354 | 9070371.9242 | 9464520 | 0 | 50000 | 375000 | 345000 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 267375 | 0 | 45000 | 5125587.4534 | 2460775.2 | 0 | 27203629.5776 | 8467289.2475 | 2395779.474 | 0 | 48309.1787 | 362318.8406 | 333333.3333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 258333.3333 | 0 | 43478.2609 | 4952258.4091 | 622902.6632 | 17484002.7407 | 9382808.1511 | 9185340 | 0 | 0 | 18568148.1511 | 8758951.8085 | 2329592.4679 | 0 | 0 | 11088544.2765 | 10029350.3704 | 9914880 | 0 | 0 | 19944230.3704 | 9362505.8885 | 2506237.2217 | 0 | 0 | 11868743.1101 | 12108570.2142 | 3004770 | 0 | 50000 | 375000 | 395000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 267375 | 0 | 45000 | 5125587.4534 | 901431 | 0 | 22272733.6676 | 11303479.8611 | 755672.152 | 0 | 48309.1787 | 362318.8406 | 381642.5121 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 258333.3333 | 0 | 43478.2609 | 4952258.4091 | 226701.6456 | 18332194.1934
Discount
| year | Factor
2023/24 | 0 | 1 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [19 empty] | 0 | 0 | 0 | [17 empty] | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [16 empty] | 0 |  | 0 | 0 | 0 | [17 empty] | 0 | 0
| 1 | 0.96618 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 50000 | 375000 | 345000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45000 | 0 |  |  | 815000 | 0 | 0 | 0 | 48309.1787 | 362318.8406 | 333333.3333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43478.2609 | 0 | 0 | 787439.6135 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 50000 | 375000 | 395000 | 0 | 0 | [8 empty] | 45000 |  | 0 |  | 865000 | 0 | 0 | 0 | 48309.1787 | 362318.8406 | 381642.5121 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43478.2609 | 0 | 0 | 835748.7923
| 2 | 0.93351 | 8257454.7049 | 0 |  |  | 8257454.7049 | 7708422.3248 | 0 | 0 | 0 | 7708422.3248 | 8539893.5958 | 0 |  |  | 8539893.5958 | 7972082.0517 | 0 | 0 | 0 | 7972082.0517 | 9070371.9242 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 267375 | 0 | 0 | 5125587.4534 |  |  | 14463334.3776 | 8467289.2475 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 258333.3333 | 0 | 0 | 4952258.4091 | 0 | 13677880.99 | 9382808.1511 | 0 |  |  | 9382808.1511 | 8758951.8085 | 0 | 0 | 0 | 8758951.8085 | 10029350.3704 | 0 |  |  | 10029350.3704 | 9362505.8885 | 0 | 0 | 0 | 9362505.8885 | 12108570.2142 | 0 | [7 empty] | 0 | 0 | 0 | 0 |  | 267375 |  |  | 5125587.4534 | 0 |  | 17501532.6676 | 11303479.8611 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 258333.3333 | 0 | 0 | 4952258.4091 | 0 | 16514071.6035
| 3 | 0.90194 | 0 | 28800 |  |  | 28800 | 0 | 25975.9499 | 0 | 0 | 25975.9499 | 0 | 43200 |  |  | 43200 | 0 | 38963.9249 | 0 | 0 | 38963.9249 | 0 | 0 | [17 empty] | 0 |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [16 empty] | 0 |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 4 | 0.87144 | 0 | 28800 |  |  | 28800 | 0 | 25097.5362 | 0 | 0 | 25097.5362 | 0 | 43200 |  |  | 43200 | 0 | 37646.3042 | 0 | 0 | 37646.3042 | 0 | 0 | [17 empty] | 0 |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [16 empty] | 0 |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 5 | 0.84197 | 0 | 28800 |  |  | 28800 | 0 | 24248.8272 | 0 | 0 | 24248.8272 | 0 | 43200 |  |  | 43200 | 0 | 36373.2408 | 0 | 0 | 36373.2408 | 0 | 0 | [17 empty] | 0 |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [16 empty] | 0 |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 6 | 0.8135 | 0 | 28800 |  |  | 28800 | 0 | 23428.8186 | 0 | 0 | 23428.8186 | 0 | 43200 |  |  | 43200 | 0 | 35143.2278 | 0 | 0 | 35143.2278 | 0 | 0 | [17 empty] | 0 |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [16 empty] | 0 |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 7 | 0.78599 | 0 | 28800 |  |  | 28800 | 0 | 22636.5397 | 0 | 0 | 22636.5397 | 0 | 43200 |  |  | 43200 | 0 | 33954.8095 | 0 | 0 | 33954.8095 | 0 | 86400 | [17 empty] | 22464 |  | 108864 | 0 | 67909.619 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17656.5009 | 85566.1199 | 0 | 100800 |  |  | 100800 | 0 | 79227.8888 | 0 | 0 | 79227.8888 | 0 | 57600 |  |  | 57600 | 0 | 45273.0793 | 0 | 0 | 45273.0793 | 0 | 86400 | [16 empty] | 25920 |  | 112320 | 0 | 67909.619 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20372.8857 | 88282.5047
| 8 | 0.75941 | 0 | 28800 |  |  | 28800 | 0 | 21871.0528 | 0 | 0 | 21871.0528 | 0 | 43200 |  |  | 43200 | 0 | 32806.5792 | 0 | 0 | 32806.5792 | 0 | 0 | [17 empty] | 0 |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [16 empty] | 0 |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 9 | 0.73373 | 0 | 28800 |  |  | 28800 | 0 | 21131.452 | 0 | 0 | 21131.452 | 0 | 43200 |  |  | 43200 | 0 | 31697.178 | 0 | 0 | 31697.178 | 0 | 0 | [17 empty] | 0 |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [16 empty] | 0 |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 10 | 0.70892 | 0 | 28800 |  |  | 28800 | 0 | 20416.8618 | 0 | 0 | 20416.8618 | 0 | 43200 |  |  | 43200 | 0 | 30625.2928 | 0 | 0 | 30625.2928 | 0 | 0 | [17 empty] | 0 |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [16 empty] | 0 |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 11 | 0.68495 | 0 | 28800 |  |  | 28800 | 0 | 19726.4366 | 0 | 0 | 19726.4366 | 0 | 43200 |  |  | 43200 | 0 | 29589.6548 | 0 | 0 | 29589.6548 | 0 | 0 | [17 empty] | 0 |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [16 empty] | 0 |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 12 | 0.66178 | 0 | 1301900 |  |  | 1301900 | 0 | 861575.676 | 0 | 0 | 861575.676 | 0 | 1207840 |  |  | 1207840 | 0 | 799328.339 | 0 | 0 | 799328.339 | 0 | 919280 | [17 empty] | 239012.8 |  | 1158292.8 | 0 | 608364.1505 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 158174.6791 | 766538.8296 | 0 | 875260 |  |  | 875260 | 0 | 579232.4497 | 0 | 0 | 579232.4497 | 0 | 1004320 |  |  | 1004320 | 0 | 664642.2021 | 0 | 0 | 664642.2021 | 0 | 201530 | [16 empty] | 60459 |  | 261989 | 0 | 133369.1881 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40010.7564 | 173379.9445
| 13 | 0.6394 | 0 | 28800 |  |  | 28800 | 0 | 18414.8396 | 0 | 0 | 18414.8396 | 0 | 43200 |  |  | 43200 | 0 | 27622.2594 | 0 | 0 | 27622.2594 | 0 | 0 | [17 empty] | 0 |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [16 empty] | 0 |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 14 | 0.61778 | 0 | 28800 |  |  | 28800 | 0 | 17792.1156 | 0 | 0 | 17792.1156 | 0 | 43200 |  |  | 43200 | 0 | 26688.1733 | 0 | 0 | 26688.1733 | 0 | 0 | [17 empty] | 0 |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [16 empty] | 0 |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 15 | 0.59689 | 0 | 28800 |  |  | 28800 | 0 | 17190.4498 | 0 | 0 | 17190.4498 | 0 | 43200 |  |  | 43200 | 0 | 25785.6747 | 0 | 0 | 25785.6747 | 0 | 0 | [17 empty] | 0 |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [16 empty] | 0 |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 16 | 0.57671 | 0 | 28800 |  |  | 28800 | 0 | 16609.1303 | 0 | 0 | 16609.1303 | 0 | 43200 |  |  | 43200 | 0 | 24913.6954 | 0 | 0 | 24913.6954 | 0 | 0 | [17 empty] | 0 |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [16 empty] | 0 |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 17 | 0.5572 | 0 | 28800 |  |  | 28800 | 0 | 16047.4688 | 0 | 0 | 16047.4688 | 0 | 43200 |  |  | 43200 | 0 | 24071.2033 | 0 | 0 | 24071.2033 | 0 | 86400 | [17 empty] | 22464 |  | 108864 | 0 | 48142.4065 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12517.0257 | 60659.4322 | 0 | 100800 |  |  | 100800 | 0 | 56166.141 | 0 | 0 | 56166.141 | 0 | 57600 |  |  | 57600 | 0 | 32094.9377 | 0 | 0 | 32094.9377 | 0 | 86400 | [16 empty] | 25920 |  | 112320 | 0 | 48142.4065 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14442.722 | 62585.1285
| 18 | 0.53836 | 0 | 28800 |  |  | 28800 | 0 | 15504.8008 | 0 | 0 | 15504.8008 | 0 | 43200 |  |  | 43200 | 0 | 23257.2012 | 0 | 0 | 23257.2012 | 0 | 0 | [17 empty] | 0 |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [16 empty] | 0 |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 19 | 0.52016 | 0 | 28800 |  |  | 28800 | 0 | 14980.4839 | 0 | 0 | 14980.4839 | 0 | 43200 |  |  | 43200 | 0 | 22470.7258 | 0 | 0 | 22470.7258 | 0 | 0 | [17 empty] | 0 |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [16 empty] | 0 |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 20 | 0.50257 | 0 | 28800 |  |  | 28800 | 0 | 14473.8975 | 0 | 0 | 14473.8975 | 0 | 43200 |  |  | 43200 | 0 | 21710.8462 | 0 | 0 | 21710.8462 | 0 | 0 | [17 empty] | 0 |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [16 empty] | 0 |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 21 | 0.48557 | 0 | 28800 |  |  | 28800 | 0 | 13984.442 | 0 | 0 | 13984.442 | 0 | 43200 |  |  | 43200 | 0 | 20976.663 | 0 | 0 | 20976.663 | 0 | 0 | [17 empty] | 0 |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [16 empty] | 0 |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 22 | 0.46915 | 0 | 1301900 |  |  | 1301900 | 0 | 610787.2062 | 0 | 0 | 610787.2062 | 0 | 1207840 |  |  | 1207840 | 0 | 566658.8979 | 0 | 0 | 566658.8979 | 0 | 919280 | [17 empty] | 239012.8 |  | 1158292.8 | 0 | 431280.7918 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 112133.0059 | 543413.7977 | 0 | 875260 |  |  | 875260 | 0 | 410628.7811 | 0 | 0 | 410628.7811 | 0 | 1004320 |  |  | 1004320 | 0 | 471177.3615 | 0 | 0 | 471177.3615 | 0 | 201530 | [16 empty] | 60459 |  | 261989 | 0 | 94547.9266 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28364.378 | 122912.3046
| 23 | 0.45329 | 0 | 28800 |  |  | 28800 | 0 | 13054.6262 | 0 | 0 | 13054.6262 | 0 | 43200 |  |  | 43200 | 0 | 19581.9394 | 0 | 0 | 19581.9394 | 0 | 0 | [17 empty] | 0 |  | 0 | 0 | 0 | [17 empty] | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [16 empty] | 0 |  | 0 | 0 | 0 | [17 empty] | 0 | 0
| 24 | 0.43796 | 0 | 28800 |  |  | 28800 | 0 | 12613.1655 | 0 | 0 | 12613.1655 | 0 | 43200 |  |  | 43200 | 0 | 18919.7482 | 0 | 0 | 18919.7482 | 0 | 0 | [17 empty] | 0 |  | 0 | 0 | 0 | [17 empty] | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [16 empty] | 0 |  | 0 | 0 | 0 | [17 empty] | 0 | 0
| 25 | 0.42315 | 0 | 28800 |  |  | 28800 | 0 | 12186.6333 | 0 | 0 | 12186.6333 | 0 | 43200 |  |  | 43200 | 0 | 18279.9499 | 0 | 0 | 18279.9499 | 0 | 0 | [17 empty] | 0 |  | 0 | 0 | 0 | [17 empty] | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [16 empty] | 0 |  | 0 | 0 | 0 | [17 empty] | 0 | 0
| 26 | 0.40884 | 0 | 28800 |  |  | 28800 | 0 | 11774.5249 | 0 | 0 | 11774.5249 | 0 | 43200 |  |  | 43200 | 0 | 17661.7874 | 0 | 0 | 17661.7874 | 0 | 0 | [17 empty] | 0 |  | 0 | 0 | 0 | [17 empty] | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [16 empty] | 0 |  | 0 | 0 | 0 | [17 empty] | 0 | 0
| 27 | 0.39501 | 0 | 28800 |  |  | 28800 | 0 | 11376.3526 | 0 | 0 | 11376.3526 | 0 | 43200 |  |  | 43200 | 0 | 17064.5289 | 0 | 0 | 17064.5289 | 0 | 86400 | [17 empty] | 22464 |  | 108864 | 0 | 34129.0577 | [17 empty] | 8873.555 | 43002.6127 | 0 | 100800 |  |  | 100800 | 0 | 39817.234 | 0 | 0 | 39817.234 | 0 | 57600 |  |  | 57600 | 0 | 22752.7052 | 0 | 0 | 22752.7052 | 0 | 86400 | [16 empty] | 25920 |  | 112320 | 0 | 34129.0577 | [17 empty] | 10238.7173 | 44367.7751
| 28 | 0.38165 | 0 | 28800 |  |  | 28800 | 0 | 10991.645 | 0 | 0 | 10991.645 | 0 | 43200 |  |  | 43200 | 0 | 16487.4675 | 0 | 0 | 16487.4675 | 0 | 0 | [17 empty] | 0 |  | 0 | 0 | 0 | [17 empty] | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [16 empty] | 0 |  | 0 | 0 | 0 | [17 empty] | 0 | 0
| 29 | 0.36875 | 0 | 28800 |  |  | 28800 | 0 | 10619.9469 | 0 | 0 | 10619.9469 | 0 | 43200 |  |  | 43200 | 0 | 15929.9203 | 0 | 0 | 15929.9203 | 0 | 0 | [17 empty] | 0 |  | 0 | 0 | 0 | [17 empty] | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [16 empty] | 0 |  | 0 | 0 | 0 | [17 empty] | 0 | 0
| 30 | 0.35628 | 0 | 28800 |  |  | 28800 | 0 | 10260.8182 | 0 | 0 | 10260.8182 | 0 | 43200 |  |  | 43200 | 0 | 15391.2273 | 0 | 0 | 15391.2273 | 0 | 0 | [17 empty] | 0 |  | 0 | 0 | 0 | [17 empty] | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [16 empty] | 0 |  | 0 | 0 | 0 | [17 empty] | 0 | 0
| 31 | 0.3459 | 0 | 28800 |  |  | 28800 | 0 | 9961.9594 | 0 | 0 | 9961.9594 | 0 | 43200 |  |  | 43200 | 0 | 14942.9392 | 0 | 0 | 14942.9392 | 0 | 0 | [17 empty] | 0 |  | 0 | 0 | 0 | [17 empty] | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [16 empty] | 0 |  | 0 | 0 | 0 | [17 empty] | 0 | 0
| 32 | 0.33583 | 0 | 1401900 |  |  | 1401900 | 0 | 470795.2718 | 0 | 0 | 470795.2718 | 0 | 1307840 |  |  | 1307840 | 0 | 439207.4244 | 0 | 0 | 439207.4244 | 0 | 1019280 | [17 empty] | 265012.8 |  | 1284292.8 | 0 | 342301.3087 | [17 empty] | 88998.3403 | 431299.6489 | 0 | 975260 |  |  | 975260 | 0 | 327518.2229 | 0 | 0 | 327518.2229 | 0 | 1104320 |  |  | 1104320 | 0 | 370860.0004 | 0 | 0 | 370860.0004 | 0 | 301530 | [16 empty] | 90459 |  | 391989 | 0 | 101261.7864 | [17 empty] | 30378.5359 | 131640.3223
| 33 | 0.32605 | 0 | 28800 |  |  | 28800 | 0 | 9390.1022 | 0 | 0 | 9390.1022 | 0 | 43200 |  |  | 43200 | 0 | 14085.1533 | 0 | 0 | 14085.1533 | 0 | 0 | [17 empty] | 0 |  | 0 | 0 | 0 | [17 empty] | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [16 empty] | 0 |  | 0 | 0 | 0 | [17 empty] | 0 | 0
| 34 | 0.31655 | 0 | 28800 |  |  | 28800 | 0 | 9116.6041 | 0 | 0 | 9116.6041 | 0 | 43200 |  |  | 43200 | 0 | 13674.9061 | 0 | 0 | 13674.9061 | 0 | 0 | [17 empty] | 0 |  | 0 | 0 | 0 | [17 empty] | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [16 empty] | 0 |  | 0 | 0 | 0 | [17 empty] | 0 | 0
| 35 | 0.30733 | 0 | 28800 |  |  | 28800 | 0 | 8851.0719 | 0 | 0 | 8851.0719 | 0 | 43200 |  |  | 43200 | 0 | 13276.6079 | 0 | 0 | 13276.6079 | 0 | 0 | [17 empty] | 0 |  | 0 | 0 | 0 | [17 empty] | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [16 empty] | 0 |  | 0 | 0 | 0 | [17 empty] | 0 | 0
| 36 | 0.29838 | 0 | 28800 |  |  | 28800 | 0 | 8593.2737 | 0 | 0 | 8593.2737 | 0 | 43200 |  |  | 43200 | 0 | 12889.9106 | 0 | 0 | 12889.9106 | 0 | 0 | [17 empty] | 0 |  | 0 | 0 | 0 | [17 empty] | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [16 empty] | 0 |  | 0 | 0 | 0 | [17 empty] | 0 | 0
| 37 | 0.28969 | 0 | 28800 |  |  | 28800 | 0 | 8342.9842 | 0 | 0 | 8342.9842 | 0 | 43200 |  |  | 43200 | 0 | 12514.4763 | 0 | 0 | 12514.4763 | 0 | 86400 | [17 empty] | 22464 |  | 108864 | 0 | 25028.9526 | [17 empty] | 6507.5277 | 31536.4803 | 0 | 100800 |  |  | 100800 | 0 | 29200.4447 | 0 | 0 | 29200.4447 | 0 | 57600 |  |  | 57600 | 0 | 16685.9684 | 0 | 0 | 16685.9684 | 0 | 86400 | [16 empty] | 25920 |  | 112320 | 0 | 25028.9526 | [17 empty] | 7508.6858 | 32537.6384
| 38 | 0.28125 | 0 | 28800 |  |  | 28800 | 0 | 8099.9847 | 0 | 0 | 8099.9847 | 0 | 43200 |  |  | 43200 | 0 | 12149.977 | 0 | 0 | 12149.977 | 0 | 0 | [17 empty] | 0 |  | 0 | 0 | 0 | [17 empty] | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [16 empty] | 0 |  | 0 | 0 | 0 | [17 empty] | 0 | 0
| 39 | 0.27306 | 0 | 28800 |  |  | 28800 | 0 | 7864.0628 | 0 | 0 | 7864.0628 | 0 | 43200 |  |  | 43200 | 0 | 11796.0942 | 0 | 0 | 11796.0942 | 0 | 0 | [17 empty] | 0 |  | 0 | 0 | 0 | [17 empty] | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [16 empty] | 0 |  | 0 | 0 | 0 | [17 empty] | 0 | 0
| 40 | 0.2651 | 0 | 28800 |  |  | 28800 | 0 | 7635.0124 | 0 | 0 | 7635.0124 | 0 | 43200 |  |  | 43200 | 0 | 11452.5186 | 0 | 0 | 11452.5186 | 0 | 0 | [17 empty] | 0 |  | 0 | 0 | 0 | [17 empty] | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [16 empty] | 0 |  | 0 | 0 | 0 | [17 empty] | 0 | 0
| 41 | 0.25738 | 0 | 28800 |  |  | 28800 | 0 | 7412.6334 | 0 | 0 | 7412.6334 | 0 | 43200 |  |  | 43200 | 0 | 11118.9501 | 0 | 0 | 11118.9501 | 0 | 0 | [17 empty] | 0 |  | 0 | 0 | 0 | [17 empty] | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [16 empty] | 0 |  | 0 | 0 | 0 | [17 empty] | 0 | 0
| 42 | 0.24989 | 0 | 1301900 |  |  | 1301900 | 0 | 325327.246 | 0 | 0 | 325327.246 | 0 | 1207840 |  |  | 1207840 | 0 | 301822.921 | 0 | 0 | 301822.921 | 0 | 919280 | [17 empty] | 239012.8 |  | 1158292.8 | 0 | 229715.6699 | [17 empty] | 59726.0742 | 289441.7441 | 0 | 875260 |  |  | 875260 | 0 | 218715.6658 | 0 | 0 | 218715.6658 | 0 | 1004320 |  |  | 1004320 | 0 | 250966.0187 | 0 | 0 | 250966.0187 | 0 | 201530 | [16 empty] | 60459 |  | 261989 | 0 | 50359.6281 | [17 empty] | 15107.8884 | 65467.5166
| 43 | 0.24261 | 0 | 28800 |  |  | 28800 | 0 | 6987.1179 | 0 | 0 | 6987.1179 | 0 | 43200 |  |  | 43200 | 0 | 10480.6769 | 0 | 0 | 10480.6769 | 0 | 0 | [17 empty] | 0 |  | 0 | 0 | 0 | [17 empty] | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [16 empty] | 0 |  | 0 | 0 | 0 | [17 empty] | 0 | 0
| 44 | 0.23554 | 0 | 28800 |  |  | 28800 | 0 | 6783.6096 | 0 | 0 | 6783.6096 | 0 | 43200 |  |  | 43200 | 0 | 10175.4144 | 0 | 0 | 10175.4144 | 0 | 0 | [17 empty] | 0 |  | 0 | 0 | 0 | [17 empty] | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [16 empty] | 0 |  | 0 | 0 | 0 | [17 empty] | 0 | 0
| 45 | 0.22868 | 0 | 28800 |  |  | 28800 | 0 | 6586.0288 | 0 | 0 | 6586.0288 | 0 | 43200 |  |  | 43200 | 0 | 9879.0432 | 0 | 0 | 9879.0432 | 0 | 0 | [17 empty] | 0 |  | 0 | 0 | 0 | [17 empty] | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [16 empty] | 0 |  | 0 | 0 | 0 | [17 empty] | 0 | 0
| 46 | 0.22202 | 0 | 28800 |  |  | 28800 | 0 | 6394.2027 | 0 | 0 | 6394.2027 | 0 | 43200 |  |  | 43200 | 0 | 9591.304 | 0 | 0 | 9591.304 | 0 | 0 | [17 empty] | 0 |  | 0 | 0 | 0 | [17 empty] | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [16 empty] | 0 |  | 0 | 0 | 0 | [17 empty] | 0 | 0
| 47 | 0.21555 | 0 | 28800 |  |  | 28800 | 0 | 6207.9638 | 0 | 0 | 6207.9638 | 0 | 43200 |  |  | 43200 | 0 | 9311.9457 | 0 | 0 | 9311.9457 | 0 | 86400 | [17 empty] | 22464 |  | 108864 | 0 | 18623.8913 | [17 empty] | 4842.2117 | 23466.1031 | 0 | 100800 |  |  | 100800 | 0 | 21727.8732 | 0 | 0 | 21727.8732 | 0 | 57600 |  |  | 57600 | 0 | 12415.9275 | 0 | 0 | 12415.9275 | 0 | 86400 | [16 empty] | 25920 |  | 112320 | 0 | 18623.8913 | [17 empty] | 5587.1674 | 24211.0587
| 48 | 0.20928 | 0 | 28800 |  |  | 28800 | 0 | 6027.1493 | 0 | 0 | 6027.1493 | 0 | 43200 |  |  | 43200 | 0 | 9040.7239 | 0 | 0 | 9040.7239 | 0 | 0 | [17 empty] | 0 |  | 0 | 0 | 0 | [17 empty] | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [16 empty] | 0 |  | 0 | 0 | 0 | [17 empty] | 0 | 0
| 49 | 0.20318 | 0 | 28800 |  |  | 28800 | 0 | 5851.6013 | 0 | 0 | 5851.6013 | 0 | 43200 |  |  | 43200 | 0 | 8777.4019 | 0 | 0 | 8777.4019 | 0 | 0 | [17 empty] | 0 |  | 0 | 0 | 0 | [17 empty] | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [16 empty] | 0 |  | 0 | 0 | 0 | [17 empty] | 0 | 0
| 50 | 0.19726 | 0 | 28800 |  |  | 28800 | 0 | 5681.1663 | 0 | 0 | 5681.1663 | 0 | 43200 |  |  | 43200 | 0 | 8521.7494 | 0 | 0 | 8521.7494 | 0 | 0 | [17 empty] | 0 |  | 0 | 0 | 0 | [17 empty] | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [16 empty] | 0 |  | 0 | 0 | 0 | [17 empty] | 0 | 0
| 51 | 0.19152 | 0 | 28800 |  |  | 28800 | 0 | 5515.6954 | 0 | 0 | 5515.6954 | 0 | 43200 |  |  | 43200 | 0 | 8273.5431 | 0 | 0 | 8273.5431 | 0 | 0 | [17 empty] | 0 |  | 0 | 0 | 0 | [17 empty] | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [16 empty] | 0 |  | 0 | 0 | 0 | [17 empty] | 0 | 0
| 52 | 0.18594 | 0 | 1328900 |  |  | 1328900 | 0 | 247094.3779 | 0 | 0 | 247094.3779 | 0 | 1234840 |  |  | 1234840 | 0 | 229604.9527 | 0 | 0 | 229604.9527 | 0 | 946280 | [17 empty] | 246032.8 |  | 1192312.8 | 0 | 175950.386 | [17 empty] | 45747.1004 | 221697.4863 | 0 | 875260 |  |  | 875260 | 0 | 162744.996 | 0 | 0 | 162744.996 | 0 | 1004320 |  |  | 1004320 | 0 | 186742.2873 | 0 | 0 | 186742.2873 | 0 | 228530 | [16 empty] | 68559 |  | 297089 | 0 | 42492.6467 | [17 empty] | 12747.794 | 55240.4407
| 53 | 0.18052 | 0 | 28800 |  |  | 28800 | 0 | 5199.0719 | 0 | 0 | 5199.0719 | 0 | 43200 |  |  | 43200 | 0 | 7798.6079 | 0 | 0 | 7798.6079 | 0 | 0 | [17 empty] | 0 |  | 0 | 0 | 0 | [17 empty] | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [16 empty] | 0 |  | 0 | 0 | 0 | [17 empty] | 0 | 0
| 54 | 0.17527 | 0 | 28800 |  |  | 28800 | 0 | 5047.6426 | 0 | 0 | 5047.6426 | 0 | 43200 |  |  | 43200 | 0 | 7571.464 | 0 | 0 | 7571.464 | 0 | 0 | [17 empty] | 0 |  | 0 | 0 | 0 | [17 empty] | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [16 empty] | 0 |  | 0 | 0 | 0 | [17 empty] | 0 | 0
| 55 | 0.17016 | 0 | 28800 |  |  | 28800 | 0 | 4900.6239 | 0 | 0 | 4900.6239 | 0 | 43200 |  |  | 43200 | 0 | 7350.9359 | 0 | 0 | 7350.9359 | 0 | 0 | [17 empty] | 0 |  | 0 | 0 | 0 | [17 empty] | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [16 empty] | 0 |  | 0 | 0 | 0 | [17 empty] | 0 | 0
| 56 | 0.1652 | 0 | 28800 |  |  | 28800 | 0 | 4757.8873 | 0 | 0 | 4757.8873 | 0 | 43200 |  |  | 43200 | 0 | 7136.831 | 0 | 0 | 7136.831 | 0 | 0 | [17 empty] | 0 |  | 0 | 0 | 0 | [17 empty] | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [16 empty] | 0 |  | 0 | 0 | 0 | [17 empty] | 0 | 0
| 57 | 0.16039 | 0 | 28800 |  |  | 28800 | 0 | 4619.3081 | 0 | 0 | 4619.3081 | 0 | 43200 |  |  | 43200 | 0 | 6928.9621 | 0 | 0 | 6928.9621 | 0 | 86400 | [17 empty] | 22464 |  | 108864 | 0 | 13857.9242 | [17 empty] | 3603.0603 | 17460.9845 | 0 | 100800 |  |  | 100800 | 0 | 16167.5782 | 0 | 0 | 16167.5782 | 0 | 57600 |  |  | 57600 | 0 | 9238.6161 | 0 | 0 | 9238.6161 | 0 | 86400 | [16 empty] | 25920 |  | 112320 | 0 | 13857.9242 | [17 empty] | 4157.3773 | 18015.3015
| 58 | 0.15572 | 0 | 28800 |  |  | 28800 | 0 | 4484.7651 | 0 | 0 | 4484.7651 | 0 | 43200 |  |  | 43200 | 0 | 6727.1477 | 0 | 0 | 6727.1477 | 0 | 0 | [17 empty] | 0 |  | 0 | 0 | 0 | [17 empty] | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [16 empty] | 0 |  | 0 | 0 | 0 | [17 empty] | 0 | 0
| 59 | 0.15119 | 0 | 28800 |  |  | 28800 | 0 | 4354.1409 | 0 | 0 | 4354.1409 | 0 | 43200 |  |  | 43200 | 0 | 6531.2113 | 0 | 0 | 6531.2113 | 0 | 0 | [17 empty] | 0 |  | 0 | 0 | 0 | [17 empty] | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [16 empty] | 0 |  | 0 | 0 | 0 | [17 empty] | 0 | 0
| 60 | 0.14678 | 0 | 28800 |  |  | 28800 | 0 | 4227.3213 | 0 | 0 | 4227.3213 | 0 | 43200 |  |  | 43200 | 0 | 6340.9819 | 0 | 0 | 6340.9819 | 0 | 0 | [17 empty] | 0 |  | 0 | 0 | 0 | [17 empty] | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [16 empty] | 0 |  | 0 | 0 | 0 | [17 empty] | 0 | 0
| 61 | 0.14251 | 0 | 28800 |  |  | 28800 | 0 | 4104.1954 | 0 | 0 | 4104.1954 | 0 | 43200 |  |  | 43200 | 0 | 6156.2931 | 0 | 0 | 6156.2931 | 0 | 0 | [17 empty] | 0 |  | 0 | 0 | 0 | [17 empty] | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [16 empty] | 0 |  | 0 | 0 | 0 | [17 empty] | 0 | 0
| 62 | 0.13836 | 0 | 1401900 |  |  | 1401900 | 0 | 193961.4184 | 0 | 0 | 193961.4184 | 0 | 1307840 |  |  | 1307840 | 0 | 180947.6435 | 0 | 0 | 180947.6435 | 0 | 1019280 | [17 empty] | 265012.8 |  | 1284292.8 | 0 | 141023.6069 | [17 empty] | 36666.1378 | 177689.7447 | 0 | 975260 |  |  | 975260 | 0 | 134933.1714 | 0 | 0 | 134933.1714 | 0 | 1104320 |  |  | 1104320 | 0 | 152789.4098 | 0 | 0 | 152789.4098 | 0 | 301530 | [16 empty] | 90459 |  | 391989 | 0 | 41718.5152 | [17 empty] | 12515.5546 | 54234.0698
| 63 | 0.13433 | 0 | 28800 |  |  | 28800 | 0 | 3868.5978 | 0 | 0 | 3868.5978 | 0 | 43200 |  |  | 43200 | 0 | 5802.8967 | 0 | 0 | 5802.8967 | 0 | 0 | [17 empty] | 0 |  | 0 | 0 | 0 | [17 empty] | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [16 empty] | 0 |  | 0 | 0 | 0 | [17 empty] | 0 | 0
| 64 | 0.13041 | 0 | 28800 |  |  | 28800 | 0 | 3755.9202 | 0 | 0 | 3755.9202 | 0 | 43200 |  |  | 43200 | 0 | 5633.8803 | 0 | 0 | 5633.8803 | 0 | 0 | [17 empty] | 0 |  | 0 | 0 | 0 | [17 empty] | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [16 empty] | 0 |  | 0 | 0 | 0 | [17 empty] | 0 | 0
| 65 | 0.12662 | 0 | 28800 |  |  | 28800 | 0 | 3646.5244 | 0 | 0 | 3646.5244 | 0 | 43200 |  |  | 43200 | 0 | 5469.7867 | 0 | 0 | 5469.7867 | 0 | 0 | [17 empty] | 0 |  | 0 | 0 | 0 | [17 empty] | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [16 empty] | 0 |  | 0 | 0 | 0 | [17 empty] | 0 | 0
| 66 | 0.12293 | 0 | 28800 |  |  | 28800 | 0 | 3540.315 | 0 | 0 | 3540.315 | 0 | 43200 |  |  | 43200 | 0 | 5310.4725 | 0 | 0 | 5310.4725 | 0 | 0 | [17 empty] | 0 |  | 0 | 0 | 0 | [17 empty] | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [16 empty] | 0 |  | 0 | 0 | 0 | [17 empty] | 0 | 0
| 67 | 0.11935 | 0 | 28800 |  |  | 28800 | 0 | 3437.199 | 0 | 0 | 3437.199 | 0 | 43200 |  |  | 43200 | 0 | 5155.7985 | 0 | 0 | 5155.7985 | 0 | 86400 | [17 empty] | 22464 |  | 108864 | 0 | 10311.5971 | [17 empty] | 2681.0152 | 12992.6123 | 0 | 100800 |  |  | 100800 | 0 | 12030.1966 | 0 | 0 | 12030.1966 | 0 | 57600 |  |  | 57600 | 0 | 6874.398 | 0 | 0 | 6874.398 | 0 | 86400 | [16 empty] | 25920 |  | 112320 | 0 | 10311.5971 | [17 empty] | 3093.4791 | 13405.0762
| 68 | 0.11587 | 0 | 28800 |  |  | 28800 | 0 | 3337.0864 | 0 | 0 | 3337.0864 | 0 | 43200 |  |  | 43200 | 0 | 5005.6296 | 0 | 0 | 5005.6296 | 0 | 0 | [17 empty] | 0 |  | 0 | 0 | 0 | [17 empty] | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [16 empty] | 0 |  | 0 | 0 | 0 | [17 empty] | 0 | 0
| 69 | 0.1125 | 0 | 28800 |  |  | 28800 | 0 | 3239.8897 | 0 | 0 | 3239.8897 | 0 | 43200 |  |  | 43200 | 0 | 4859.8346 | 0 | 0 | 4859.8346 | 0 | 0 | [17 empty] | 0 |  | 0 | 0 | 0 | [17 empty] | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [16 empty] | 0 |  | 0 | 0 | 0 | [17 empty] | 0 | 0
| 70 | 0.10922 | 0 | 28800 |  |  | 28800 | 0 | 3145.524 | 0 | 0 | 3145.524 | 0 | 43200 |  |  | 43200 | 0 | 4718.286 | 0 | 0 | 4718.286 | 0 | 0 | [17 empty] | 0 |  | 0 | 0 | 0 | [17 empty] | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [16 empty] | 0 |  | 0 | 0 | 0 | [17 empty] | 0 | 0
| 71 | 0.10604 | 0 | 28800 |  |  | 28800 | 0 | 3053.9068 | 0 | 0 | 3053.9068 | 0 | 43200 |  |  | 43200 | 0 | 4580.8602 | 0 | 0 | 4580.8602 | 0 | 0 | [17 empty] | 0 |  | 0 | 0 | 0 | [17 empty] | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [16 empty] | 0 |  | 0 | 0 | 0 | [17 empty] | 0 | 0
| 72 | 0.10295 | 0 | 1301900 |  |  | 1301900 | 0 | 134030.5179 | 0 | 0 | 134030.5179 | 0 | 1207840 |  |  | 1207840 | 0 | 124347.0472 | 0 | 0 | 124347.0472 | 0 | 919280 | [17 empty] | 239012.8 |  | 1158292.8 | 0 | 94639.8145 | [17 empty] | 24606.3518 | 119246.1662 | 0 | 875260 |  |  | 875260 | 0 | 90107.9584 | 0 | 0 | 90107.9584 | 0 | 1004320 |  |  | 1004320 | 0 | 103394.6768 | 0 | 0 | 103394.6768 | 0 | 201530 | [16 empty] | 60459 |  | 261989 | 0 | 20747.5 | [17 empty] | 6224.25 | 26971.75
| 73 | 0.099951 | 0 | 28800 |  |  | 28800 | 0 | 2878.6001 | 0 | 0 | 2878.6001 | 0 | 43200 |  |  | 43200 | 0 | 4317.9001 | 0 | 0 | 4317.9001 | 0 | 0 | [17 empty] | 0 |  | 0 | 0 | 0 | [17 empty] | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [16 empty] | 0 |  | 0 | 0 | 0 | [17 empty] | 0 | 0
| 74 | 0.09704 | 0 | 28800 |  |  | 28800 | 0 | 2794.7573 | 0 | 0 | 2794.7573 | 0 | 43200 |  |  | 43200 | 0 | 4192.136 | 0 | 0 | 4192.136 | 0 | 0 | [17 empty] | 0 |  | 0 | 0 | 0 | [17 empty] | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [16 empty] | 0 |  | 0 | 0 | 0 | [17 empty] | 0 | 0
| 75 | 0.094214 | 0 | 28800 |  |  | 28800 | 0 | 2713.3567 | 0 | 0 | 2713.3567 | 0 | 43200 |  |  | 43200 | 0 | 4070.035 | 0 | 0 | 4070.035 | 0 | 0 | [17 empty] | 0 |  | 0 | 0 | 0 | [17 empty] | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [16 empty] | 0 |  | 0 | 0 | 0 | [17 empty] | 0 | 0
| 76 | 0.091916 | 0 | 28800 |  |  | 28800 | 0 | 2647.1772 | 0 | 0 | 2647.1772 | 0 | 43200 |  |  | 43200 | 0 | 3970.7658 | 0 | 0 | 3970.7658 | 0 | 0 | [17 empty] | 0 |  | 0 | 0 | 0 | [17 empty] | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [16 empty] | 0 |  | 0 | 0 | 0 | [17 empty] | 0 | 0
| 77 | 0.089674 | 0 | 28800 |  |  | 28800 | 0 | 2582.6119 | 0 | 0 | 2582.6119 | 0 | 43200 |  |  | 43200 | 0 | 3873.9179 | 0 | 0 | 3873.9179 | 0 | 86400 | [17 empty] | 22464 |  | 108864 | 0 | 7747.8358 | [17 empty] | 2014.4373 | 9762.2731 | 0 | 100800 |  |  | 100800 | 0 | 9039.1417 | 0 | 0 | 9039.1417 | 0 | 57600 |  |  | 57600 | 0 | 5165.2238 | 0 | 0 | 5165.2238 | 0 | 86400 | [16 empty] | 25920 |  | 112320 | 0 | 7747.8358 | [17 empty] | 2324.3507 | 10072.1865
| 78 | 0.087487 | 0 | 28800 |  |  | 28800 | 0 | 2519.6214 | 0 | 0 | 2519.6214 | 0 | 43200 |  |  | 43200 | 0 | 3779.4321 | 0 | 0 | 3779.4321 | 0 | 0 | [17 empty] | 0 |  | 0 | 0 | 0 | [17 empty] | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [16 empty] | 0 |  | 0 | 0 | 0 | [17 empty] | 0 | 0
| 79 | 0.085353 | 0 | 28800 |  |  | 28800 | 0 | 2458.1672 | 0 | 0 | 2458.1672 | 0 | 43200 |  |  | 43200 | 0 | 3687.2508 | 0 | 0 | 3687.2508 | 0 | 0 | [17 empty] | 0 |  | 0 | 0 | 0 | [17 empty] | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [16 empty] | 0 |  | 0 | 0 | 0 | [17 empty] | 0 | 0
| 80 | 0.083271 | 0 | 28800 |  |  | 28800 | 0 | 2398.2119 | 0 | 0 | 2398.2119 | 0 | 43200 |  |  | 43200 | 0 | 3597.3179 | 0 | 0 | 3597.3179 | 0 | 0 | [17 empty] | 0 |  | 0 | 0 | 0 | [17 empty] | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [16 empty] | 0 |  | 0 | 0 | 0 | [17 empty] | 0 | 0
| 81 | 0.08124 | 0 | 28800 |  |  | 28800 | 0 | 2339.7189 | 0 | 0 | 2339.7189 | 0 | 43200 |  |  | 43200 | 0 | 3509.5784 | 0 | 0 | 3509.5784 | 0 | 0 | [17 empty] | 0 |  | 0 | 0 | 0 | [17 empty] | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [16 empty] | 0 |  | 0 | 0 | 0 | [17 empty] | 0 | 0
| 82 | 0.079259 | 0 | 1301900 |  |  | 1301900 | 0 | 103186.9947 | 0 | 0 | 103186.9947 | 0 | 1207840 |  |  | 1207840 | 0 | 95731.9146 | 0 | 0 | 95731.9146 | 0 | 919280 | [17 empty] | 239012.8 |  | 1158292.8 | 0 | 72861.0035 | [17 empty] | 18943.8609 | 91804.8644 | 0 | 875260 |  |  | 875260 | 0 | 69372.0324 | 0 | 0 | 69372.0324 | 0 | 1004320 |  |  | 1004320 | 0 | 79601.1694 | 0 | 0 | 79601.1694 | 0 | 201530 | [16 empty] | 60459 |  | 261989 | 0 | 15973.0202 | [17 empty] | 4791.9061 | 20764.9263
| 83 | 0.077326 | 0 | 28800 |  |  | 28800 | 0 | 2226.9782 | 0 | 0 | 2226.9782 | 0 | 43200 |  |  | 43200 | 0 | 3340.4672 | 0 | 0 | 3340.4672 | 0 | 0 | [17 empty] | 0 |  | 0 | 0 | 0 | [17 empty] | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [16 empty] | 0 |  | 0 | 0 | 0 | [17 empty] | 0 | 0
| 84 | 0.07544 | 0 | 28800 |  |  | 28800 | 0 | 2172.6616 | 0 | 0 | 2172.6616 | 0 | 43200 |  |  | 43200 | 0 | 3258.9924 | 0 | 0 | 3258.9924 | 0 | 0 | [17 empty] | 0 |  | 0 | 0 | 0 | [17 empty] | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [16 empty] | 0 |  | 0 | 0 | 0 | [17 empty] | 0 | 0
| 85 | 0.0736 | 0 | 28800 |  |  | 28800 | 0 | 2119.6699 | 0 | 0 | 2119.6699 | 0 | 43200 |  |  | 43200 | 0 | 3179.5048 | 0 | 0 | 3179.5048 | 0 | 0 | [17 empty] | 0 |  | 0 | 0 | 0 | [17 empty] | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [16 empty] | 0 |  | 0 | 0 | 0 | [17 empty] | 0 | 0
| 86 | 0.071805 | 0 | 28800 |  |  | 28800 | 0 | 2067.9706 | 0 | 0 | 2067.9706 | 0 | 43200 |  |  | 43200 | 0 | 3101.9559 | 0 | 0 | 3101.9559 | 0 | 0 | [17 empty] | 0 |  | 0 | 0 | 0 | [17 empty] | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [16 empty] | 0 |  | 0 | 0 | 0 | [17 empty] | 0 | 0
| 87 | 0.070053 | 0 | 28800 |  |  | 28800 | 0 | 2017.5323 | 0 | 0 | 2017.5323 | 0 | 43200 |  |  | 43200 | 0 | 3026.2985 | 0 | 0 | 3026.2985 | 0 | 86400 | [17 empty] | 22464 |  | 108864 | 0 | 6052.5969 | [17 empty] | 1573.6752 | 7626.2721 | 0 | 100800 |  |  | 100800 | 0 | 7061.3631 | 0 | 0 | 7061.3631 | 0 | 57600 |  |  | 57600 | 0 | 4035.0646 | 0 | 0 | 4035.0646 | 0 | 86400 | [16 empty] | 25920 |  | 112320 | 0 | 6052.5969 | [17 empty] | 1815.7791 | 7868.376
| 88 | 0.068345 | 0 | 28800 |  |  | 28800 | 0 | 1968.3242 | 0 | 0 | 1968.3242 | 0 | 43200 |  |  | 43200 | 0 | 2952.4863 | 0 | 0 | 2952.4863 | 0 | 0 | [17 empty] | 0 |  | 0 | 0 | 0 | [17 empty] | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [16 empty] | 0 |  | 0 | 0 | 0 | [17 empty] | 0 | 0
| 89 | 0.066678 | 0 | 28800 |  |  | 28800 | 0 | 1920.3163 | 0 | 0 | 1920.3163 | 0 | 43200 |  |  | 43200 | 0 | 2880.4744 | 0 | 0 | 2880.4744 | 0 | 0 | [17 empty] | 0 |  | 0 | 0 | 0 | [17 empty] | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [16 empty] | 0 |  | 0 | 0 | 0 | [17 empty] | 0 | 0
| 90 | 0.065051 | 0 | 28800 |  |  | 28800 | 0 | 1873.4793 | 0 | 0 | 1873.4793 | 0 | 43200 |  |  | 43200 | 0 | 2810.219 | 0 | 0 | 2810.219 | 0 | 0 | [17 empty] | 0 |  | 0 | 0 | 0 | [17 empty] | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [16 empty] | 0 |  | 0 | 0 | 0 | [17 empty] | 0 | 0
| 91 | 0.063465 | 0 | 28800 |  |  | 28800 | 0 | 1827.7847 | 0 | 0 | 1827.7847 | 0 | 43200 |  |  | 43200 | 0 | 2741.677 | 0 | 0 | 2741.677 | 0 | 0 | [17 empty] | 0 |  | 0 | 0 | 0 | [17 empty] | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [16 empty] | 0 |  | 0 | 0 | 0 | [17 empty] | 0 | 0
| 92 | 0.061917 | 0 | 1401900 |  |  | 1401900 | 0 | 86801.1979 | 0 | 0 | 86801.1979 | 0 | 1307840 |  |  | 1307840 | 0 | 80977.3013 | 0 | 0 | 80977.3013 | 0 | 1019280 | [17 empty] | 265012.8 |  | 1284292.8 | 0 | 63110.582 | [17 empty] | 16408.7513 | 79519.3334 | 0 | 975260 |  |  | 975260 | 0 | 60385.0034 | 0 | 0 | 60385.0034 | 0 | 1104320 |  |  | 1104320 | 0 | 68375.9889 | 0 | 0 | 68375.9889 | 0 | 301530 | [16 empty] | 90459 |  | 391989 | 0 | 18669.7804 | [17 empty] | 5600.9341 | 24270.7146
| 93 | 0.060407 | 0 | 28800 |  |  | 28800 | 0 | 1739.7118 | 0 | 0 | 1739.7118 | 0 | 43200 |  |  | 43200 | 0 | 2609.5677 | 0 | 0 | 2609.5677 | 0 | 0 | [17 empty] | 0 |  | 0 | 0 | 0 | [17 empty] | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [16 empty] | 0 |  | 0 | 0 | 0 | [17 empty] | 0 | 0
| 94 | 0.058933 | 0 | 28800 |  |  | 28800 | 0 | 1697.2798 | 0 | 0 | 1697.2798 | 0 | 43200 |  |  | 43200 | 0 | 2545.9197 | 0 | 0 | 2545.9197 | 0 | 0 | [17 empty] | 0 |  | 0 | 0 | 0 | [17 empty] | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [16 empty] | 0 |  | 0 | 0 | 0 | [17 empty] | 0 | 0
| 95 | 0.057496 | 0 | 28800 |  |  | 28800 | 0 | 1655.8827 | 0 | 0 | 1655.8827 | 0 | 43200 |  |  | 43200 | 0 | 2483.8241 | 0 | 0 | 2483.8241 | 0 | 0 | [17 empty] | 0 |  | 0 | 0 | 0 | [17 empty] | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [16 empty] | 0 |  | 0 | 0 | 0 | [17 empty] | 0 | 0
| 96 | 0.056094 | 0 | 28800 |  |  | 28800 | 0 | 1615.4953 | 0 | 0 | 1615.4953 | 0 | 43200 |  |  | 43200 | 0 | 2423.243 | 0 | 0 | 2423.243 | 0 | 0 | [17 empty] | 0 |  | 0 | 0 | 0 | [17 empty] | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [16 empty] | 0 |  | 0 | 0 | 0 | [17 empty] | 0 | 0
| 97 | 0.054725 | 0 | 28800 |  |  | 28800 | 0 | 1576.093 | 0 | 0 | 1576.093 | 0 | 43200 |  |  | 43200 | 0 | 2364.1395 | 0 | 0 | 2364.1395 | 0 | 86400 | [17 empty] | 22464 |  | 108864 | 0 | 4728.279 | [17 empty] | 1229.3525 | 5957.6316 | 0 | 100800 |  |  | 100800 | 0 | 5516.3255 | 0 | 0 | 5516.3255 | 0 | 57600 |  |  | 57600 | 0 | 3152.186 | 0 | 0 | 3152.186 | 0 | 86400 | [16 empty] | 25920 |  | 112320 | 0 | 4728.279 | [17 empty] | 1418.4837 | 6146.7627
| 98 | 0.053391 | 0 | 28800 |  |  | 28800 | 0 | 1537.6517 | 0 | 0 | 1537.6517 | 0 | 43200 |  |  | 43200 | 0 | 2306.4776 | 0 | 0 | 2306.4776 | 0 | 0 | [17 empty] | 0 |  | 0 | 0 | 0 | [17 empty] | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [16 empty] | 0 |  | 0 | 0 | 0 | [17 empty] | 0 | 0
| 99 | 0.052088 | 0 | 28800 |  |  | 28800 | 0 | 1500.148 | 0 | 0 | 1500.148 | 0 | 43200 |  |  | 43200 | 0 | 2250.222 | 0 | 0 | 2250.222 | 0 | 0 | [17 empty] | 0 |  | 0 | 0 | 0 | [17 empty] | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [16 empty] | 0 |  | 0 | 0 | 0 | [17 empty] | 0 | 0
Note on B26: Tom Green:

## Preferred OBC PV
Client/Authority
East Devon District Council
Project name
Sidmouth Beach Management Plan
| Project reference |  |  | 2018-01-01 | [30 empty] | 35419.7714
| Base date for estimates (year 0) |  |  | £
| Scaling factor (e.g. £m, £k, £) |  |  | 3.5%
Initial discount rate
|  |  | Option 4: | One Offshore Breakwater | [18 empty] | TOTALS: | PV | PV | [17 empty] | PV | PV
[19 empty] | Maintain Front. A | 0
[19 empty] | Maintain Flood Gates Fron. B | 10 |  | 28000
[19 empty] | Replacement to demountable defences | 50 |  | 27000
[19 empty] | Maintenance to demountable defences | 10 |  | 1000
[19 empty] | Training for demountable defences | 1 |  | 600
[19 empty] | Recharge Fron. B | 10 |  | 86130
[19 empty] | Recycle Fron. B | 5 |  | 86400
[19 empty] | Recharge Fron. C | 100 |  | 0
[19 empty] | Repiar River Wall Fron. D | 30 |  | 100000
[19 empty] | Year of construction: | 3
|  |  | Construction Costs | Maint. | Existing staff costs | Further staff costs | Site investigation and survey | Consultants’ fees | Contractors’ fees | Cost consultants’ fees | Inflation allowance | Environmental enhancement | Environmental mitigation | Existing staff costs | Further staff costs | Consultants’ fees | Site supervision | Cost consultants’ fees | Land purchase & compensation | Risk - Monte Carlo 95% | Risk - OB Future Costs | Negative costs | Cash | Capital | Maint | Existing staff costs | Further staff costs | Site investigation and survey | Consultants’ fees | Contractors’ fees | Cost consultants’ fees | Construction costs | Inflation allowance for months | Environmental enhancement | Environmental mitigation | Existing staff costs | Further staff costs | Consultants’ fees | Site supervision | Cost consultants’ fees | Land purchase & compensation | Risk - Monte Carlo 95% - Capital | Risk - Monte Carlo 50% - Maintenance | Total PV cost |  | Contributions
|  | cash sum | 12108570.2142 | 3062370 | 0 | 50000 | 375000 | 395000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 267375 | 0 | 45000 | 5125587.4534 | 918711 | 0 | 22347613.6676 | 10921236.5807 | 747747.2867 | 0 | 47520.4623 | 362318.8406 | 379061.355 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 241156.9309 | 0 | 40587.4218 | 4642073.2684 | 224324.186 | 17606026.3323 | 20303456.6713
|  | Discount | [20 empty] | 20781491.3266
| year | Factor
2023/24 | 0 | 1 | 0 | 0 |  | 12500 | [13 empty] | 4838.7666 | 0 |  | 17338.7666 | 0 | 0 | 0 | 12500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4838.7666 | 0 | 17338.7666
2024/25 | 1 | 0.96618 | 0 | 0 |  | 12500 | 375000 | 316000 | 0 | 0 | [9 empty] | 272325.783 | 0 |  | 975825.783 | 0 | 0 | 0 | 12077.2947 | 362318.8406 | 305314.0097 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 263116.6986 | 0 | 942826.8435
2025/26 | 2 | 0.93351 | 0 | 0 |  | 12500 |  | 79000 |  |  |  | 0 | 0 | 0 | 0 |  |  |  |  | 35419.7714 | 0 |  | 126919.7714 | 0 | 0 | 0 | 11668.8838 | 0 | 73747.3453 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33064.7356 | 0 | 118480.9646
2026/27 | 3 | 0.90194 | 12108570.2142 | 0 |  | 12500 | [10 empty] | 267375 |  | 45000 | 4813003.1325 | 0 |  | 17246448.3466 | 10921236.5807 | 0 | 0 | 11274.2838 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 241156.9309 | 0 | 40587.4218 | 4341053.0677 | 0 | 15555308.2849
| 4 | 0.87144 | 0 | 600 | [16 empty] | 180 |  | 780 | 0 | 522.8653 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 156.8596 | 679.7249
| 5 | 0.84197 | 0 | 600 | [16 empty] | 180 |  | 780 | 0 | 505.1839 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 151.5552 | 656.7391
| 6 | 0.8135 | 0 | 600 | [16 empty] | 180 |  | 780 | 0 | 488.1004 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 146.4301 | 634.5305
| 7 | 0.78599 | 0 | 600 | [16 empty] | 180 |  | 780 | 0 | 471.5946 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 141.4784 | 613.0729
| 8 | 0.75941 | 0 | 87000 | [16 empty] | 26100 |  | 113100 | 0 | 66068.8054 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19820.6416 | 85889.447
| 9 | 0.73373 | 0 | 600 | [16 empty] | 180 |  | 780 | 0 | 440.2386 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 132.0716 | 572.3102
| 10 | 0.70892 | 0 | 600 | [16 empty] | 180 |  | 780 | 0 | 425.3513 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 127.6054 | 552.9567
| 11 | 0.68495 | 0 | 600 | [16 empty] | 180 |  | 780 | 0 | 410.9674 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 123.2902 | 534.2577
| 12 | 0.66178 | 0 | 600 | [16 empty] | 180 |  | 780 | 0 | 397.07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 119.121 | 516.191
| 13 | 0.6394 | 0 | 202130 | [16 empty] | 60639 |  | 262769 | 0 | 129242.7614 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38772.8284 | 168015.5899
| 14 | 0.61778 | 0 | 600 | [16 empty] | 180 |  | 780 | 0 | 370.6691 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 111.2007 | 481.8698
| 15 | 0.59689 | 0 | 600 | [16 empty] | 180 |  | 780 | 0 | 358.1344 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 107.4403 | 465.5747
| 16 | 0.57671 | 0 | 600 | [16 empty] | 180 |  | 780 | 0 | 346.0235 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 103.8071 | 449.8306
| 17 | 0.5572 | 0 | 600 | [16 empty] | 180 |  | 780 | 0 | 334.3223 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100.2967 | 434.6189
| 18 | 0.53836 | 0 | 87000 | [16 empty] | 26100 |  | 113100 | 0 | 46837.4191 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14051.2257 | 60888.6449
| 19 | 0.52016 | 0 | 600 | [16 empty] | 180 |  | 780 | 0 | 312.0934 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 93.628 | 405.7214
| 20 | 0.50257 | 0 | 600 | [16 empty] | 180 |  | 780 | 0 | 301.5395 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 90.4619 | 392.0014
| 21 | 0.48557 | 0 | 600 | [16 empty] | 180 |  | 780 | 0 | 291.3425 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 87.4028 | 378.7453
| 22 | 0.46915 | 0 | 600 | [16 empty] | 180 |  | 780 | 0 | 281.4904 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 84.4471 | 365.9375
| 23 | 0.45329 | 0 | 202130 | [16 empty] | 60639 |  | 262769 | 0 | 91622.6251 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27486.7875 | 119109.4127
| 24 | 0.43796 | 0 | 600 | [16 empty] | 180 |  | 780 | 0 | 262.7743 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 78.8323 | 341.6066
| 25 | 0.42315 | 0 | 600 | [16 empty] | 180 |  | 780 | 0 | 253.8882 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 76.1665 | 330.0547
| 26 | 0.40884 | 0 | 600 | [16 empty] | 180 |  | 780 | 0 | 245.3026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 73.5908 | 318.8934
| 27 | 0.39501 | 0 | 600 | [16 empty] | 180 |  | 780 | 0 | 237.0073 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 71.1022 | 308.1095
| 28 | 0.38165 | 0 | 87000 | [16 empty] | 26100 |  | 113100 | 0 | 33203.9276 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9961.1783 | 43165.1059
| 29 | 0.36875 | 0 | 600 | [16 empty] | 180 |  | 780 | 0 | 221.2489 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 66.3747 | 287.6236
| 30 | 0.35628 | 0 | 600 | [16 empty] | 180 |  | 780 | 0 | 213.767 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 64.1301 | 277.8972
| 31 | 0.3459 | 0 | 600 | [16 empty] | 180 |  | 780 | 0 | 207.5408 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 62.2622 | 269.8031
| 32 | 0.33583 | 0 | 600 | [16 empty] | 180 |  | 780 | 0 | 201.4959 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60.4488 | 261.9447
| 33 | 0.32605 | 0 | 302130 | [16 empty] | 90639 |  | 392769 | 0 | 98508.0411 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29552.4123 | 128060.4534
| 34 | 0.31655 | 0 | 600 | [16 empty] | 180 |  | 780 | 0 | 189.9293 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 56.9788 | 246.908
| 35 | 0.30733 | 0 | 600 | [16 empty] | 180 |  | 780 | 0 | 184.3973 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55.3192 | 239.7165
| 36 | 0.29838 | 0 | 600 | [16 empty] | 180 |  | 780 | 0 | 179.0265 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53.708 | 232.7345
| 37 | 0.28969 | 0 | 600 | [16 empty] | 180 |  | 780 | 0 | 173.8122 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52.1437 | 225.9558
| 38 | 0.28125 | 0 | 87000 | [16 empty] | 26100 |  | 113100 | 0 | 24468.7037 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7340.6111 | 31809.3148
| 39 | 0.27306 | 0 | 600 | [16 empty] | 180 |  | 780 | 0 | 163.8346 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49.1504 | 212.985
| 40 | 0.2651 | 0 | 600 | [16 empty] | 180 |  | 780 | 0 | 159.0628 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 47.7188 | 206.7816
| 41 | 0.25738 | 0 | 600 | [16 empty] | 180 |  | 780 | 0 | 154.4299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46.329 | 200.7588
| 42 | 0.24989 | 0 | 600 | [16 empty] | 180 |  | 780 | 0 | 149.9319 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44.9796 | 194.9115
| 43 | 0.24261 | 0 | 202130 | [16 empty] | 60639 |  | 262769 | 0 | 49038.4078 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14711.5223 | 63749.9302
| 44 | 0.23554 | 0 | 600 | [16 empty] | 180 |  | 780 | 0 | 141.3252 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42.3976 | 183.7228
| 45 | 0.22868 | 0 | 600 | [16 empty] | 180 |  | 780 | 0 | 137.2089 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41.1627 | 178.3716
| 46 | 0.22202 | 0 | 600 | [16 empty] | 180 |  | 780 | 0 | 133.2126 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39.9638 | 173.1763
| 47 | 0.21555 | 0 | 600 | [16 empty] | 180 |  | 780 | 0 | 129.3326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38.7998 | 168.1324
| 48 | 0.20928 | 0 | 87000 | [16 empty] | 26100 |  | 113100 | 0 | 18207.0135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5462.104 | 23669.1175
| 49 | 0.20318 | 0 | 600 | [16 empty] | 180 |  | 780 | 0 | 121.9084 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36.5725 | 158.4809
| 50 | 0.19726 | 0 | 600 | [16 empty] | 180 |  | 780 | 0 | 118.3576 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35.5073 | 153.8649
| 51 | 0.19152 | 0 | 600 | [16 empty] | 180 |  | 780 | 0 | 114.9103 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34.4731 | 149.3834
| 52 | 0.18594 | 0 | 600 | [16 empty] | 180 |  | 780 | 0 | 111.5634 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33.469 | 145.0324
| 53 | 0.18052 | 0 | 229130 | [16 empty] | 68739 |  | 297869 | 0 | 41363.3108 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12408.9932 | 53772.304
| 54 | 0.17527 | 0 | 600 | [16 empty] | 180 |  | 780 | 0 | 105.1592 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31.5478 | 136.707
| 55 | 0.17016 | 0 | 600 | [16 empty] | 180 |  | 780 | 0 | 102.0963 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30.6289 | 132.7252
| 56 | 0.1652 | 0 | 600 | [16 empty] | 180 |  | 780 | 0 | 99.1227 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29.7368 | 128.8594
| 57 | 0.16039 | 0 | 600 | [16 empty] | 180 |  | 780 | 0 | 96.2356 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28.8707 | 125.1063
| 58 | 0.15572 | 0 | 87000 | [16 empty] | 26100 |  | 113100 | 0 | 13547.728 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4064.3184 | 17612.0463
| 59 | 0.15119 | 0 | 600 | [16 empty] | 180 |  | 780 | 0 | 90.7113 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27.2134 | 117.9246
| 60 | 0.14678 | 0 | 600 | [16 empty] | 180 |  | 780 | 0 | 88.0692 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26.4208 | 114.49
| 61 | 0.14251 | 0 | 600 | [16 empty] | 180 |  | 780 | 0 | 85.5041 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25.6512 | 111.1553
| 62 | 0.13836 | 0 | 600 | [16 empty] | 180 |  | 780 | 0 | 83.0137 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24.9041 | 107.9178
| 63 | 0.13433 | 0 | 302130 | [16 empty] | 90639 |  | 392769 | 0 | 40584.0086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12175.2026 | 52759.2112
| 64 | 0.13041 | 0 | 600 | [16 empty] | 180 |  | 780 | 0 | 78.2483 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23.4745 | 101.7228
| 65 | 0.12662 | 0 | 600 | [16 empty] | 180 |  | 780 | 0 | 75.9693 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22.7908 | 98.76
| 66 | 0.12293 | 0 | 600 | [16 empty] | 180 |  | 780 | 0 | 73.7566 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22.127 | 95.8835
| 67 | 0.11935 | 0 | 600 | [16 empty] | 180 |  | 780 | 0 | 71.6083 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21.4825 | 93.0908
| 68 | 0.11587 | 0 | 87000 | [16 empty] | 26100 |  | 113100 | 0 | 10080.7819 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3024.2346 | 13105.0165
| 69 | 0.1125 | 0 | 600 | [16 empty] | 180 |  | 780 | 0 | 67.4977 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20.2493 | 87.747
| 70 | 0.10922 | 0 | 600 | [16 empty] | 180 |  | 780 | 0 | 65.5318 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19.6595 | 85.1913
| 71 | 0.10604 | 0 | 600 | [16 empty] | 180 |  | 780 | 0 | 63.6231 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19.0869 | 82.71
| 72 | 0.10295 | 0 | 600 | [16 empty] | 180 |  | 780 | 0 | 61.77 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18.531 | 80.3009
| 73 | 0.099951 | 0 | 202130 | [16 empty] | 60639 |  | 262769 | 0 | 20203.1747 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6060.9524 | 26264.1271
| 74 | 0.09704 | 0 | 600 | [16 empty] | 180 |  | 780 | 0 | 58.2241 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17.4672 | 75.6913
| 75 | 0.094214 | 0 | 600 | [16 empty] | 180 |  | 780 | 0 | 56.5283 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16.9585 | 73.4867
| 76 | 0.091916 | 0 | 600 | [16 empty] | 180 |  | 780 | 0 | 55.1495 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16.5449 | 71.6944
| 77 | 0.089674 | 0 | 600 | [16 empty] | 180 |  | 780 | 0 | 53.8044 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16.1413 | 69.9457
| 78 | 0.087487 | 0 | 87000 | [16 empty] | 26100 |  | 113100 | 0 | 7611.3563 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2283.4069 | 9894.7632
| 79 | 0.085353 | 0 | 600 | [16 empty] | 180 |  | 780 | 0 | 51.2118 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15.3635 | 66.5754
| 80 | 0.083271 | 0 | 600 | [16 empty] | 180 |  | 780 | 0 | 49.9627 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14.9888 | 64.9516
| 81 | 0.08124 | 0 | 600 | [16 empty] | 180 |  | 780 | 0 | 48.7441 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14.6232 | 63.3674
| 82 | 0.079259 | 0 | 600 | [16 empty] | 180 |  | 780 | 0 | 47.5553 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14.2666 | 61.8218
| 83 | 0.077326 | 0 | 202130 | [16 empty] | 60639 |  | 262769 | 0 | 15629.8297 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4688.9489 | 20318.7787
| 84 | 0.07544 | 0 | 600 | [16 empty] | 180 |  | 780 | 0 | 45.2638 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13.5791 | 58.8429
| 85 | 0.0736 | 0 | 600 | [16 empty] | 180 |  | 780 | 0 | 44.1598 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13.2479 | 57.4077
| 86 | 0.071805 | 0 | 600 | [16 empty] | 180 |  | 780 | 0 | 43.0827 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12.9248 | 56.0075
| 87 | 0.070053 | 0 | 600 | [16 empty] | 180 |  | 780 | 0 | 42.0319 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12.6096 | 54.6415
| 88 | 0.068345 | 0 | 87000 | [16 empty] | 26100 |  | 113100 | 0 | 5945.9794 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1783.7938 | 7729.7732
| 89 | 0.066678 | 0 | 600 | [16 empty] | 180 |  | 780 | 0 | 40.0066 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12.002 | 52.0086
| 90 | 0.065051 | 0 | 600 | [16 empty] | 180 |  | 780 | 0 | 39.0308 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11.7092 | 50.7401
| 91 | 0.063465 | 0 | 600 | [16 empty] | 180 |  | 780 | 0 | 38.0788 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11.4237 | 49.5025
| 92 | 0.061917 | 0 | 600 | [16 empty] | 180 |  | 780 | 0 | 37.1501 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11.145 | 48.2951
| 93 | 0.060407 | 0 | 302130 | [16 empty] | 90639 |  | 392769 | 0 | 18250.6639 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5475.1992 | 23725.8631
| 94 | 0.058933 | 0 | 600 | [16 empty] | 180 |  | 780 | 0 | 35.36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10.608 | 45.968
| 95 | 0.057496 | 0 | 600 | [16 empty] | 180 |  | 780 | 0 | 34.4976 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10.3493 | 44.8468
| 96 | 0.056094 | 0 | 600 | [16 empty] | 180 |  | 780 | 0 | 33.6562 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10.0968 | 43.753
| 97 | 0.054725 | 0 | 600 | [16 empty] | 180 |  | 780 | 0 | 32.8353 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9.8506 | 42.6859
| 98 | 0.053391 | 0 | 87000 | [16 empty] | 26100 |  | 113100 | 0 | 4644.9896 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1393.4969 | 6038.4864
| 99 | 0.052088 | 0 | 600 | [16 empty] | 180 |  | 780 | 0 | 31.2531 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9.3759 | 40.629
Note on B27: Tom Green:

## Contributions
Sector | Source of Funding | Total Cash Value | Year of Contribution | Year of Contribution | Year of Contribution | Year of Contribution | PV Value
|  |  | 2023/24 | 2024/25 | 2025/26 | 2026/27
|  |  | 1 | 0.96618 | 0.93351 | 0.90194
Local Levy | Local Levy | 500000 |  |  |  | 500000 | 450971.3528 |  | Local Levy | 450971.3528
Public Sector | Contributions 1 - East Devon District Council Risk Budget Contribution | 1700000 |  |  |  | 1700000 | 1533302.5996 |  | Public Sector | 2603165.9332
Public Sector | Contributions 2 – East Devon District Council Up front contribution | 499917 | 17417 | 482500 |  |  | 483600.5749 |  | Private & Voluntary | 135291.4059
Public Sector | Contributions 3 – Devon County Council | 500000 |  |  |  | 500000 | 450971.3528 |  | Total | 3189428.6919
Public Sector | Contributions 4 – Sidmouth Town Council (1) | 100000 |  |  |  | 100000 | 90194.2706
Private & Voluntary | Contributions 5 – Sidmouth Life Boat (2) | 100000 |  |  |  | 100000 | 90194.2706
Private & Voluntary | Contributions 6 – Cliff Road Action Group (GRAG) (3) | 50000 |  |  |  | 50000 | 45097.1353
Public Sector | Contributions 7 – EDDC Housing | 50000 |  |  |  | 50000 | 45097.1353
| Total funding | 3499917 | 17417 | 482500 | 0 | 3000000 | 3189428.6919
Scheme Cash Costs | Cost less contingency | 15914481.2092 | 12500 | 752745 | 104767.5 | 15044468.7092 | 14406840.2502
| Contingency | 5125587.4534 | 4838.7666 | 272325.783 | 35419.7714 | 4813003.1325 | 4642073.2684
| Total cost | 21040068.6626 | 17338.7666 | 1025070.783 | 140187.2714 | 19857471.8416 | 19048913.5186 | 19331385.5186
FDGiA Available (PV)
| FDGiA Required | 17540151.6626 | -78.2334 | 542570.783 | 140187.2714 | 16857471.8416 | 15859484.8268 |  | 15722341 | -419615.8268
[7 empty] | 282472 |  | 15414059.8039
16141956.8268
|  | 21040068.6626 | 17338.7666 | 1025070.783 | 140187.2714 | 19857471.8416 | 19048913.5186

## Programme
| 2023/24 | [7 empty] | 2024/25 | [11 empty] | 2025/26 | [11 empty] | 2026/27
 | time axis 2023-08-01 to 2027-12-01
Submit OBC to Environment Agency for Assurance | bar: 2023-08-01
OBC approved | bar: 2023-10-01
Tender Consultant for Detailed design phase | bar: 2023-11-01 to 2024-02-01
Appoint Consultant | bar: 2024-03-01
Commence Detailed Design Stage | bar: 2024-04-01 to 2025-03-01
Planning & consents Process | bar: 2025-02-01 to 2025-07-01
Tender Contractor | bar: 2025-08-01 to 2025-11-01
Award Contractor | bar: 2025-12-01
Mobilisation | bar: 2026-01-01 to 2026-02-01
Construction Commence | bar: 2026-03-01 to 2027-02-01
Construction Complete | bar: 2027-03-01
Ready for service. | bar: 2027-03-01

## Construction costing wall
Slab and Ramp
Ramp v2 costing
Formwork
|  | Side | Contact Area (m²) | Rate (£/m²) | Cost | Subtotal
|  | west | 62.4 | 200 | 12480 | 25840
|  | east | 57.2 | 200 | 11440
|  | South | 9.6 | 200 | 1920
Concrete mass
| Area (m²) | Width (m) | Volume (m³) | Rate (£/m²) | Cost | Subtotal
| 62.4 | 4 | 249.6 | 320 | 79872 | 79872
Slab costing
Formwork
|  | Side | Contact Area (m²) | Rate (£/m²) | Cost | Subtotal
|  | west | 6 | 200 | 1200 | 3420
|  | north-east | 7.5 | 200 | 1500
|  | South | 3.6 | 200 | 720
Concrete mass
| Area (m²) | Length (m) | Volume (m³) | Rate (£/m²) | Cost | Subtotal
| 3.6 | 22 | 79.2 | 320 | 25344 | 25344
Slab Reinforcment Steel
Assumed Φ16/150mm top and bottom
Weight per meter of 16DIA bars=1.58kg/m)
Total weight of reinfrocement = Number * length * weight per meter
Direction | Number of bars needed | Length (m) | Total Weight (tonnes) | Rate (£/tonnes) | Cost | Subtotal
x | 160 | 20 | 5.056 | 130 | 657.28 | 1380.288
y | 293.3333 | 12 | 5.5616 | 130 | 723.008
Excavations
| Rate given for excavations is equal to 2000£/day |  |  | Giving a rate of 40£/cu.m.for excavations
We assume that 50cu.m. are excavated per day
We assume that volume excavated will be reused for the filling under the slab
| Area (m²) | Width (m) | Volume (m³) | Rate (£/m^3) | Cost | Subtotal
| 62.4 | 2.3 | 143.52 | 40 | 5740.8 | 19468.8
| 62.4 | 4 | 249.6 | 40 | 9984
| 62.4 | 1.5 | 93.6 | 40 | 3744
Joints and sealant
Subtotal
10000
Ramp to key into rock (Breaking out bedrock)
Subtotal
10000
Total cost for Ramp and Slab |  |  | 175325.088
Training Arm Encasement
Encasement
Formwork
|  | Side | Area (m²) | Rate (£/m²) | Cost | Subtotal
|  | west and east | 250 | 200 | 50000 | 52000
|  | End bit | 10 | 200 | 2000
Concrete mass
| Area (m²) | Thickness (m) | Volume (m³) | Rate (£/m²) | Cost | Subtotal
| 346 | 0.3 | 103.8 | 320 | 33216 | 33216
Excavations
| Rate given for excavations is equal to 2000£/day |  |  | Giving a rate of 40£/cu.m.for excavations
We assume that 50cu.m. are excavated per day
| Area (m²) | Length (m) | Volume (m³) | Rate (£/m^3) | Cost | Subtotal
west | 2 | 25 | 50 | 40 | 2000 | 4000
east | 2 | 25 | 50 | 40 | 2000
Total cost for Training arm |  |  | 89216
Splash Wall
| Bays I,II,III | [5 empty] | Bays I,II,III
| Assume splash wall in bays I, II and III will be 1m above ground level. | [5 empty] | Assume splash wall in bays I, II and III will be 0.5m above ground level.
| Length=100m+198m+170m | [5 empty] | Length=100m+198m+170m
| Formwork | [5 empty] | Formwork
| Height (m) | Length (m) | Formwork Area (m²) | Rate (£/m²) | Cost | Subtotal | Height (m) | Length (m) | Formwork Area (m²) | Rate (£/m²) | Cost | Subtotal
seaword | 2 | 468 | 936 | 200 | 187200 | 374400 | 1.5 | 468 | 702 | 200 | 140400 | 280800
landword | 2 | 468 | 936 | 200 | 187200 |  | 1.5 | 468 | 702 | 200 | 140400
| Concrete mass | [5 empty] | Concrete mass
| Area (m²) | Length (m) | Volume (m³) | Rate (£/m²) | Cost | Subtotal | Area (m²) | Length (m) | Volume (m³) | Rate (£/m²) | Cost | Subtotal
| 1.05 | 468 | 491.4 | 320 | 157248 | 157248 | 0.9 | 468 | 421.2 | 320 | 134784 | 134784
Seawall section IV
Assume splash wall is 1.3m above ground level in bay IV
Length=140m
Formwork
| Height (m) | Length (m) | Contact Area (m²) | Rate (£/m²) | Cost | Subtotal
seaword | 2.3 | 140 | 322 | 200 | 64400 | 128800
landword | 2.3 | 140 | 322 | 200 | 64400
Concrete mass
| Area (m²) | Length (m) | Volume (m³) | Rate (£/m²) | Cost | Subtotal
| 1.14 | 140 | 159.6 | 320 | 51072 | 51072
| Excavations | [11 empty] | Stone Cladding
| Rate given for excavations is equal to 2000£/day |  |  | Giving a rate of 40£/cu.m.for excavations | [8 empty] | Rate (m²) | Cost
| We assume that 50cu.m. are excavated per day | [11 empty] | 185 | 106375 | full height 250m
| Since the the shape of the existing foundations is unknown 40% of the volume has been assumed to need excavation | [11 empty] | 185 | 53187.5 | half height
| Area (m²) | Length (m) | Volume (m³) | Rate (£/m^3) | Cost | Subtotal
| 0.98 | 600 | 588 | 40 | 23520 | 23520
[13 empty] | 2000 | 608000 | SS by the below - used in PF Calc submitted 20/02/21
Demountable defences
| Rate for demountable defences is £1,000 per 1m run | [11 empty] | Flood Glass
| We estimate that there will be 50m of demountable defences | [11 empty] | Rate (£/m) | Cost
[13 empty] | 2000 | 468000 | assumed town frontage and 0.5m height - no glass on final frontage iV
|  |  | Length (m) | Rate (£/m^3) | Cost | Subtotal | [6 empty] | 1000 | 234000 | assumes 500mm glass
|  |  | 50 | 1000 | 50000 | 50000
Total cost for Splash Wall |  |  | 785040 | 2018 Costs | [7 empty] | Are you able to state how much the half stone clad wall is per linear metre? |  |  | 185 |  | Forward Riv email | with and without RC
New cost Feb 21 |  |  | 1143655 | SS by the below - used in PF Calc submitted 20/02/21 | [7 empty] | Or even better the cost of the glass top section for the whole wall? As we will probably look at a cheaper top section. |  |  |  | 234000
|  |  | 813050.5 | RC plus Clad
|  |  | 234000 | flood glass
|  |  | 50000 | demountable
|  |  | 23520 | Excavation
|  |  | 1120570.5 | New total for PF Calc |  | used in PF Calc submitted 22/02/21
BAY I
BAY II
BAY III
BAY IV
Note on E101: Ayman Elmaghrbi: £100/m2 is formwork rate we got from S. Martin. We doubled that to account for other costs e.g. labours
Note on L101: Ayman Elmaghrbi: £100/m2 is formwork rate we got from S. Martin. We doubled that to account for other costs e.g. labours
Note on E107: Ayman Elmaghrbi: £160/m3 is the rate for concrete we got from S. Martin. It is doubled here to accound for labour and other costs
Note on L107: Ayman Elmaghrbi: £160/m3 is the rate for concrete we got from S. Martin. It is doubled here to accound for labour and other costs

## update wall Feb21
Splash Wall
| Stone wall complete | [5 empty] | 50% stone wall 50% Glass pannels
| Bays I,II,III | [6 empty] | Bays I,II,III
| Assume splash wall in bays I, II and III will be 1m above ground level. | [6 empty] | Assume splash wall in bays I, II and III will be 1m above ground level.
| Length=100m+198m+170m | [6 empty] | Length=100m+198m+170m
| Formwork+Cladding | [6 empty] | Formwork+Cladding | [5 empty] | Glass pannels
| Height (m) | Length (m) | Formwork Area (m²) | Rate (£/m²) | Cost | Subtotal |  | Height (m) | Length (m) | Formwork Area (m²) | Rate (£/m²) | Cost | Subtotal | Rate (£/m) | Cost
seaword | 2 | 468 | 936 | 865 | 809640 | 1619280 | seaword | 2 | 234 | 468 | 865 | 404820 | 1476774 | 2000 | 468000
landword | 2 | 468 | 936 | 865 | 809640 |  | landword | 2 | 234 | 468 | 865 | 404820
[7 empty] | cladding length | 2.3 | 468 |  |  |  |  | Stone Cladding
[14 empty] | Rate (m²) | Cost
[14 empty] | 185 | 199134
| Concrete mass | [6 empty] | Concrete mass
| Area (m²) | Length (m) | Volume (m³) | Rate (£/m²) | Cost | Subtotal | Area for glass foundation | Area (m²) | Length @50% (m) | Volume (m³) | Rate (£/m²) | Cost | Subtotal
| 1.05 | 468 | 491.4 | 320 | 157248 | 157248 | 0.75 | 1.05 | 234 | 421.2 | 320 | 134784 | 134784
| Seawall section IV | [6 empty] | Seawall section IV
| Assume splash wall is 1.3m above ground level in bay IV | [6 empty] | Assume splash wall is 1.3m above ground level in bay IV
| Length=140m | [6 empty] | Length=140m
| Formwork | [6 empty] | Formwork | [5 empty] | Glass pannels
| Height (m) | Length (m) | Contact Area (m²) | Rate (£/m²) | Cost | Subtotal |  | Height (m) | Length (m) | Contact Area (m²) | Rate (£/m²) | Cost | Subtotal | Rate (£/m) | Cost
seaword | 2.3 | 140 | 322 | 865 | 278530 | 557060 | seaword | 2.3 | 70 | 161 | 865 | 139265 | 478100 | 2000 | 140000
landword | 2.3 | 140 | 322 | 865 | 278530 |  | landword | 2.3 | 70 | 161 | 865 | 139265 |  | Stone Cladding
[7 empty] | cladding length | 2.3 | 140 |  |  |  |  | Rate (m²) | Cost
[14 empty] | 185 | 59570
| Concrete mass | [6 empty] | Concrete mass
| Area (m²) | Length (m) | Volume (m³) | Rate (£/m²) | Cost | Subtotal | Area for glass foundation | Area (m²) | Length (m) | Volume (m³) | Rate (£/m²) | Cost | Subtotal
| 1.14 | 140 | 159.6 | 320 | 51072 | 51072 | 0.84 | 1.14 | 70 | 138.6 | 320 | 44352 | 44352
| Excavations | [6 empty] | Excavations
| Rate given for excavations is equal to 2000£/day |  |  | Giving a rate of 40£/cu.m.for excavations |  |  |  | Rate given for excavations is equal to 2000£/day |  |  | Giving a rate of 40£/cu.m.for excavations
| We assume that 50cu.m. are excavated per day | [6 empty] | We assume that 50cu.m. are excavated per day
| Since the the shape of the existing foundations is unknown 40% of the volume has been assumed to need excavation | [6 empty] | Since the the shape of the existing foundations is unknown 40% of the volume has been assumed to need excavation
| Area (m²) | Length (m) | Volume (m³) | Rate (£/m^3) | Cost | Subtotal |  | Area (m²) | Length (m) | Volume (m³) | Rate (£/m^3) | Cost | Subtotal
| 0.98 | 600 | 588 | 40 | 23520 | 23520 |  | 0.98 | 600 | 588 | 40 | 23520 | 23520
| Demountable defences | [6 empty] | Demountable defences
| Rate for demountable defences is £1,000 per 1m run | [6 empty] | Rate for demountable defences is £1,000 per 1m run
| We estimate that there will be 50m of demountable defences | [6 empty] | We estimate that there will be 50m of demountable defences
|  |  | Length (m) | Rate (£/m^3) | Cost | Subtotal |  |  |  | Length (m) | Rate (£/m^3) | Cost | Subtotal
|  |  | 50 | 1000 | 50000 | 50000 |  |  |  | 50 | 1000 | 50000 | 50000
Total cost for Stone Clad Splash Wall |  |  | 2458180 |  |  |  | Total cost for Splash Wall 50% stone 50% glass |  |  | 2207530
|  |  | 1673140 | [6 empty] | 1422490
BAY I
BAY II
BAY III
BAY IV
Note on E18: Ayman Elmaghrbi: £160/m3 is the rate for concrete we got from S. Martin. It is doubled here to accound for labour and other costs
Note on I18: Alice Johnson: -0.3m3 which is thickness of wall stem
Note on M18: Ayman Elmaghrbi: £160/m3 is the rate for concrete we got from S. Martin. It is doubled here to accound for labour and other costs
Note on I31: Alice Johnson: -0.3m3 which is thickness of wall stem

## Re-nourishment-Recycling rates
Short 60-70m similar to town groynes
Long ~ 120m enough to hold a beach similar to Jacobs ladder
Initial nourishment
Town beach | Same (*) = 36,232 m3
East beach | 20000 | 20000 | 26250 | 35000 | 35000 | as 1 long groyne
(*) There may be a small saving by re-using surpless materails from behind breakwaters, not accounted for.
These don’t hold enough beach and therefore can add more but it wont stay for long before bypassing to the east.
External Nourishment
| 1 short | 2 short | 1 long | 2 long | 1 long 1 short | Even longer single groyne
Town beach | Same at least 10 years, as it was initially nourished 1995 ish and gone by 2007. I think this needs a sensitivity check for ever 5 years to see how that affects costs, I would be upset if it is gone in less than 5 years but that may happen in a couple of bad winters. (**)
East beach | Won't technically hold enough material to protect cliff, some will be supplied from the town frontage as that is lost. Nourish every 3-4 years |  | No specific nourishment required for contingency say ever 30 years. | No specific nourishment required for contingency say ever 30 years. | No specific nourishment required for contingency say ever 30 years. | Rarely = 50 years as most of the time this will be bigger than required
(**) I would like the modelling to join up and that this is a more evidenced number than off the monitoring alone, though the modelling is somewhat matched to the monitoring it can then give an idea of what shape eg more is lost initally and then it settles to its more equilibruim limited beach shape we now see.
Recycling
| 1 short | 2 short | 1 long | 2 long | 1 long 1 short | Even longer single groyne
Town beach | Receiving additional material there none to recycle.
East beach | No spare materail to recycle |  | If the groyne length is design just enough to hold cliff at east beach then there will not be spare to recycle. |  |  | Every 5-10 years, as required by town beach
Note on E8: Anna Kontini: Due to designed beach profile changed to straight line 25% decrease of the initial volume has been excluded from calculations. (The triangle was calculated to have 2100m^2 area and we accounted for 4.2m average height of beach reprofiling).

## Short Rock Volumes
CH | Beach Profile mOD | Crest Design Level mOD | Crest Width m | Width at base m | Area Trapiziod m2 | Volume m3 | Side Slopes 1:
39 | 3.188 | - |  |  |  |  | 2
39.5 | 2.786 | 4.6 | 5 | 12.256 | 15.6512
40 | 2.453 | 4.6 | 5 | 13.588 | 19.9542 | 8.9014
41 | 1.959 | 4.6 | 5 | 15.564 | 27.1548 | 23.5545
42 | 1.585 | 4.6 | 5 | 17.06 | 33.2554 | 30.2051
43 | 1.368 | 4.6 | 5 | 17.928 | 37.0516 | 35.1535
44 | 1.203 | 4.6 | 5 | 18.588 | 40.0642 | 38.5579
45 | 1.061 | 4.6 | 5 | 19.156 | 42.744 | 41.4041
46 | 0.918 | 4.6 | 5 | 19.728 | 45.5242 | 44.1341
47 | 0.785 | 4.6 | 5 | 20.26 | 48.1834 | 46.8538
48 | 0.643 | 4.4722 | 5 | 20.3169 | 48.472 | 48.3277
49 | 0.516 | 4.3444 | 5 | 20.3138 | 48.4562 | 48.4641
50 | 0.398 | 4.2167 | 5 | 20.2747 | 48.2578 | 48.357
51 | 0.257 | 4.0889 | 5 | 20.3276 | 48.5262 | 48.392
52 | 0.128 | 3.9611 | 5 | 20.3324 | 48.551 | 48.5386
53 | 0.023 | 3.8333 | 5 | 20.2413 | 48.0889 | 48.32
54 | -0.086 | 3.7056 | 5 | 20.1662 | 47.7096 | 47.8993
55 | -0.205 | 3.5778 | 5 | 20.1311 | 47.5327 | 47.6211
56 | -0.325 | 3.45 | 5 | 20.1 | 47.3762 | 47.4545
57 | -0.436 | 3.3222 | 5 | 20.0329 | 47.0396 | 47.2079
58 | -0.574 | 3.1944 | 5 | 20.0738 | 47.2446 | 47.1421
59 | -0.708 | 3.0667 | 5 | 20.0987 | 47.3696 | 47.3071
60 | -0.822 | 2.9389 | 5 | 20.0436 | 47.093 | 47.2313
61 | -0.935 | 2.8111 | 5 | 19.9844 | 46.7973 | 46.9451
62 | -1.052 | 2.6833 | 5 | 19.9413 | 46.5821 | 46.6897
63 | -1.128 | 2.5556 | 5 | 19.7342 | 45.5549 | 46.0685
64 | -1.283 | 2.4278 | 5 | 19.8431 | 46.0936 | 45.8243
65 | -1.386 | 2.3 | 5 | 19.744 | 45.6032 | 45.8484
66 | -1.427 | 2.1722 | 5 | 19.3969 | 43.9049 | 44.7541
67 | -1.412 | 2.0444 | 5 | 18.8258 | 41.1762 | 42.5406
68 | -1.421 | 1.9167 | 5 | 18.3507 | 38.9684 | 40.0723
69 | -1.442 | 1.7889 | 5 | 17.9236 | 37.0317 | 38.0001
70 | -1.456 | 1.6611 | 5 | 17.4684 | 35.0183 | 36.025
71 | -1.5 | 1.5333 | 5 | 17.1333 | 33.5689 | 34.2936
72 | -1.509 | 1.4056 | 5 | 16.6582 | 31.562 | 32.5655
73 | -1.56 | 1.2778 | 5 | 16.3511 | 30.2949 | 30.9285
74 | -1.574 | 1.15 | 5 | 15.896 | 28.4604 | 29.3776
75 | -1.586 | 1.0222 | 5 | 15.4329 | 26.6468 | 27.5536
76 | -1.639 | 0.89444 | 5 | 15.1338 | 25.5039 | 26.0753
77 | -1.665 | 0.76667 | 5 | 14.7267 | 23.9843 | 24.7441
78 | -1.686 | 0.63889 | 5 | 14.2996 | 22.4347 | 23.2095
79 | -1.718 | 0.51111 | 5 | 13.9164 | 21.0834 | 21.759
80 | -1.746 | 0.38333 | 5 | 13.5173 | 19.7148 | 20.3991
81 | -1.775 | 0.25556 | 5 | 13.1222 | 18.3991 | 19.0569
82 | -1.818 | 0.12778 | 5 | 12.7831 | 17.301 | 17.85
83 | -1.86 | -1.7764e-15 | 5 | 12.44 | 16.2192 | 16.7601
84 | -1.869 | 0 | 5 | 12.476 | 16.3313 | 16.2753
85 | -1.884 | -0.4182 | 5 | 10.8632 | 11.6261 | 13.9787
86 | -1.897 | -0.8364 | 5 | 9.2424 | 7.5527 | 9.5894
87 | -1.916 | -1.2546 | 5 | 7.6456 | 4.1819 | 5.8673
88 | -1.956 | -1.6728 | 5 | 6.1328 | 1.5764 | 2.8792
89 | -1.958 | -2.091 | 5 | 4.468 | -0.62962 | 0.47339
90 | -1.99
91 | -2.025
92 | -2.048
93 | -2.08
94 | -2.107
95 | -2.107
96 | -2.131
97 | -2.158
98 | -2.159
99 | -2.16
100 | -2.16
101 | -2.157
102 | -2.154
103 | -2.151
104 | -2.148
105 | -2.145
106 | -2.142
107 | -2.139
108 | -2.136
109 | -2.133
110 | -2.128
111 | -2.123
112 | -2.118
113 | -2.113
114 | -2.112
115 | -2.111
116 | -2.11
117 | -2.109
118 | -2.108
119 | -2.107
120 | -2.106
121 | -2.105
122 | -2.104
123 | -2.103
124 | -2.102
125 | -2.101
126 | -2.1
127 | -2.099
128 | -2.098
129 | -2.097
130 | -2.096
131 | -2.095
132 | -2.094
133 | -2.093
134 | -2.092
135 | -2.091
136 | -2.09
[5 empty] | Long Groyne Volume | 1697.4313 | m3

## Long Rock Volumes
CH | Beach Profile mOD | Crest Design Level mOD | Crest Width m | Width at base m | Area Trapiziod m2 | Volume m3 | Side Slopes 1:
39 | 3.188 | - |  |  |  |  | 2
39.5 | 2.786 | 2.786 | 5 | 5 | 0
40 | 2.453 | 3.01 | 5 | 7.228 | 3.4055 | 0.85137
41 | 1.959 | 3.24 | 5 | 10.124 | 9.6869 | 6.5462
42 | 1.585 | 3.47 | 5 | 12.54 | 16.5314 | 13.1092
43 | 1.368 | 3.7 | 5 | 14.328 | 22.5364 | 19.5339
44 | 1.203 | 3.93 | 5 | 15.908 | 28.5081 | 25.5223
45 | 1.061 | 4.15 | 5 | 17.356 | 34.5288 | 31.5185
46 | 0.918 | 4.38 | 5 | 18.848 | 41.2809 | 37.9049
47 | 0.785 | 4.6 | 5 | 20.26 | 48.1834 | 44.7322
48 | 0.643 | 4.6 | 5 | 20.828 | 51.1007 | 49.6421
49 | 0.516 | 4.6 | 5 | 21.336 | 53.7781 | 52.4394
50 | 0.398 | 4.6 | 5 | 21.808 | 56.3236 | 55.0509
51 | 0.257 | 4.6 | 5 | 22.372 | 59.4383 | 57.881
52 | 0.128 | 4.6 | 5 | 22.888 | 62.3576 | 60.8979
53 | 0.023 | 4.6 | 5 | 23.308 | 64.7829 | 63.5702
54 | -0.086 | 4.6 | 5 | 23.744 | 67.3472 | 66.065
55 | -0.205 | 4.6 | 5 | 24.22 | 70.201 | 68.7741
56 | -0.325 | 4.6 | 5 | 24.7 | 73.1362 | 71.6686
57 | -0.436 | 4.6 | 5 | 25.144 | 75.9026 | 74.5194
58 | -0.574 | 4.6 | 5 | 25.696 | 79.4106 | 77.6566
59 | -0.708 | 4.6 | 5 | 26.232 | 82.8897 | 81.1501
60 | -0.822 | 4.6 | 5 | 26.688 | 85.9062 | 84.3979
61 | -0.935 | 4.6 | 5 | 27.14 | 88.9475 | 87.4268
62 | -1.052 | 4.6 | 5 | 27.608 | 92.1502 | 90.5488
63 | -1.128 | 4.6 | 5 | 27.912 | 94.26 | 93.2051
64 | -1.283 | 4.6 | 5 | 28.532 | 98.6344 | 96.4472
65 | -1.386 | 4.6 | 5 | 28.944 | 101.5944 | 100.1144
66 | -1.427 | 4.6 | 5 | 29.108 | 102.7845 | 102.1894
67 | -1.412 | 4.6 | 5 | 29.048 | 102.3483 | 102.5664
68 | -1.421 | 4.6 | 5 | 29.084 | 102.6099 | 102.4791
69 | -1.442 | 4.6 | 5 | 29.168 | 103.2215 | 102.9157
70 | -1.456 | 4.6 | 5 | 29.224 | 103.6303 | 103.4259
71 | -1.5 | 4.6 | 5 | 29.4 | 104.92 | 104.2751
72 | -1.509 | 4.6 | 5 | 29.436 | 105.1848 | 105.0524
73 | -1.56 | 4.6 | 5 | 29.64 | 106.6912 | 105.938
74 | -1.574 | 4.6 | 5 | 29.696 | 107.1066 | 106.8989
75 | -1.586 | 4.6 | 5 | 29.744 | 107.4632 | 107.2849
76 | -1.639 | 4.6 | 5 | 29.956 | 109.0452 | 108.2542
77 | -1.665 | 4.6 | 5 | 30.06 | 109.8255 | 109.4353
78 | -1.686 | 4.6 | 5 | 30.144 | 110.4576 | 110.1415
79 | -1.718 | 4.6 | 5 | 30.272 | 111.4242 | 110.9409
80 | -1.746 | 4.4722 | 5 | 29.8729 | 108.4237 | 109.924
81 | -1.775 | 4.3444 | 5 | 29.4778 | 105.4924 | 106.9581
82 | -1.818 | 4.2167 | 5 | 29.1387 | 103.0077 | 104.2501
83 | -1.86 | 4.0889 | 5 | 28.7956 | 100.523 | 101.7654
84 | -1.869 | 3.9611 | 5 | 28.3204 | 97.1309 | 98.827
85 | -1.884 | 3.8333 | 5 | 27.8693 | 93.9625 | 95.5467
86 | -1.897 | 3.7056 | 5 | 27.4102 | 90.79 | 92.3763
87 | -1.916 | 3.5778 | 5 | 26.9751 | 87.8321 | 89.3111
88 | -1.956 | 3.45 | 5 | 26.624 | 85.4797 | 86.6559
89 | -1.958 | 3.3222 | 5 | 26.1209 | 82.1626 | 83.8211
90 | -1.99 | 3.1944 | 5 | 25.7378 | 79.6792 | 80.9209
91 | -2.025 | 3.0667 | 5 | 25.3667 | 77.3085 | 78.4938
92 | -2.048 | 2.9389 | 5 | 24.9476 | 74.6726 | 75.9905
93 | -2.08 | 2.8111 | 5 | 24.5644 | 72.3015 | 73.487
94 | -2.107 | 2.6833 | 5 | 24.1613 | 69.8463 | 71.0739
95 | -2.107 | 2.5556 | 5 | 23.6502 | 66.7916 | 68.3189
96 | -2.131 | 2.4278 | 5 | 23.2351 | 64.3588 | 65.5752
97 | -2.158 | 2.3 | 5 | 22.832 | 62.0375 | 63.1982
98 | -2.159 | 2.1722 | 5 | 22.3249 | 59.1751 | 60.6063
99 | -2.16 | 2.0444 | 5 | 21.8178 | 56.3769 | 57.776
100 | -2.16 | 1.9167 | 5 | 21.3067 | 53.6218 | 54.9993
101 | -2.157 | 1.7889 | 5 | 20.7836 | 50.8695 | 52.2456
102 | -2.154 | 1.6611 | 5 | 20.2604 | 48.1857 | 49.5276
103 | -2.151 | 1.5333 | 5 | 19.7373 | 45.5703 | 46.878
104 | -2.148 | 1.4056 | 5 | 19.2142 | 43.0233 | 44.2968
105 | -2.145 | 1.2778 | 5 | 18.6911 | 40.5447 | 41.784
106 | -2.142 | 1.15 | 5 | 18.168 | 38.1345 | 39.3396
107 | -2.139 | 1.0222 | 5 | 17.6449 | 35.7928 | 36.9636
108 | -2.136 | 0.89444 | 5 | 17.1218 | 33.5194 | 34.6561
109 | -2.133 | 0.76667 | 5 | 16.5987 | 31.3145 | 32.4169
110 | -2.128 | 0.63889 | 5 | 16.0676 | 29.1458 | 30.2301
111 | -2.123 | 0.51111 | 5 | 15.5364 | 27.0476 | 28.0967
112 | -2.118 | 0.38333 | 5 | 15.0053 | 25.02 | 26.0338
113 | -2.113 | 0.25556 | 5 | 14.4742 | 23.0629 | 24.0414
114 | -2.112 | 0.12778 | 5 | 13.9591 | 21.2321 | 22.1475
115 | -2.111 | -1.7764e-15 | 5 | 13.444 | 19.4676 | 20.3499
116 | -2.11 | 0 | 5 | 13.44 | 19.4542 | 19.4609
117 | -2.109 | 0 | 5 | 13.436 | 19.4408 | 19.4475
118 | -2.108 | 0 | 5 | 13.432 | 19.4273 | 19.434
119 | -2.107 | 0 | 5 | 13.428 | 19.4139 | 19.4206
120 | -2.106 | 0 | 5 | 13.424 | 19.4005 | 19.4072
121 | -2.105 | 0 | 5 | 13.42 | 19.3871 | 19.3938
122 | -2.104 | 0 | 5 | 13.416 | 19.3736 | 19.3803
123 | -2.103 | 0 | 5 | 13.412 | 19.3602 | 19.3669
124 | -2.102 | 0 | 5 | 13.408 | 19.3468 | 19.3535
125 | -2.101 | 0 | 5 | 13.404 | 19.3334 | 19.3401
126 | -2.1 | 0 | 5 | 13.4 | 19.32 | 19.3267
127 | -2.099 | 0 | 5 | 13.396 | 19.3066 | 19.3133
128 | -2.098 | 0 | 5 | 13.392 | 19.2932 | 19.2999
129 | -2.097 | 0 | 5 | 13.388 | 19.2798 | 19.2865
130 | -2.096 | 0 | 5 | 13.384 | 19.2664 | 19.2731
131 | -2.095 | -0.4182 | 5 | 11.7072 | 14.0073 | 16.6369
132 | -2.094 | -0.8364 | 5 | 10.0304 | 9.4511 | 11.7292
133 | -2.093 | -1.2546 | 5 | 8.3536 | 5.5978 | 7.5245
134 | -2.092 | -1.6728 | 5 | 6.6768 | 2.4475 | 4.0226
135 | -2.091 | -2.091 | 5 | 5 | 0 | 1.2237
136 | -2.09 |  | 5 | 13.36 | 19.1862 | 9.5931
[5 empty] | Long Groyne Volume | 5583.0896 | m3