## OBC Cover
[7 empty] | CIS | Hub
LARGE PROJECTS REVIEW GROUP | [5 empty] | SOC | Corporate Assets | North East Hub
OBC REVIEW SUMMARY | [6 empty] | E&B | North West Hub
[7 empty] | Finance | Midlands Hub
[7 empty] | FCRM | Eastern Hub
| Project Title | SIDMOUTH BEACH MANAGEMENT SCHEME |  |  |  |  | Facilities | South West Hub
[7 empty] | RMA | South East Hub
| LPRG Co-ordinator | Angela Maughan |  |  |  |  | Resources & Legal
| LPRG Reference | AM01984 |  |  |  |  | Waterways
| Submission type | Outline Business Case | Date received | 2023-07-07 | completed by LPRG Chair
| Approval Value (£k) |  | Hub |  | completed by LPRG Submissions Coordinator
| Total Project Cost (£k) | 25009 | Area |  |  | Successful delivery of the project to time, cost and quality appears highly likely and there are no major outstanding issues that at this stage appear to threaten delivery.
| Total GiA and Local Levy (£k) | 17611 | RMA | East Devon District Council
| Project Sponsor |  | RMA Reviewer |  |  | Successful delivery appears feasible but significant issues already exist requiring management attention. These appear resolvable at this stage and, if addressed promptly, should not present a cost/schedule overrun.
Project Executive/SRO
| Project Manager |  |  |  |  | Successful delivery of the project appears to be unachievable. There are major issues which, at this stage, do not appear to be manageable or resolvable. The project may need re-base lining and/or overall viability re-assessed.
| Originator | Martin Davies (PSO)
| Following the review of the documents the issues raised will be addressed by: [delete whichever is not required] |  | Correspondence | Meeting (TEAMS)
The selected option considers total embedded carbon and offers opportunities for reducing carbon and contributing to Net Zero.
| Delivery Confidence Assessment and Recommendation to Approving Officer |  |  |  |  | The option selection process has not considered total embedded carbon and makes no contribution to Net Zero. The project should be re-assessed.
Contribution towards Net Zero Carbon
| Specific items for the attention of the SRO/Executive/Approver to improve delivery confidence and further the contribution to Net Zero Carbon. |  |  |  |  | In progress
| 1 |  |  |  |  | Date of rejection
| 2 |  |  |  |  | Recommended, close
| 3 |  |  |  |  | Withdrawn |  | The Case for change
| 4 | [6 empty] | Objectives
[6 empty] | Green - No or minor issues to resolve | Commercial | Procurement strategy
| Defra/EA/RMA Reviewer Pool |  |  |  |  | Amber - Significant issues to resolve
| Hugh McCurrich (Chair) |  | Claire Trevor-Roper (FSoD) |  |  | Red - Major issues to resolve
| Phil Foxley (FCRM/Property Flood Resilience) |  | Ian Perkins (Modelling and Forecasting)
| Richard Nunn (LPRG advisor plus links to NPAB) |  | Neil Guthrie (Carbon)
| Michael Frye (EA Bsuiness Finance Operations) |  | Will Maclennan (Environment)
| Carolann Simmonds (Economics) |  | Stewart Rowe (RMA)
| Mark Hagger (Commercial) |  | Neil Fraser (Estates)
| Tim Ive (Engineering & Technical) |  | Steve Cook (Benefits Realisation) | [5 empty] | SE | Cambs Bedfordshire
| Emma Love (Environment) |  | Rachel Holliday (FSoD) | [5 empty] | NE | Cumbria Lancashire
| David Cotterell (Appraisal) |  | Martin Smalls (Funding) | [5 empty] | W | Devon Cornwall Isles of Scilly
| Gary Story (Finance) |  | Jas Bahi (Procurement)
Jose Poncela Blanco (Defra Flood Management)
| Angelika Hoerner (Defra Flood Management) | [7 empty] | SE | Essex Norfolk Suffolk
[9 empty] | SE | Greater Manchester Merseyside & Cheshire
|  |  | Status | In progress |  |  |  |  | SE | Herts North London
|  |  | Date | [5 empty] | NE | Kent South London
[9 empty] | SE | Lincs Northants
| FSOD category: | A4 | FSOD Number: | [6 empty] | Derbyshire Notts Leicestershire
[9 empty] | NE | London
| FSoD Approver: |  |  |  |  | A1 | Area Manager |  | W | Northumberland Durham Tees
| Name |  |  |  |  | A2 | Area FCRM Manager |  | SE | Shrops Heref Worcs Glos
| Title |  |  |  |  | A3 | Director of Operations |  | W | Solent South Downs
[6 empty] | A4 |  |  | W | Staffs Warks West Mids
| In Consultation with: (if required) |  |  |  |  | A5 |  |  | SE | Wessex
| Name |  |  |  |  | C6 |  |  |  | Thames
| Title |  |  |  |  | C7 |  |  | NE | Yorkshire
[6 empty] | C11 |  |  | NE | North East
[6 empty] | T2 |  |  | W | East Midlands
[9 empty] | W | West Midlands
[9 empty] | SE | East Anglia
[9 empty] | HO | E&B
[9 empty] | HO | Evidence
[9 empty] | HO | FCRM
[9 empty] | HO | Finance
[9 empty] | HO | Res & Legal
Note on D18: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: If different from PM

## OBC Issues Raised
[5 empty] | If you want to add your name to a comment or enhance an existing comment, please add your name and add enhanced text in a different colour | [5 empty] | Please highlight changes in the documents |  |  | If you want to add your name to a comment or enhance an existing comment, please add your name and add enhanced text in a different colour | [5 empty] | Please highlight changes in the documents |  |  | If you want to add your name to a comment or enhance an existing comment, please add your name and add enhanced text in a different colour
No | Date | Theme | Document Section / Appendix | Document Reference | LPRG Review of OBC | Action Required | Accounting Officer Test | Action Type | Reviewer | Response from Team | Document Section / Reference amended | Name of Person Providing Response | Date | LPRG Review | Action Required | Action Type | Reviewer | Date | Response from Team | Document Section / Reference amended | Name of Person Providing Response | Date | LPRG Review | Action Required | Action Type | Reviewer | Date
FSoD Advice to the team |  |  |  |  | Post successful assurance, the FSoD team will arrange approval of the £17,611k under A4 from the appropriate Director of Operations (Phil Lodge) in consultation with Deputy Director of Finance (Rowan Gray). |  |  | D: No comments or comment included for information but no action needed. | CTR | No response required | N/A | N/A | 2023-10-06
1 | 2023-07-12 | Engineering | OBC | p19, Selected Option / Appendix H | The Selected Option refers to demountable defences being used at the current boat and maintenance access, which the drawings in Appendix H show as 27m. What product is being proposed and is it suitable and been successfully applied in a coastal environment, where shingle damage will be probable? Where will the barriers be stored and who will deploy them? Is it necessary to have 27m for an access or can it be reduced? | Please provide further details to confirm the technical feasibility of using demountable defences in this coastal location. | Feasibility | A: Clarification requested on the review sheet only. | Phil Foxley | We agree that demountables are not desirable for this location. The 27m length of demountable was to avoid impacts on Fishermans area. Since the OBC submission we have considered further the alignment of the wall (to be progressed at Detailed Design). We will explore the option of amending the alignment, removing the the need for demountables.This change would likely reduce the size and cost of the wall but would require additional highway gate and other flood gates. We believe that this change will be cost neutral as a minimum. | N/A | IB | 2023-10-06
2 | 2023-07-12 | Economics | Appendix K | Initial Capital Costs | The costs for 27m of Demountable Defences at £27k seems very low. I had 12m of Demountable Defences in a scheme in 2007 and the costs were in the order of £38k. Have all the infrastructure works, baseplates etc. been included. | Please review the source of your costs for demountable defences | Value for Money | B: Minor issue. Please respond here and adjust the documents. | Phil Foxley | See response to comment 1 | As above | IB | 2023-10-06
3 | 2023-07-12 | Economics | Appendix K | Ongoing Costs | There are costs included for replacement of the demountable defences at year 50 and maintenance every 10 years, but there are no costs included for storage, deployment, security while deployed, removal and exercising/training of the demountable defences. | Please include all the associated ongoing costs for the demountable defences | Value for Money | B: Minor issue. Please respond here and adjust the documents. | Phil Foxley | See response to comment 1. If demountables are retained, there is an EDDC Sidmouth Depot with secure storage that is a favoured location with no cost impact. There is also a toilet block which is due to be rebuilt and could include provision for storage. Similar temporry defence arrangement (temporary strucutres and gate closures) are in place at Exmouth. The existing training scheme and skills will be shared with staff operating Sidmouth structures. Costs for deployment would be negligible as this will be covered by EDDC staff costs already in place. Training for use of demountables are estimated at one day per year for three people. | Training costs added. No change to text within OBC. All tables affected. Costs added to Appendix K. | TBS | 2023-10-06
4 | 2023-07-13 | Governance & Risk | Section 6.4 and Appendix L | Risks | Another beach management scheme has recently been subject to delay and cost increases due to the construction work uncovering previously unknown structures of historic interest. Is this a risk for Sidmouth and what mitigation has been considered. | Comment on this sheet please | Feasibility | A: Clarification requested on the review sheet only. | Hugh McCurrich | Sidmouth has an active historic group on the Advisory Group and nothing was noted. The 1990 scheme completed extensive bathymetric survey which didn't identify anything at the breakwater. The seawall has had renovation and nothing of relevance was noted during this work. The risk is therefore considered to be very low. | N/A | TBS | 2023-10-06
5 | 2023-07-18 | Estates | section 5.1, tables 20 and 21; and App K | Costs - Compensation | It is refreshing, and encouraging, to see a provision for compensation at this stage. I note however from App K that the £45k provided for is based on (from Row 15) potential impacts on hotels/ businesses. I would however also anticipate some provision is made to Compensate Crown Estates for consent to undertake the planned work, and for compensatin for impacts on fisheries (if dredgings are taken from off-shore fishing grounds) for recharge. | Comment on sheet please. | Affordability | B: Minor issue. Please respond here and adjust the documents. |  | All offshore material is coming from a licenced ground with fees included in the pricing. The foreshore and estuaries map indicates that Crown Estate do not own the foreshore at this location. | N/A | IB | 2023-10-06
6 | 2023-07-19 | Economics |  | OBC | Can you please update your Critical Success Factors to follow the 5 standard CSFs as presented in the HMT Geen Book please? | Update the OBC text | Compliance with guidance and policy | B: Minor issue. Please respond here and adjust the documents. | Carolann Simmonds | Yes, section updated. | Section 3.1 | IB | 2023-10-06
7 | 2023-07-19 | Economics |  | Economics Appendix I | You say the coast is at risk from waves from both SE and SW and you have modelled both and then added the AAD damages. THis is justified in the report as the events are independant. This only works if there is sufficient time between flood events so as to not trigger write-off and to allow enough time between events for the properties to be refurbished. e.g. you could add damages starting from a 1:10 AEP but not if they start at 1:1 AEP as the damages fromt he revious flood would not have been repaired. | Please confirm at what return period flooding starts from the SE and also from the SW (you have modelled the 1:1 event)? If this is extremely frequent, then what mitigation have you taken to avoid overestimating losses as it will take at least 6-12 months to repair a property after each flood. | Compliance with guidance and policy | B: Minor issue. Please respond here and adjust the documents. | Carolann Simmonds | The 1:1 year event was modelled for both South West and South East events. Flooding from different directions were combined by taking the worst case from both storm events, rather than adding the damages. In Year 100, flooding was predicted for the 1:1 from both the SE and SW, however, following the advice in the Flood and Coastal Erosion Risk Management Appraisal Guidance (FCERM-AG) (Environment Agency, 2010), properties are written-off if they are flooded above threshold on average more than once every three years. | N/A - Described in Appendix I | IB | 2023-10-06
8 | 2023-07-19 | Economics | OBC |  | Based on Table 15 and the FCERM-AG decision rule, the national economically preferred option should be 1.1c. However, you then go on to make the case for a Local Choice for Option 6. | Please add text to the OBC to make this distinction clear. Also, please confirm the PF calculator is set up for Option 1.1c and that you have sufficient contributions to afford your Local Choice. | Affordability | C: Major Issue affecting the recommendation for approval. Please respond here. | Carolann Simmonds | As outlined in Section 3.7 and 3.8, the only option that meets the project objectives and CSF is Option 6. The benefits and number of properties protected are the same for all options considered, therefore the FDGiA available for the scheme will be the same for all options. The PF calculator is therefore set-up for Option 6. | Discussed with Carolann Simmonds in meeting 6/10/2023. There is no difference in benefits and properties protected between different options. Agreed that PF calculator does not need updating. | IB | 2023-10-06
9 | 2023-07-19 | Economics |  | Appendix I Section 5.1.9 | Roads are generally are safe to reopen once the flood water has receeded. Normally some velocity of flow is required to cause scour and damage. | Please outline what evidence you have to justify that road surfaces would actually be damaged in these floods. Is there any historical evidence, other than immediately behind the seawall where other forces will impact road surface stability? | Compliance with guidance and policy | B: Minor issue. Please respond here and adjust the documents. | Carolann Simmonds | Discussed with Carolann Simmonds in meeting 6/10/2023. Allowance within guidance to identify the damages based on water depth etc. Evidence of historic damage during flooding included in Appendix I. | Appendix I - Section 5.1.9 | TBS | 2023-10-06
10 | 2023-07-19 | Economics | Appendix I | Section 5.4 | I'm not quite sure how you have done your capping. If I am reading this right, you could be underestimating your damages. | Could someone please give me a call to discuss this formula? | Compliance with guidance and policy | A: Clarification requested on the review sheet only. | Carolann Simmonds | Discussed with Carolann Simmonds and agreed revision to OBC appendix I | Appendix I - Section 5.4 updated to revise text | Emma Hick | 2023-10-06
11 | 2023-07-19 | Economics | Appendix I | Section 6.1.4.1 | Residential market values should be based on the regional market value, not local authority, in accordance with EA guidance. | Please check the average market values for SW region of England and test how they compare and affect your calculations. If the difference is significant, you will need to update your calculations. | Compliance with guidance and policy | B: Minor issue. Please respond here and adjust the documents. | Carolann Simmonds | There is a potential discrepancy between the East Devon District Council area and SW England area. Sidmouth is an affluent area with property prices substantially exceeding the EDDC area or the wider SW England area. Selection of the EDDC prices was considered as an appropriate basis for reflecting the property damages at Sidmouth without unfairly inflating the damages/benefits. Average SW England house price in Sept 2020 - £269.7k Average EDDC house price in Sept 2020 - £297.6k (10.3% higher) Property values were identified in 2020. These were uplifted to the Outline Business Case (OBC) date of 2022 using the GDP deflator indices. This resulted in a 5.2% increase to the damages. Review of house price information at Land Registry indicates an actual increase in average house price in SW England of 21.3% (£327.1k Jul 2022 vs. £269.7 Sept 2020). The EDDC inflated average house price was £313.1k. This suggests the benefits may have been underestimated rather than overestimated. Additional text added to OBC/appendices to clarify assumptions. | Discussed with Carolann Simmonds in meeting 6/10/2023. Agreed no need to revise as benefits are underestimated. | IB | 2023-10-06
12 | 2023-07-19 | Carbon | OBC | 3.6 | Good to see the lowest carbon option being the preferred option. If any help is needed with carbon assessment in the next stage please contact carbonplanningtool@environment-agency.gov.uk and we may be able to support it. | None | Compliance with guidance and policy | D: No comments or comment included for information but no action needed. | Neil Guthrie | No action | N/A | N/A | 2023-10-06
13 | 2023-07-21 | Commercial | 4.1 |  | I see that Option A is proposed for all of the contracts (NEC ECC/PSC). Whilst I understand the desire for cost certainty, I believe this appraoch may be problematic for a number of reasons - (a) Option A is not available under CDF therefore you will need to adopt other procurement routes. (b) There are still major design uncertainties particularly with regard to the offshore breakwater, therefore significant compensation events (CEs) are likely to be required. Whilst CEs would also be required for other NEC options, at least the client payment would be based on the actual costs. (c) Contractors/consultants in the infrastructure market are heavily in demand. I would worry that you may not receive many bids or that they will be inflated. | Please review your procurement strategy and at least conduct some market engagement, prior to committing to your proposed contract strategy. | Value for Money | B: Minor issue. Please respond here and adjust the documents. | Mark Hagger | a) Procurement amended to NEC Option C. b) It is not a design and build. A separate consultant will complete design and final build costs will be based on the final design, reducing potential number and size of CEs. Uncertanties in cost accomodated within the large risk budget. c) Due to the value of the construction contract, Contractors are regularly in contact to check on progress of the design/tender. Risk of low interest is considered low. | a) Section 4.1 b) N/A c) N/A | TBS | 2023-10-06
14 | 2023-07-21 | Engineering | table 20 |  | Only £25k is proposed for site investigation. For a scheme of this size I would expect £250k, to properly investigate ground conditions in the location of the structures, services locations, etc | Please review | Value for Money | C: Major Issue affecting the recommendation for approval. Please respond here. | Mark Hagger | Agreed. Some historic bathymetric surveys, though no known GI at the location fo the proposed breakwater. Likely GI requirements reconsidered and budget increased. | Cost increased in Appendix K and cascaded through OBC document (including Tables 20 and 21). | IB | 2023-10-06
15 | 2021-07-21 | Engineering |  |  | There has been a number of flood schemes delivered in Sidmouth since the 1990's that have benefitted the town but not achieved an acceptable solution. | 1. Have there been any lessons learnt from the previous schemes? 2. How have the economics been accounted for/included as previous schemes were likely to have a design life of more than 30 years? | Compliance with guidance and policy | B: Minor issue. Please respond here and adjust the documents. | Tim Ive | 1.Lessons have been learnt from previous schemes, firstly a good physical model largely correctly predicted the as seen affects on Sidmouth, and we are planning on having a physical model made to correlate with a digital model. Previous schemes were only focussed on coastal erosion/storm damage of the town, not flood risk and not coastal risk to properties outside the town frontage. This scheme takes a more holistic approach. The current scheme has also taken on board a lot of feedback from the previous schemes. Initially not liked, the existing rock islands are extremely popular due to the reduced storm risk in their lea and the increased recreational benefits they provide. 2. The 1990s scheme was purely a coastal defence scheme (erosion of the town) so no flooding damages/benefits were included. The design life of the scheme is circa 100 years, which is when we feel the current scheme will start to fail. This is reflected in the economics. |  | TBS | 2023-10-06
16 | 2021-07-21 | Engineering |  |  | The risk pot is very healthy and I support the approach taken however we can be caught out by increaseing costs so we need to be clear what happens if costs increase. | If costs increase above the funding provided who would under those circumstances cover the costs? | Affordability | B: Minor issue. Please respond here and adjust the documents. | Tim Ive | a) An allowance for inflation is included within the FCERM bid. b) If costs increase, and the project is not eligible for further GiA, East Devon will cover costs in excess of the target. | End of Section 5.2 | TBS | 2023-10-06
17 | 2021-07-21 | Engineering |  |  | The previous scheems indicate that there has been a significent loss of beach recharge material. Are there any tolerences on the ammount/rate of loss before any subsequent intevention would be required | What modelling has/proposed to be carried out to indetify the rate of beach recharge and how would any loss be managed. | Compliance with guidance and policy | B: Minor issue. Please respond here and adjust the documents. | Tim Ive | Morphologic change (beach loss) happened several years ago. More recently, beach volume is static. Further modelliong will be completed during detailed design to confirm anticipated transport, with appropriate sensitivity testing. The specific modelling scope is to be confirmed. | N/A | IB | 2023-10-06
18 | 2021-07-21 | Engineering |  |  | Deploying demountable barriers can be costly (even if they are stop logs ) and time consuming. Therefore we need to be clear who will do this, who recieves the flood warnings, where is the kit stored, what are the safe deployment times, are there people on standby abel to do this at relative short notice?. | Who will be accountable for manageing and implimenting the deployment of the demountable barriers? | Affordability | B: Minor issue. Please respond here and adjust the documents. | Tim Ive | See response to item 1 | N/A | TBS | 2023-10-06
19 | 2023-07-21 | Modelling |  |  | The modelling does not appear to have been reviewed or assured. | We would recommend that the modelling is reviewed and assured to provide confidence and reduce the risk going forward. This should also save time and cost. The review could be undertaken by E&R, via PSO or it could be a third-party review. | Compliance with guidance and policy | B: Minor issue. Please respond here and adjust the documents. | Clare Fravigar | The wave model used was from the State of the Nation project so was already calibrated and local validation was undertaken to further validate the model performance. Whilst overtopping is difficult to quantify and validate, tests were undertaken on known storm events and where additional evidence / videos / images were available to validate outputs. The Tuflow model from the BMP was used with only minor local adjustments to represent options. The sediment transport model was first calibrated against known performance to create a baseline model to which options could be tested. We Therefore we feel the model does not require further review. This was agreed by the EA at the time the work was progressed. Additional more detailed modelling will be undertaken during the detailed design phase, where further validation will be undertaken on key aspects and uncertainties. | N/A | TG | 2023-10-06
20 | 2023-07-23 | Environment | Table 21 | OBC | The costs for Site investigation and survey seems very low, given that dredging, beach recharge and breakwater construction are proposed. This would normally require extensive bathymetric and other surveys to be required to support the marine licence and CEFAS requirements. The surveys are usually very expensive and £25K seems very low. If the proper surveys are not carried out ahead of the marine licence submission it could lead to significant delays in approvals. | Review site investigation and survey requirements to support marine licence requirements and update costs accordingly. | Compliance with guidance and policy | B: Minor issue. Please respond here and adjust the documents. | Will Maclennan | See response to item 14 | See response to item 14 | IB | 2023-10-06
21 | 2023-07-25 | Finance |  | FCERM2 | Has EDDC produced an FCERM2 (application for grant) to go with this OBC as this will be needed to obtain approval? | Provide FCERM2 | Compliance with guidance and policy | C: Major Issue affecting the recommendation for approval. Please respond here. | Michael Frye | Accompanying the response to these queries and confirmation of final costs, an FCERM2 form will be submitted. | N/A | TBS | 2023-10-06
22 | 2023-07-25 | Commercial | 4.1 |  | As per Mark's comments above Option A should only be considered when we are able to define the scope and only considered when the jobs are bid as under a single source contract ability to agree shared risk is very difficult and the Client will have an inflated Option A price to cover all risks. | Please provide a more detailed Procurement strategy. | Value for Money | C: Major Issue affecting the recommendation for approval. Please respond here. | Jas Bahi | See response to item 13 | See response to item 13 | GA | 2023-10-06
23 | 2023-07-25 | Commercial | 4.1 |  | The procurement strategy is still appears to be undetermined and this is ok for the Construction stage, however for the Detailed Design stage I would like to see a procurement strategy that clears states if we are using frameworks or open market. with a procurement plan (although stated earlier in bullet point) or selection for the preferred route and why. What risk do we need to manage in the PSC contract and the ECC that we need to articulate in the Detail Design contract now. | Please provide a more detailed Procurement strategy. | Value for Money | B: Minor issue. Please respond here and adjust the documents. | Jas Bahi | Intention to use CDF for Detailed Design? | See response to item 13 | TBS | 2023-10-06
24 | 2023-07-25 | Economics | 2.7.3 |  | £500k contribution from Highway for a benefit of £23.4m - Should their contribution not be a lot higher for the longer term benefit this provides them? | Comment | Affordability | A: Clarification requested on the review sheet only. | Jas Bahi | Discussions have been held to maximise contributions. Originally it was agreed that DCC, EDDC and Local Levy would each contribute £500k to the total funding (EDDC have subsequently increased their contribution). DCC are unable to contribute further due to theuir financial situation. | N/A | TBS | 2023-10-06
25 | 2023-07-25 | Finance | Financial Case |  | No further comments at this stage | None | Affordability | D: No comments or comment included for information but no action needed. | Gary Story | No comments | N/A | N/A | N/A
26 | 26.7.23 | Commercial |  | Table 24 | Congratulations on securing the contributions. Is there agreement on when and how they will be utilised for example pro-rata with grant expenditure? How will the combined risk pot be managed? Are EDDC aware of a potential requirement due to cost overuns to increase their contribution as promoter of the scheme? | Add some text how the contributions and risk pot will be managed. | Propriety (incl. use of public money in option choice) | B: Minor issue. Please respond here and adjust the documents. | Stewart Rowe | Thank you. We will have a legal agreement with each contributor to confirm when and how money will be spent. We plan to use EDDC moneys and FDGIA during the detailed design stage, and once construction has begun, we will progressively ask from funding from all the contributors to match FDGIA applications. The additional risk pot by EDDC will be spent at the end if required, and EDDC are fully aware this money (and more) may be needed to complete the scheme. The risk pot is currently made up of FDGIA and additional EDDC moneys. It has been agreed that the FDGIA in the risk pot will be used first before EDDC dip into their £1.7m risk pot contribution. (Was a condition of EDDC councillors agreeing the extra ordinary spend (relative to the size of our council). Yes, EDDC aware of a potential requirement due to cost overruns to increase their contribution as promoter of the scheme. | N/A | TBS | 2023-10-06
16
16
16
16
16
16
16
16
16
16
16
16
16
16
16
16
16
16
16
16
A: Clarification requested on the review sheet only.
B: Minor issue. Please respond here and adjust the documents.
C: Major Issue affecting the recommendation for approval. Please respond here.
D: No comments or comment included for information but no action needed.
Defra
Commercial
Governance & Risk
Environment
Appraisal
MEICA
Economics
Modelling
Funding
|  |  | Engineering |  |  | Ian Hodge |  |  |  | Regularity (legislative compliance)
|  |  | Finance |  |  | Tim Ive |  |  |  | Propriety (incl. use of public money in option choice)
|  |  | Estates |  |  | David Cotterell |  |  |  | Value for Money
|  |  | Carbon |  |  | Richard Nunn |  |  |  | Affordability
|  |  | Learning Points |  |  | Neil Marr |  |  |  | Feasibility
[6 empty] | Nick Jones |  |  |  | Compliance with guidance and policy
Matt Georges
Martin Smalls
Kevin House
Nick Howard
Richard Williams
Rachel Wiles
Roger Quinn
Simon Lewis
Claire Trevor-Roper
Gary Story
Sagita Navickaite
Harry Walton
Note on H2: Author: See Accounting Officer Test tab for definitions

## FBC Cover (hidden)
[7 empty] | CIS | Hub
LARGE PROJECTS REVIEW GROUP | [5 empty] | SOC | Corporate Assets | North East Hub
FBC REVIEW SUMMARY | [6 empty] | E&B | North West Hub
[7 empty] | Finance | Midlands Hub
[7 empty] | FCRM | Eastern Hub
| Project Title | [5 empty] | Facilities | South West Hub
[7 empty] | RMA | South East Hub
| LPRG Co-ordinator | [5 empty] | Resources & Legal
| LPRG Reference | [5 empty] | Waterways
| Submission type | Full Business Case | Date received |  | completed by LPRG Chair
| Approval Value (£k) |  | Hub |  | completed by LPRG Submissions Coordinator
| Total Project Cost (£k) |  | Area |  |  | Successful delivery of the project to time, cost and quality appears highly likely and there are no major outstanding issues that at this stage appear to threaten delivery.
| Total GiA and Local Levy (£k) |  | RMA
| Project Sponsor |  | RMA Reviewer |  |  | Successful delivery appears feasible but significant issues already exist requiring management attention. These appear resolvable at this stage and, if addressed promptly, should not present a cost/schedule overrun.
Project Executive/SRO
| Project Manager |  |  |  |  | Successful delivery of the project appears to be unachievable. There are major issues which, at this stage, do not appear to be manageable or resolvable. The project may need re-base lining and/or overall viability re-assessed.
Originator
| Following the review of the documents the issues raised will be addressed by: [delete whichever is not required] |  | Correspondence | Meeting (TEAMS)
The selected option considers total embedded carbon and offers opportunities for reducing carbon and contributing to Net Zero.
| Delivery Confidence Assessment and Recommendation to Approving Officer |  |  |  |  | The option selection process has not considered total embedded carbon and makes no contribution to Net Zero. The project should be re-assessed.
| Contribution towards Net Zero Carbon | The option selection process has not considered total embedded carbon and makes no contribution to Net Zero. The project should be re-assessed.
| Specific items for the attention of the SRO/Executive/Approver to improve delivery confidence and further the contribution to Net Zero Carbon. |  |  |  |  | In progress
| 1 |  |  |  |  | Date of rejection
| 2 |  |  |  |  | Recommended, close
| 3 |  |  |  |  | Withdrawn |  | The Case for change
| 4 | [6 empty] | Objectives
[6 empty] | Green - No or minor issues to resolve | Commercial | Procurement strategy
| Defra/EA/RMA Reviewer Pool |  |  |  |  | Amber - Significant issues to resolve
| Hugh McCurrich (Chair) |  | Claire Trevor-Roper (FSoD) |  |  | Red - Major issues to resolve
| Phil Foxley (FCRM/Property Flood Resilience) |  | Ian Perkins (Modelling and Forecasting)
| Richard Nunn (LPRG advisor plus links to NPAB) |  | Neil Guthrie (Carbon)
| Andy Eden (Strategies) |  | Will Maclennan (Environment)
| Carolann Simmonds (Economics) |  | Stewart Rowe (RMA)
| Mark Hagger (Commercial) |  | Neil Fraser (Estates)
| Tim Ive (Engineering & Technical) |  | Steve Cook (Benefits Realisation) | [5 empty] | SE | Cambs Bedfordshire
| Emma Love (Environment) |  | Rachel Holliday (FSoD) | [5 empty] | NE | Cumbria Lancashire
| David Cotterell (Appraisal) |  | Martin Smalls (Funding) | [5 empty] | W | Devon Cornwall Isles of Scilly
| Gary Story (Finance) |  | Jas Bahi (Procurement)
| Jose Poncela Blanco (Defra Flood Management) |  | Gary Story (Finance)
| Angelika Hoerner (Defra Flood Management) | [7 empty] | SE | Essex Norfolk Suffolk
[9 empty] | SE | Greater Manchester Merseyside & Cheshire
|  |  | Status | In progress |  |  |  |  | SE | Herts North London
|  |  | Date | [5 empty] | NE | Kent South London
[9 empty] | SE | Lincs Northants
| FSOD category: |  | FSOD Number: | [6 empty] | Derbyshire Notts Leicestershire
[9 empty] | NE | London
| FSoD Approver: |  |  |  |  | A1 | Area Manager |  | W | Northumberland Durham Tees
| Name |  |  |  |  | A2 | Area FCRM Manager |  | SE | Shrops Heref Worcs Glos
| Title |  |  |  |  | A3 | Director of Operations |  | W | Solent South Downs
[6 empty] | A4 |  |  | W | Staffs Warks West Mids
| In Consultation with: (if required) |  |  |  |  | A5 |  |  | SE | Wessex
| Name |  |  |  |  | C6 |  |  |  | Thames
| Title |  |  |  |  | C7 |  |  | NE | Yorkshire
[6 empty] | C11 |  |  | NE | North East
[6 empty] | T2 |  |  | W | East Midlands
[9 empty] | W | West Midlands
[9 empty] | SE | East Anglia
[9 empty] | HO | E&B
[9 empty] | HO | Evidence
[9 empty] | HO | FCRM
[9 empty] | HO | Finance
[9 empty] | HO | Res & Legal
Note on D18: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: If different from PM

## FBC Issues Raised (hidden)
[5 empty] | If you want to add your name to a comment or enhance an existing comment, please add your name and add enhanced text in a different colour | [5 empty] | Please highlight changes in the documents |  |  | If you want to add your name to a comment or enhance an existing comment, please add your name and add enhanced text in a different colour | [5 empty] | Please highlight changes in the documents |  |  | If you want to add your name to a comment or enhance an existing comment, please add your name and add enhanced text in a different colour
No | Date | Theme | Document Section / Appendix | Document Reference | LPRG Review of FBC | Action Required | Accounting Officer Test | Action Type | Reviewer | Response from Team | Document Section / Reference amended | Name of Person Providing Response | Date | LPRG Review | Action Required | Action Type | Reviewer | Date | Response from Team | Document Section / Reference amended | Name of Person Providing Response | Date | LPRG Review | Action Required | Action Type | Reviewer | Date
FSoD Advice to the team
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
16
16
16
16
16
16
16
16
16
16
16
16
16
16
16
16
16
16
16
16
16
16
16
16
16
16
16
16
16
16
A: Clarification requested on the review sheet only.
B: Minor issue. Please respond here and adjust the documents.
C: Major Issue affecting the recommendation for approval. Please respond here.
D: No comments or comment included for information but no action needed.
Defra
Commercial
Governance & Risk
Environment
Appraisal
MEICA
Economics
Modelling
Funding
|  |  | Engineering |  |  | Ian Hodge |  |  |  | Regularity (legislative compliance)
|  |  | Finance |  |  | Tim Ive |  |  |  | Propriety (incl. use of public money in option choice)
|  |  | Estates |  |  | David Cotterell |  |  |  | Value for Money
|  |  | Carbon |  |  | Richard Nunn |  |  |  | Affordability
|  |  | Learning Points |  |  | Neil Marr |  |  |  | Feasibility
[6 empty] | Nick Jones |  |  |  | Compliance with guidance and policy
Matt Georges
Martin Smalls
Kevin House
Nick Howard
Richard Williams
Rachel Wiles
Roger Quinn
Simon Lewis
Claire Trevor-Roper
Gary Story
Sagita Navickaite
Harry Walton
Note on H2: Author: See Accounting Officer Test tab for definitions

## BCUR1 Cover (hidden)
[6 empty] | CIS | Hub
LARGE PROJECTS REVIEW GROUP |  |  |  |  | SOC | Corporate Assets | North East Hub
BCUR1 REVIEW SUMMARY | [5 empty] | E&B | North West Hub
[6 empty] | Finance | Midlands Hub
[6 empty] | FCRM | Eastern Hub
| Project Title |  |  |  |  | Facilities | South West Hub
[6 empty] | RMA | South East Hub
| LPRG Co-ordinator |  |  |  |  | Resources & Legal
| LPRG Reference |  |  |  |  | Waterways
| Submission type | Date received |  | completed by LPRG Chair
| BCUR Value (£k) | Hub |  | completed by LPRG Submissions Coordinator
| Total Project Cost (£k) | Area |  |  | Successful delivery of the project to time, cost and quality appears highly likely and there are no major outstanding issues that at this stage appear to threaten delivery.
| Total GiA and Local Levy (£k) | RMA
| Project Sponsor | RMA Reviewer |  |  | Successful delivery appears feasible but significant issues already exist requiring management attention. These appear resolvable at this stage and, if addressed promptly, should not present a cost/schedule overrun.
Project Executive/SRO
| Project Manager |  |  |  | Successful delivery of the project appears to be unachievable. There are major issues which, at this stage, do not appear to be manageable or resolvable. The project may need re-base lining and/or overall viability re-assessed.
Originator
| Following the review of the documents the issues raised will be addressed by: [delete whichever is not required] | Correspondence | Meeting (TEAMS)
The selected option considers total embedded carbon and has the lowest embedded carbon of all options considered and optimises the contribution to Net Zero.
The selected option considers total embedded carbon and contributes to Net Zero, but there may be opportunities to reduce total embedded carbon further.
| Delivery Confidence Assessment and Recommendation to Approving Officer |  |  |  | The option selection process has not considered total embedded carbon and makes no contribution to Net Zero. The project should be re-assessed.
Contribution towards Net Zero Carbon
| Specific items for the attention of the SRO/Executive/Approver to improve delivery confidence and further the contribution to Net Zero Carbon. |  |  |  | In progress
| 1 |  |  |  | Date of rejection
| 2 |  |  |  | Recommended, close
| 3 |  |  |  | Withdrawn |  | The Case for change
| 4 | [5 empty] | Objectives
[5 empty] | Green - No or minor issues to resolve | Commercial | Procurement strategy
| Defra/EA/RMA Reviewer Pool |  |  |  | Amber - Significant issues to resolve
| Hugh McCurrich (Chair) | Claire Trevor-Roper (FSoD) |  |  | Red - Major issues to resolve
| Phil Foxley (FCRM/Property Flood Resilience) | Ian Perkins (Modelling and Forecasting)
| Richard Nunn (LPRG advisor plus links to NPAB) | Neil Guthrie (Carbon)
| Andy Eden (Strategies) | Will Maclennan (Environment)
| Carolann Simmonds (Economics) | Stewart Rowe (RMA)
| Mark Hagger (Commercial) | Neil Fraser (Estates)
| Tim Ive (Engineering & Technical) | Steve Cook (Benefits Realisation) | [5 empty] | SE | Cambs Bedfordshire
| Emma Love (Environment) | Rachel Holliday (FSoD) | [5 empty] | NE | Cumbria Lancashire
| David Cotterell (Appraisal) | Martin Smalls (Funding) | [5 empty] | W | Devon Cornwall Isles of Scilly
| Gary Story (Finance) | Jas Bahi (Procurement)
Jose Poncela Blanco (Defra Flood Management)
| Angelika Hoerner (Defra Flood Management) | [6 empty] | SE | Essex Norfolk Suffolk
[8 empty] | SE | Greater Manchester Merseyside & Cheshire
|  | Status | In progress |  |  |  |  | SE | Herts North London
|  | Date | [5 empty] | NE | Kent South London
[8 empty] | SE | Lincs Northants
| FSOD category: | FSOD Number: | [6 empty] | Derbyshire Notts Leicestershire
[8 empty] | NE | London
| FSoD Approver: |  |  |  | A1 | Area Manager |  | W | Northumberland Durham Tees
| Name |  |  |  | A2 | Area FCRM Manager |  | SE | Shrops Heref Worcs Glos
| Title |  |  |  | A3 | Director of Operations |  | W | Solent South Downs
[5 empty] | A4 |  |  | W | Staffs Warks West Mids
| In Consultation with: (if required) |  |  |  | A5 |  |  | SE | Wessex
| Name |  |  |  | C6 |  |  |  | Thames
| Title |  |  |  | C7 |  |  | NE | Yorkshire
[5 empty] | C11 |  |  | NE | North East
[5 empty] | T2 |  |  | W | East Midlands
[8 empty] | W | West Midlands
[8 empty] | SE | East Anglia
[8 empty] | HO | E&B
[8 empty] | HO | Evidence
[8 empty] | HO | FCRM
[8 empty] | HO | Finance
[8 empty] | HO | Res & Legal
BCUR (SOC1)
BCUR (SOC2)
BCUR (SOC3)
BCUR (OBC1)
BCUR (OBC2)
BCUR (OBC3)
BCUR (FBC1)
BCUR (FBC2)
BCUR (FBC3)
Note on D18: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: If different from PM

## BCUR1 Issues Raised (hidden)
[5 empty] | If you want to add your name to a comment or enhance an existing comment, please add your name and add enhanced text in a different colour | [5 empty] | Please highlight changes in the documents |  |  | If you want to add your name to a comment or enhance an existing comment, please add your name and add enhanced text in a different colour | [5 empty] | Please highlight changes in the documents |  |  | If you want to add your name to a comment or enhance an existing comment, please add your name and add enhanced text in a different colour
No | Date | Theme | Document Section / Appendix | Document Reference | LPRG Review of BCUR | Action Required | Accounting Officer Test | Action Type | Reviewer | Response from Team | Document Section / Reference amended | Name of Person Providing Response | Date | LPRG Review | Action Required | Action Type | Reviewer | Date | Response from Team | Document Section / Reference amended | Name of Person Providing Response | Date | LPRG Review | Action Required | Action Type | Reviewer | Date
FSoD Advice to the team
1 | 1900-02-23
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
16
16
16
16
16
16
16
16
16
16
16
16
16
16
16
16
16
16
16
16
16
16
16
16
16
16
16
16
16
16
A: Clarification requested on the review sheet only.
B: Minor issue. Please respond here and adjust the documents.
C: Major Issue affecting the recommendation for approval. Please respond here.
D: No comments or comment included for information but no action needed.
Defra
Commercial
Governance & Risk
Environment
Appraisal
MEICA
Economics
Modelling
Funding
|  |  | Engineering |  |  | Ian Hodge |  |  |  | Regularity (legislative compliance)
|  |  | Finance |  |  | Tim Ive |  |  |  | Propriety (incl. use of public money in option choice)
|  |  | Estates |  |  | David Cotterell |  |  |  | Value for Money
|  |  | Carbon |  |  | Richard Nunn |  |  |  | Affordability
|  |  | Learning Points |  |  | Neil Marr |  |  |  | Feasibility
[6 empty] | Nick Jones |  |  |  | Compliance with guidance and policy
Matt Georges
Martin Smalls
Kevin House
Nick Howard
Richard Williams
Rachel Wiles
Roger Quinn
Simon Lewis
Claire Trevor-Roper
Gary Story
Sagita Navickaite
Harry Walton
Note on H2: Author: See Accounting Officer Test tab for definitions

## BCUR2 Cover (hidden)
[6 empty] | CIS | Hub
LARGE PROJECTS REVIEW GROUP |  |  |  |  | SOC | Corporate Assets | North East Hub
BCUR2 REVIEW SUMMARY | [5 empty] | E&B | North West Hub
[6 empty] | Finance | Midlands Hub
[6 empty] | FCRM | Eastern Hub
| Project Title |  |  |  |  | Facilities | South West Hub
[6 empty] | RMA | South East Hub
| LPRG Co-ordinator |  |  |  |  | Resources & Legal
| LPRG Reference |  |  |  |  | Waterways
| Submission type | Date received |  | completed by LPRG Chair
| BCUR Value (£k) | Hub |  | completed by LPRG Submissions Coordinator
| Total Project Cost (£k) | Area |  |  | Successful delivery of the project to time, cost and quality appears highly likely and there are no major outstanding issues that at this stage appear to threaten delivery.
| Total GiA and Local Levy (£k) | RMA
| Project Sponsor | RMA Reviewer |  |  | Successful delivery appears feasible but significant issues already exist requiring management attention. These appear resolvable at this stage and, if addressed promptly, should not present a cost/schedule overrun.
Project Executive/SRO
| Project Manager |  |  |  | Successful delivery of the project appears to be unachievable. There are major issues which, at this stage, do not appear to be manageable or resolvable. The project may need re-base lining and/or overall viability re-assessed.
Originator
| Following the review of the documents the issues raised will be addressed by: [delete whichever is not required] | Correspondence | Meeting (TEAMS)
The selected option considers total embedded carbon and has the lowest embedded carbon of all options considered and optimises the contribution to Net Zero.
The selected option considers total embedded carbon and contributes to Net Zero, but there may be opportunities to reduce total embedded carbon further.
| Delivery Confidence Assessment and Recommendation to Approving Officer |  |  |  | The option selection process has not considered total embedded carbon and makes no contribution to Net Zero. The project should be re-assessed.
Contribution towards Net Zero Carbon
| Specific items for the attention of the SRO/Executive/Approver to improve delivery confidence and further the contribution to Net Zero Carbon. |  |  |  | In progress
| 1 |  |  |  | Date of rejection
| 2 |  |  |  | Recommended, close
| 3 |  |  |  | Withdrawn |  | The Case for change
| 4 | [5 empty] | Objectives
[5 empty] | Green - No or minor issues to resolve | Commercial | Procurement strategy
| Defra/EA/RMA Reviewer Pool |  |  |  | Amber - Significant issues to resolve
| Hugh McCurrich (Chair) | Claire Trevor-Roper (FSoD) |  |  | Red - Major issues to resolve
| Phil Foxley (FCRM/Property Flood Resilience) | Ian Perkins (Modelling and Forecasting)
| Richard Nunn (LPRG advisor plus links to NPAB) | Neil Guthrie (Carbon)
| Andy Eden (Strategies) | Will Maclennan (Environment)
| Carolann Simmonds (Economics) | Stewart Rowe (RMA)
| Mark Hagger (Commercial) | Neil Fraser (Estates)
| Tim Ive (Engineering & Technical) | Steve Cook (Benefits Realisation) | [5 empty] | SE | Cambs Bedfordshire
| Emma Love (Environment) | Rachel Holliday (FSoD) | [5 empty] | NE | Cumbria Lancashire
| David Cotterell (Appraisal) | Martin Smalls (Funding) | [5 empty] | W | Devon Cornwall Isles of Scilly
| Gary Story (Finance) | Jas Bahi (Procurement)
Jose Poncela Blanco (Defra Flood Management)
| Angelika Hoerner (Defra Flood Management) | [6 empty] | SE | Essex Norfolk Suffolk
[8 empty] | SE | Greater Manchester Merseyside & Cheshire
|  | Status | In progress |  |  |  |  | SE | Herts North London
|  | Date | [5 empty] | NE | Kent South London
[8 empty] | SE | Lincs Northants
| FSOD category: | FSOD Number: | [6 empty] | Derbyshire Notts Leicestershire
[8 empty] | NE | London
| FSoD Approver: |  |  |  | A1 | Area Manager |  | W | Northumberland Durham Tees
| Name |  |  |  | A2 | Area FCRM Manager |  | SE | Shrops Heref Worcs Glos
| Title |  |  |  | A3 | Director of Operations |  | W | Solent South Downs
[5 empty] | A4 |  |  | W | Staffs Warks West Mids
| In Consultation with: (if required) |  |  |  | A5 |  |  | SE | Wessex
| Name |  |  |  | C6 |  |  |  | Thames
| Title |  |  |  | C7 |  |  | NE | Yorkshire
[5 empty] | C11 |  |  | NE | North East
[5 empty] | T2 |  |  | W | East Midlands
[8 empty] | W | West Midlands
[8 empty] | SE | East Anglia
[8 empty] | HO | E&B
[8 empty] | HO | Evidence
[8 empty] | HO | FCRM
[8 empty] | HO | Finance
[8 empty] | HO | Res & Legal
BCUR (SOC1)
BCUR (SOC2)
BCUR (SOC3)
BCUR (OBC1)
BCUR (OBC2)
BCUR (OBC3)
BCUR (FBC1)
BCUR (FBC2)
BCUR (FBC3)
Note on D18: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: If different from PM

## BCUR2 Issues Raised (hidden)
[5 empty] | If you want to add your name to a comment or enhance an existing comment, please add your name and add enhanced text in a different colour | [5 empty] | Please highlight changes in the documents |  |  | If you want to add your name to a comment or enhance an existing comment, please add your name and add enhanced text in a different colour | [5 empty] | Please highlight changes in the documents |  |  | If you want to add your name to a comment or enhance an existing comment, please add your name and add enhanced text in a different colour
No | Date | Theme | Document Section / Appendix | Document Reference | LPRG Review of BCUR | Action Required | Accounting Officer Test | Action Type | Reviewer | Response from Team | Document Section / Reference amended | Name of Person Providing Response | Date | LPRG Review | Action Required | Action Type | Reviewer | Date | Response from Team | Document Section / Reference amended | Name of Person Providing Response | Date | LPRG Review | Action Required | Action Type | Reviewer | Date
FSoD Advice to the team
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
16
16
16
16
16
16
16
16
16
16
16
16
16
16
16
16
16
16
16
16
16
16
16
16
16
16
16
16
16
16
A: Clarification requested on the review sheet only.
B: Minor issue. Please respond here and adjust the documents.
C: Major Issue affecting the recommendation for approval. Please respond here.
D: No comments or comment included for information but no action needed.
Defra
Commercial
Governance & Risk
Environment
Appraisal
MEICA
Economics
Modelling
Funding
|  |  | Engineering |  |  | Ian Hodge |  |  |  | Regularity (legislative compliance)
|  |  | Finance |  |  | Tim Ive |  |  |  | Propriety (incl. use of public money in option choice)
|  |  | Estates |  |  | David Cotterell |  |  |  | Value for Money
|  |  | Carbon |  |  | Richard Nunn |  |  |  | Affordability
|  |  | Learning Points |  |  | Neil Marr |  |  |  | Feasibility
[6 empty] | Nick Jones |  |  |  | Compliance with guidance and policy
Matt Georges
Martin Smalls
Kevin House
Nick Howard
Richard Williams
Rachel Wiles
Roger Quinn
Simon Lewis
Claire Trevor-Roper
Gary Story
Sagita Navickaite
Harry Walton
Note on H2: Author: See Accounting Officer Test tab for definitions

## Accounting Officer Tests
Accounting Officer Test Guidance
For HMT Guidance documents go to: https://www.gov.uk/government/publications/parliamentary-scrutiny-of-public-spending
Regularity: first of all we must ensure that we have full and current legal powers to undertake the activity. Any planned expenditure should be in accordance with relevant legislation and if in doubt consult our lawyers.
Propriety: proposals and expenditure should respect Parliament’s intentions for the governing legislation and the use of public money must adhere to the principles outlined in Managing Public Money. In other words, the proposed activity and expenditure should be proper by honouring the conventions, protocols and controls applied to public expenditure. The Affordability question can arise under this consideration because if a proposal was not financially sustainable then this would be an improper course of action. But we address this more explicitly in the fifth test.
Value for money: this is a key test and can at times be one of the most challenging to evaluate if there are non-monetised benefits. The VFM test should be applied as to how the proposals impact on the Exchequer as a whole, and not solely to the impact on Defra. Alternative proposals, or doing nothing, must be evaluated to see if they could deliver a better/equal quality or more cost effective outcome? The risk involved is also a consideration. You should engage our economists in undertaking a VFM analysi; ; they wil help ensure that we apply the Treasury’s green book guidance on investment appraisal rigorously..
Feasibility: can a proposal realistically be implemented effectively, sustainably and to the intended timescale? If a particular proposal is novel or untested, it may be appropriate to recommend a pilot trial. Equally, a degree of novelty and administrative complexity may be a warning sign that feasibility is a critical test that needs to be fully satisfied.
Affordability: this addresses the test of financial sustainability. Proposals must respect the Department’s spending Control Totals and agreed budgets and should not involve unaffordable longer term commitments. With continuing downward pressure on Departmental budgets for the foreseeable future, this test is unavoidable and the Accounting Officer must be assured that any short-term tactical fix (e.g. reprioritising an in-year budget) can be sustained in the longer term.

## Timeline
Timeline to Recommendation
#REF!
Date | No of Weeks | LPRG Activity | No of Weeks | Team Activity
Submission Deadline
#REF! |  |  |  | Submission first received
Total time taken (weeks) | 0 |  | 0
Average time taken (weeks) | #DIV/0! |  | #DIV/0!